## 1_区域边界_EB_MA
区域划分：第一大区/第二楼层/第三小区 (EB & MA)
EB: B2=柱子开始→柱子结束, B1=梁开始→柱子结束; 一楼以上(L2+)非CIS/CIST区=整段,楼板若放在L5 Transfer则按名内 at L#Zone 归还(-T区优先)。MA无地库(Deck/L1-L5),同用整段+L5归还。时长=日历天。工作量=区内各活动工程量合计。★黄底'✔已修订'=本次修正:EB.B2楼层原被误判为整段,已改回柱子开始→结束,时间段大幅缩短。
第一大区 Building | 第二楼层 Level | 第三小区 Zone | 小区全称 | 边界规则 | 区域开始 | 区域结束 | 时长 (天) | 工作量 (总) | 柱/梁/总 | 全区跨度 | 修订/复核 Rev./Flag
EB | B2 | 3.3 | EB2-3.3 (EB1S7, Slab B-3.3+3.5) | B2 柱子开始→柱子结束 | 2026-09-18 | 2026-09-28 | 10 天 | 7nos | 1/0/1 | 2026-09-18~2026-09-28 | ✔已修订
EB | B2 | EB2-2.1 | EB2-2.1 (EB1S2.1, Slab B-2.1(CJ1-1,2)) | B2 柱子开始→柱子结束 | 2026-06-17 | 2026-07-15 | 28 天 | 16nos | 1/0/5 | 2026-04-01~2026-10-23 | ✔已修订
EB | B2 | EB2-2.2 | EB2-2.2 (EB1S2.2, Slab B-2.2(CJ2)) | B2 柱子开始→柱子结束 | 2026-06-22 | 2026-06-30 | 8 天 | 8nos | 1/0/2 | 2026-04-09~2026-06-30 | ✔已修订
EB | B2 | EB2-2.3 | EB2-2.3 (EB1S2.3, Slab B-2.3(CJ3)) | B2 柱子开始→柱子结束 | 2026-07-01 | 2026-07-09 | 8 天 | 12nos | 1/0/2 | 2026-06-22~2026-07-09 | ✔已修订
EB | B2 | EB2-2.4 | EB2-2.4 (EB1S2.4, Slab B-2.4(CJ4)) | B2 柱子开始→柱子结束 | 2026-07-22 | 2026-07-30 | 8 天 | 7nos | 1/0/2 | 2026-07-13~2026-07-30 | ✔已修订
EB | B2 | EB2-3.1A-1 | EB2-3.1A-1 (EB1S5, Slab B-3.1) | B2 柱子开始→柱子结束 | 2026-08-03 | 2026-08-11 | 8 天 | 8nos | 1/0/2 | 2026-07-23~2026-08-11 | ✔已修订
EB | B2 | EB2-3.1A-2+3.2-2 | EB2-3.1A-2+3.2-2 (EB1S8, Slab B-3.4) | B2 柱子开始→柱子结束 | 2026-09-18 | 2026-09-28 | 10 天 | 10nos | 1/0/2 | 2026-09-18~2027-05-10 | ✔已修订
EB | B2 | EB2-3.2-1 | EB2-3.2-1 (EB1S6, Slab B-3.2) | B2 柱子开始→柱子结束 | 2026-08-12 | 2026-08-20 | 8 天 | 3nos | 1/0/1 | 2026-08-12~2026-08-20 | ✔已修订
EB | B2 | EB2-3.4+3.5 | EB2-3.4+3.5 | B2 柱子开始→柱子结束 | 2026-09-18 | 2026-09-28 | 10 天 | 2nos | 1/0/2 | 2026-09-18~2026-11-19 | ✔已修订
EB | B1 | S2.1 | EB1S2.1 (Slab B-2.1(CJ1-1,2), EB2-2.1) | B1 梁开始→柱子结束 | 2026-07-01 | 2026-07-29 | 28 天 | 2816m²+16nos | 1/1/7 | 2026-05-21~2026-10-23
EB | B1 | S2.2 | EB1S2.2 (Slab B-2.2(CJ2), EB2-2.2) | B1 梁开始→柱子结束 | — | 2026-07-29 | — | 1244m²+4nos | 1/0/3 | 2026-06-04~2026-07-29 | 无梁活动
EB | B1 | S2.3 | EB1S2.3 (Slab B-2.3(CJ3), EB2-2.3) | B1 梁开始→柱子结束 | — | 2026-07-30 | — | 1569m²+4nos | 1/0/3 | 2026-06-15~2026-07-30 | 无梁活动
EB | B1 | S2.4 | EB1S2.4 (Slab B-2.4(CJ4), EB2-2.4) | B1 梁开始→柱子结束 | 2026-07-31 | 2026-08-19 | 19 天 | 1108m²+9nos | 1/1/3 | 2026-06-24~2026-08-19
EB | B1 | S5 | EB1S5 (Slab B-3.1, EB2-3.1A-1) | B1 梁开始→柱子结束 | — | 2026-09-09 | — | 1137m²+2nos | 1/0/3 | 2026-07-03~2026-09-09 | 无梁活动
EB | B1 | S6 | EB1S6 (Slab B-3.2, EB2-3.2-1) | B1 梁开始→柱子结束 | 2026-08-21 | 2026-09-18 | 28 天 | 2089m²+10nos | 1/1/3 | 2026-08-21~2027-02-21
EB | B1 | S7 | EB1S7 (Slab B-3.3+3.5, EB2-3.3) | B1 梁开始→柱子结束 | 2026-09-29 | 2026-10-27 | 28 天 | 1367m²+18nos | 1/1/4 | 2026-09-29~2027-04-20
EB | B1 | S8 | EB1S8 (Slab B-3.4, EB2-3.1A-2+3.2-2) | B1 梁开始→柱子结束 | 2026-09-29 | 2026-11-16 | 48 天 | 2209m²+21nos | 2/1/7 | 2026-09-18~2027-03-31
EB | L1 | 4.1 | POD4.1 (ZSlabB2.2) | L1 柱子开始→柱子结束 | 2026-08-19 | 2026-09-01 | 13 天 | 770m²+27nos | 2/3/5 | 2026-07-30~2026-09-21
EB | L1 | 4.1CIS-T | POD4.1 CIST(ZSlabB2.1) | L1 柱子开始→柱子结束 | 2026-08-20 | 2026-09-11 | 22 天 | 1277m²+127nos | 2/3/9 | 2026-07-30~2027-01-19
EB | L1 | 4.2 | POD4.2 (ZSlabB2.3-1+ZSlab2.4-1) | L1 柱子开始→柱子结束 | 2026-09-07 | 2026-09-18 | 11 天 | 718m²+54nos | 2/3/5 | 2026-08-11~2026-10-01
EB | L1 | 4.2-T | POD4.2T(ZSlabB2.3-2) | L1 柱子开始→柱子结束 | 2026-08-18 | 2026-08-31 | 13 天 | 737m²+33nos | 2/3/5 | 2026-07-31~2026-09-14
EB | L1 | 4.3-T | POD4.3T (ZSlabB3.2) | L1 柱子开始→柱子结束 | 2026-10-20 | 2026-11-02 | 13 天 | 741m²+51nos | 2/3/5 | 2026-09-21~2026-11-18
EB | L1 | 4.3CIS-T | POD4.3CIST (ZSlabB3.1) | L1 柱子开始→柱子结束 | 2026-09-30 | 2026-10-13 | 13 天 | 493m²+46nos | 2/3/7 | 2026-09-10~2026-11-19
EB | L1 | 4.4 | POD4.4 (ZSlabB3.3) | L1 柱子开始→柱子结束 | 2026-11-12 | 2026-12-04 | 22 天 | 1209m²+64nos | 2/3/6 | 2026-10-28~2027-01-21
EB | L1 | 4.4-OT | POD4.4 OT (ZSlabB3.5+3.4) | L1 柱子开始→柱子结束 | 2027-01-07 | 2027-01-29 | 22 天 | 1328m²+130nos | 2/3/5 | 2026-12-23~2027-02-16
EB | L1 | B2.1 | Slab B-2.1 (EB1S2.1, EB2-2.1) | L1 柱子开始→柱子结束 | — | — | — | 1148m² | 0/0/2 | 2026-04-01~2026-04-22
EB | L1 | B2.2 | Slab B-2.2 (EB1S2.2, EB2-2.2) | L1 柱子开始→柱子结束 | — | — | — | 645m² | 0/0/1 | 2026-04-01~2026-04-10
EB | L1 | B2.3 | Slab B-2.3 (EB1S2.3, EB2-2.3) | L1 柱子开始→柱子结束 | — | — | — | 911m² | 0/0/1 | 2026-04-13~2026-05-20
EB | L1 | B2.4 | Slab B-2.4 (EB1S2.4, EB2-2.4) | L1 柱子开始→柱子结束 | — | — | — | 491m² | 0/0/1 | 2026-05-21~2026-06-12
EB | L1 | B3.1 | Slab B-3.1 (EB1S5, EB2-3.1A-1) | L1 柱子开始→柱子结束 | — | — | — | 1875m² | 0/0/2 | 2026-06-15~2026-07-03
EB | L1 | B3.2 | Slab B-3.2 (EB1S6, EB2-3.2-1) | L1 柱子开始→柱子结束 | — | — | — | 730m² | 0/0/1 | 2027-02-01~2027-02-18
EB | L1 | B3.3+3.5 | Slab B-3.3+3.5 (EB1S7, EB2-3.3) | L1 柱子开始→柱子结束 | — | — | — | 2529m² | 0/0/2 | 2027-02-19~2027-04-21
EB | L1 | B3.4 | Slab B-3.4 (EB1S8, EB2-3.1A-2+3.2-2) | L1 柱子开始→柱子结束 | — | — | — | 311m² | 0/0/1 | 2027-03-11~2027-03-30
EB | L2 | 4.1 | POD4.1 | L2 整段(含L5归还板) | 2026-09-22 | 2027-04-16 | 206 天 | 589m²+17nos | 2/2/5 | 2026-09-22~2027-04-16
EB | L2 | 4.1CIS-T | POD4.1CIST | L2 整段 | 2026-09-30 | 2026-12-30 | 91 天 | 1272m²+88nos | 2/2/8 | 2026-09-30~2026-12-30
EB | L2 | 4.2 | POD4.2 | L2 整段 | 2026-09-30 | 2026-10-26 | 26 天 | 33nos | 2/2/4 | 2026-09-30~2026-10-26
EB | L2 | 4.2-T | POD4.2T | L2 整段(含L5归还板) | 2026-09-15 | 2027-03-09 | 175 天 | 882m²+30nos | 2/2/5 | 2026-09-15~2027-03-09
EB | L2 | 4.3-T | POD4.3T | L2 整段(含L5归还板) | 2026-11-19 | 2027-04-19 | 151 天 | 943m²+40nos | 2/2/5 | 2026-11-19~2027-04-19
EB | L2 | 4.3CIS-T | POD4.3CIST | L2 整段 | 2026-10-30 | 2027-01-11 | 73 天 | 374m²+34nos | 2/2/7 | 2026-10-30~2027-01-11
EB | L2 | 4.4 | POD4.4 | L2 整段(含L5归还板) | 2026-12-18 | 2027-04-22 | 125 天 | 750m²+58nos | 2/2/5 | 2026-12-18~2027-04-22
EB | L3 | 4.1 | POD4.1 | L3 整段(含L5归还板) | 2026-10-26 | 2027-05-28 | 214 天 | 589m²+17nos | 2/2/5 | 2026-10-26~2027-05-28
EB | L3 | 4.1CIS-T | POD4.1CIST | L3 整段 | 2026-12-01 | 2027-02-19 | 80 天 | 1272m²+88nos | 2/2/8 | 2026-12-01~2027-02-19
EB | L3 | 4.2 | POD4.2 | L3 整段 | 2026-10-27 | 2026-11-20 | 24 天 | 33nos | 2/2/4 | 2026-10-27~2026-11-20
EB | L3 | 4.2-T | POD4.2T | L3 整段(含L5归还板) | 2026-10-12 | 2027-04-07 | 177 天 | 882m²+30nos | 2/2/5 | 2026-10-12~2027-04-07
EB | L3 | 4.3-T | POD4.3T | L3 整段(含L5归还板) | 2026-12-30 | 2027-05-18 | 139 天 | 943m²+40nos | 2/2/5 | 2026-12-30~2027-05-18
EB | L3 | 4.3CIS-T | POD4.3CIST | L3 整段 | 2026-12-10 | 2027-03-03 | 83 天 | 374m²+34nos | 2/2/7 | 2026-12-10~2027-03-03
EB | L3 | 4.4 | POD4.4 | L3 整段(含L5归还板) | 2027-01-25 | 2027-05-21 | 116 天 | 750m²+58nos | 2/2/5 | 2027-01-25~2027-05-21
EB | L4 | 4.1 | POD4.1 | L4 整段 | 2026-11-23 | 2027-01-22 | 60 天 | 589m²+17nos | 2/2/5 | 2026-11-23~2027-01-22
EB | L4 | 4.1CIS-T | POD4.1CIST | L4 整段 | 2027-01-23 | 2027-04-13 | 80 天 | 1272m²+88nos | 2/2/8 | 2027-01-23~2027-04-13
EB | L4 | 4.2 | POD4.2 | L4 整段 | 2026-12-02 | 2027-01-28 | 57 天 | 887m²+33nos | 2/2/5 | 2026-12-02~2027-01-28
EB | L4 | 4.2-T | POD4.2T | L4 整段 | 2026-11-09 | 2026-12-03 | 24 天 | 30nos | 2/2/4 | 2026-11-09~2026-12-03
EB | L4 | 4.3-T | POD4.3T | L4 整段 | 2026-12-30 | 2027-03-19 | 79 天 | 943m²+40nos | 2/2/5 | 2026-12-30~2027-03-19
EB | L4 | 4.3CIS-T | POD4.3CIST | L4 整段 | 2027-01-29 | 2027-04-23 | 84 天 | 374m²+34nos | 2/2/7 | 2027-01-29~2027-04-23
EB | L4 | 4.4 | POD4.4 | L4 整段 | 2027-03-05 | 2027-04-29 | 55 天 | 750m²+58nos | 2/2/5 | 2027-03-05~2027-04-29
EB | L5 | 1 | 4.2T | L5 整段 | 2026-12-04 | 2027-02-11 | 69 天 | 323m² | 0/0/1 | 2026-12-04~2027-02-11
EB | L5 | 2 | 4.4 | L5 整段 | 2027-03-22 | 2027-05-28 | 67 天 | 2616m² | 0/0/3 | 2027-03-22~2027-05-28
EB | L5 | 4.1 | POD4.1 | L5 整段 | 2027-04-16 | 2027-05-27 | 41 天 | 1nos | 0/0/2 | 2027-04-16~2027-05-27
EB | L5 | 4.1CIS | POD4.1CIS | L5 整段 | 2027-01-25 | 2027-03-05 | 39 天 | 589m² | 0/0/1 | 2027-01-25~2027-03-05
EB | L5 | 4.1CIST | POD4.1CIST | L5 整段 | 2027-03-19 | 2027-05-27 | 69 天 | 1272m² | 0/0/1 | 2027-03-19~2027-05-27
EB | L5 | 4.3 | POD4.3 | L5 整段 | 2027-04-30 | 2027-05-19 | 19 天 | — | 0/1/1 | 2027-04-30~2027-05-19
MA | Deck | Deck | Marine Deck | Deck 全区跨度 | 2026-04-18 | 2026-08-28 | 132 天 | 132nos | 0/0/8 | 2026-04-18~2026-08-28
MA | Deck | ZC1 | ZC1(CZ2-2,4-2,CD4-P14,P13,CD1-P1,P2,P3,CD2-P4) | Deck 全区跨度 | 2026-04-01 | 2026-08-21 | 142 天 | 10366m²+20nos | 0/0/21 | 2026-04-01~2026-08-21
MA | Deck | ZC2.1+2.2 | ZC2.1+2.2(CZ6-2,7-2,5,CD2-P5,P6,CD3-P7,P8,P9,P10,CD2&3-P11) | Deck 全区跨度 | 2026-08-05 | 2026-12-21 | 138 天 | 9366m² | 0/0/24 | 2026-08-05~2026-12-21
MA | Deck | ZC3.1a+3.2 | ZC3.1a+3.2(CZ2-1,3,4-1) | Deck 全区跨度 | 2026-08-24 | 2026-12-28 | 126 天 | 5462m² | 0/0/21 | 2026-08-24~2026-12-28
MA | Deck | ZC3.1b | ZC3.1b(CZ6-1,7-1) | Deck 全区跨度 | 2026-08-24 | 2027-01-11 | 140 天 | 9496m² | 0/0/24 | 2026-08-24~2027-01-11
MA | L1 | 1.1 | POD1.1(CD4-P14) | L1 柱子开始→柱子结束 | 2026-10-09 | 2026-11-06 | 28 天 | 50nos | 2/2/5 | 2026-08-05~2026-11-26
MA | L1 | 1.2 | POD1.2(CD4-P13,CD1-P1,P3-1) | L1 柱子开始→柱子结束 | 2026-07-06 | 2026-08-03 | 28 天 | 70nos | 2/2/7 | 2026-06-16~2026-08-25
MA | L1 | 1.2-T | POD1.2T(CD1-P2,P3-2) | L1 柱子开始→柱子结束 | 2026-07-06 | 2026-08-04 | 29 天 | 99nos | 2/2/4 | 2026-07-06~2026-08-31
MA | L1 | 3.1-T | POD3.1T(CD2-P4-2,P5-2,P6-2) | L1 柱子开始→柱子结束 | 2026-10-07 | 2026-10-29 | 22 天 | 54nos | 2/2/5 | 2026-08-24~2026-11-13
MA | L1 | 3.1CIS-T | POD3.1CIST(CD2&3-P11) | L1 柱子开始→柱子结束 | 2026-09-14 | 2026-09-30 | 16 天 | 46nos | 2/2/8 | 2026-09-05~2026-10-28
MA | L1 | 3.2 | POD3.2(CD2-P12,P5-1,P6-1) | L1 柱子开始→柱子结束 | 2026-10-18 | 2026-11-03 | 16 天 | 62nos | 2/2/7 | 2026-08-29~2026-12-08
MA | L1 | 3.2-T | POD3.2T(CD2-P4-1) | L1 柱子开始→柱子结束 | 2026-10-19 | 2026-11-12 | 24 天 | 11nos | 2/2/4 | 2026-10-19~2026-12-02
MA | L1 | 3.3-T | POD3.3T(CD3-P7-2,P8-3) | L1 柱子开始→柱子结束 | 2026-10-14 | 2026-10-27 | 13 天 | 20nos | 2/2/5 | 2026-09-09~2026-11-10
MA | L1 | 3.3CIS-T | POD3.3CIST(CD3-P10) | L1 柱子开始→柱子结束 | 2026-08-25 | 2026-09-25 | 31 天 | 49nos | 2/2/7 | 2026-07-26~2026-10-15
MA | L1 | 3.4 | POD3.4(CD3-P7-1,P8-1,P9-1) | L1 柱子开始→柱子结束 | 2026-10-29 | 2026-11-11 | 13 天 | 26nos | 2/2/5 | 2026-10-07~2026-12-01
MA | L1 | 3.4-T | POD3.4T(CD3-P8-2,P9-2) | L1 柱子开始→柱子结束 | 2026-10-29 | 2026-11-11 | 13 天 | 40nos | 2/2/4 | 2026-10-29~2026-12-01
MA | L1 | TOP SLAB | Top Slab | L1 柱子开始→柱子结束 | — | — | — | 15867m² | 0/0/12 | 2026-07-06~2027-03-25
MA | L2 | 1.1 | POD1.1 | L2 整段(含L5归还板) | 2026-11-27 | 2027-04-13 | 137 天 | 540m²+50nos | 2/2/5 | 2026-11-27~2027-04-13
MA | L2 | 1.2 | POD1.2 | L2 整段 | 2026-08-24 | 2026-10-15 | 52 天 | 62nos | 2/2/6 | 2026-08-24~2026-10-15
MA | L2 | 1.2-T | POD1.2T | L2 整段(含L5归还板) | 2026-09-01 | 2027-04-02 | 213 天 | 2315m²+111nos | 2/2/5 | 2026-09-01~2027-04-02
MA | L2 | 3.1-T | POD3.1T | L2 整段(含L5归还板) | 2026-11-16 | 2027-04-20 | 155 天 | 1096m²+54nos | 2/2/5 | 2026-11-16~2027-04-20
MA | L2 | 3.1CIS-T | POD3.1CIST | L2 整段 | 2026-10-21 | 2026-12-09 | 49 天 | 883m²+46nos | 2/2/8 | 2026-10-21~2026-12-09
MA | L2 | 3.2 | POD3.2 | L2 整段 | 2026-11-18 | 2027-01-28 | 71 天 | 68nos | 2/2/6 | 2026-11-18~2027-01-28
MA | L2 | 3.2-T | POD3.2T | L2 整段(含L5归还板) | 2026-12-03 | 2027-04-23 | 141 天 | 1088m²+11nos | 2/2/5 | 2026-12-03~2027-04-23
MA | L2 | 3.3-T | POD3.3T | L2 整段(含L5归还板) | 2026-11-11 | 2027-03-12 | 121 天 | 415m²+22nos | 2/2/5 | 2026-11-11~2027-03-12
MA | L2 | 3.3CIS-T | POD3.3CIST | L2 整段 | 2026-10-02 | 2026-12-14 | 73 天 | 730m²+49nos | 2/2/7 | 2026-10-02~2026-12-14
MA | L2 | 3.4 | POD3.4 | L2 整段 | 2026-12-02 | 2027-01-04 | 33 天 | 20nos | 2/2/4 | 2026-12-02~2027-01-04
MA | L2 | 3.4-T | POD3.4T | L2 整段(含L5归还板) | 2026-12-02 | 2027-04-20 | 139 天 | 933m²+42nos | 2/2/5 | 2026-12-02~2027-04-20
MA | L3 | 1.1 | POD1.1 | L3 整段(含L5归还板) | 2027-01-15 | 2027-05-03 | 108 天 | 540m²+50nos | 2/2/5 | 2027-01-15~2027-05-03
MA | L3 | 1.2 | POD1.2 | L3 整段 | 2026-10-12 | 2026-12-07 | 56 天 | 52nos | 2/2/6 | 2026-10-12~2026-12-07
MA | L3 | 1.2-T | POD1.2T | L3 整段(含L5归还板) | 2026-11-03 | 2027-04-22 | 170 天 | 2315m²+109nos | 2/2/5 | 2026-11-03~2027-04-22
MA | L3 | 3.1-T | POD3.1T | L3 整段(含L5归还板) | 2026-12-24 | 2027-05-10 | 137 天 | 1096m²+54nos | 2/2/5 | 2026-12-24~2027-05-10
MA | L3 | 3.1CIS-T | POD3.1CIST | L3 整段 | 2026-12-08 | 2027-01-28 | 51 天 | 883m²+46nos | 2/2/8 | 2026-12-08~2027-01-28
MA | L3 | 3.2 | POD3.2 | L3 整段 | 2026-12-25 | 2027-03-22 | 87 天 | 68nos | 2/2/6 | 2026-12-25~2027-03-22
MA | L3 | 3.2-T | POD3.2T | L3 整段(含L5归还板) | 2027-01-06 | 2027-05-07 | 121 天 | 1088m²+11nos | 2/2/5 | 2027-01-06~2027-05-07
MA | L3 | 3.3-T | POD3.3T | L3 整段(含L5归还板) | 2026-12-09 | 2027-04-01 | 113 天 | 415m²+22nos | 2/2/5 | 2026-12-09~2027-04-01
MA | L3 | 3.3CIS-T | POD3.3CIST | L3 整段 | 2026-11-11 | 2027-02-10 | 91 天 | 730m²+49nos | 2/2/7 | 2026-11-11~2027-02-10
MA | L3 | 3.4 | POD3.4 | L3 整段 | 2027-01-05 | 2027-02-05 | 31 天 | 20nos | 2/2/4 | 2027-01-05~2027-02-05
MA | L3 | 3.4-T | POD3.4T | L3 整段(含L5归还板) | 2027-01-05 | 2027-05-10 | 125 天 | 933m²+44nos | 2/2/5 | 2027-01-05~2027-05-10
MA | L4 | 1.1 | POD1.1 | L4 整段 | 2027-03-05 | 2027-03-24 | 19 天 | 540m² | 0/0/1 | 2027-03-05~2027-03-24
MA | L4 | 1.2 | POD1.2 | L4 整段 | 2026-12-08 | 2027-03-15 | 97 天 | 2315m²+62nos | 2/2/7 | 2026-12-08~2027-03-15
MA | L4 | 1.2-T | POD1.2T | L4 整段 | 2027-01-06 | 2027-03-08 | 61 天 | 109nos | 2/2/4 | 2027-01-06~2027-03-08
MA | L4 | 3.1-T | POD3.1T | L4 整段 | 2027-02-02 | 2027-03-31 | 57 天 | 1096m²+54nos | 2/2/5 | 2027-02-02~2027-03-31
MA | L4 | 3.1CIS-T | POD3.1CIST | L4 整段 | 2027-01-15 | 2027-03-19 | 63 天 | 883m²+46nos | 2/2/8 | 2027-01-15~2027-03-19
MA | L4 | 3.2 | POD3.2 | L4 整段 | 2027-02-08 | 2027-05-12 | 93 天 | 1088m²+68nos | 2/2/7 | 2027-02-08~2027-05-12
MA | L4 | 3.2-T | POD3.2T | L4 整段 | 2027-02-09 | 2027-03-12 | 31 天 | 11nos | 2/2/4 | 2027-02-09~2027-03-12
MA | L4 | 3.3-T | POD3.3T | L4 整段 | 2027-01-06 | 2027-02-22 | 47 天 | 415m²+22nos | 2/2/5 | 2027-01-06~2027-02-22
MA | L4 | 3.3CIS-T | POD3.3CIST | L4 整段 | 2026-12-21 | 2027-04-09 | 109 天 | 730m²+49nos | 2/2/7 | 2026-12-21~2027-04-09
MA | L4 | 3.4 | POD3.4 | L4 整段 | 2027-02-08 | 2027-03-31 | 51 天 | 933m²+20nos | 2/2/5 | 2027-02-08~2027-03-31
MA | L4 | 3.4-T | POD3.4T | L4 整段 | 2027-02-08 | 2027-03-11 | 31 天 | 44nos | 2/2/4 | 2027-02-08~2027-03-11
MA | L5 | 1.1 | 1.1 | L5 整段 | — | — | — | — | 0/0/0 | ~
MA | L5 | 1.2 | POD1.2 | L5 整段 | 2027-03-16 | 2027-04-26 | 41 天 | 1240m² | 0/0/1 | 2027-03-16~2027-04-26
MA | L5 | 1.2-T | POD1.2T | L5 整段 | 2027-03-09 | 2027-05-17 | 69 天 | 1075m² | 0/0/1 | 2027-03-09~2027-05-17
MA | L5 | 3.1-T | POD3.1T | L5 整段 | 2027-04-01 | 2027-05-12 | 41 天 | 1096m² | 0/0/1 | 2027-04-01~2027-05-12
MA | L5 | 3.1CIS-T | POD3.1CIST | L5 整段 | 2027-03-22 | 2027-05-28 | 67 天 | 883m² | 0/0/1 | 2027-03-22~2027-05-28
MA | L5 | 3.2 | POD3.2 | L5 整段 | 2027-04-12 | 2027-05-21 | 39 天 | 953m² | 0/0/1 | 2027-04-12~2027-05-21
MA | L5 | 3.2-T | POD3.2T | L5 整段 | 2027-03-15 | 2027-04-23 | 39 天 | 135m² | 0/0/1 | 2027-03-15~2027-04-23
MA | L5 | 3.3-T | 3.3-T | L5 整段 | — | — | — | — | 0/0/0 | ~
MA | L5 | 3.3CIS-T | POD3.3CIST | L5 整段 | 2027-04-10 | 2027-05-29 | 49 天 | 730m² | 0/0/1 | 2027-04-10~2027-05-29
MA | L5 | 3.4 | POD3.4 | L5 整段 | 2027-04-01 | 2027-05-12 | 41 天 | 659m² | 0/0/1 | 2027-04-01~2027-05-12
MA | L5 | 3.4-T | POD3.4T | L5 整段 | 2027-03-12 | 2027-05-20 | 69 天 | 274m² | 0/0/1 | 2027-03-12~2027-05-20

## 2_区域边界_NB
NB 区域划分：分上下两部分
地库 B2/B1=挖土开始→柱子结束; 下半部 L1=柱子开始→柱子结束; 上半部 L2-L5=该小区整段(最早开始→最晚结束)。注:非CIS的2/3楼楼板原放在L5 Transfer WBS,已按活动名内 at L2/L3 Zone 归还至真实楼层;CIS/CIST楼板在本层。时长=日历天。工作量=区内各活动工程量合计。
部分 Part | 楼层 Level | 小区 Zone | 小区全称 | 边界规则 | 区域开始 | 区域结束 | 时长 (天) | 工作量 (总) | 挖/柱/梁/板 | 全区跨度 | 复核 Flag
下部 地库 | B2 | B2-S1+1a | B2-S1+1a (C-02, ZSlab 8+8A) | B2 挖土开始→柱子结束 | 2026-08-30 | 2027-01-04 | 127 天 | 1635m²+8200m³+26nos | 2/2/0/2 | 2026-08-27~2027-01-25
下部 地库 | B2 | B2-S10 | B2-S10 (B-02) | B2 挖土开始→柱子结束 | 2026-09-24 | 2026-12-28 | 95 天 | 955m²+4900m³+22nos | 1/1/0/1 | 2026-09-21~2026-12-28
下部 地库 | B2 | B2-S11 | B2-S11 (B-03) | B2 挖土开始→柱子结束 | 2026-06-24 | 2026-10-08 | 106 天 | 610m²+3100m³+9nos | 1/1/0/1 | 2026-06-19~2026-12-31
下部 地库 | B2 | B2-S12 | B2-S12 (B-04+04A) | B2 挖土开始→柱子结束 | 2026-08-06 | 2026-12-01 | 117 天 | 1291m²+6600m³+30nos | 1/1/0/1 | 2026-08-03~2026-12-25
下部 地库 | B2 | B2-S13 | B2-S13 (A-02+B-01) | B2 挖土开始→柱子结束 | 2026-08-07 | 2026-11-26 | 111 天 | 695m²+3400m³+18nos | 1/1/0/1 | 2026-08-04~2026-11-26
下部 地库 | B2 | B2-S14 | B2-S14 (A-01+03) | B2 挖土开始→柱子结束 | 2026-07-06 | 2026-10-29 | 115 天 | 622m²+3200m³+18nos | 1/1/0/1 | 2026-07-01~2026-10-29
下部 地库 | B2 | B2-S2+S2a | B2-S2+S2a (C-01a+b, ZSlab 7) | B2 挖土开始→柱子结束 | 2026-07-31 | 2027-03-31 | 243 天 | 1711m²+8700m³+26nos | 2/2/0/2 | 2026-07-17~2027-03-31
下部 地库 | B2 | B2-S3 | B2-S3 (E-01, ZSlab 12) | B2 挖土开始→柱子结束 | 2026-08-07 | 2026-12-11 | 126 天 | 1354m²+6800m³+20nos | 1/1/0/1 | 2026-08-04~2027-03-05
下部 地库 | B2 | B2-S4 | B2-S4 (F-01, ZSlab 13) | B2 挖土开始→柱子结束 | 2026-10-08 | 2027-02-05 | 120 天 | 1308m²+6600m³+20nos | 1/1/0/1 | 2026-10-05~2027-03-03
下部 地库 | B2 | B2-S5 | B2-S5 (F-02, ZSlab 10) | B2 挖土开始→柱子结束 | 2026-10-12 | 2027-01-28 | 108 天 | 1496m²+7500m³+28nos | 1/1/0/1 | 2026-10-09~2027-02-23
下部 地库 | B2 | B2-S6+6a | B2-S6+6a (D-02, ZSlab 9a+9b) | B2 挖土开始→柱子结束 | 2026-10-24 | 2027-03-05 | 132 天 | 1465m²+7100m³+23nos | 2/2/0/2 | 2026-10-21~2027-05-28
下部 地库 | B2 | B2-S7 | B2-S7 (D-01, ZSlab 11a+11b) | B2 挖土开始→柱子结束 | 2026-10-26 | 2027-03-01 | 126 天 | 1030m²+5100m³+13nos | 1/1/0/1 | 2026-10-21~2027-05-24
下部 地库 | B2 | B2-S8 | B2-S8 (A-05+06) | B2 挖土开始→柱子结束 | 2026-09-18 | 2026-12-29 | 102 天 | 989m²+4900m³+24nos | 1/1/0/1 | 2026-09-15~2026-12-29
下部 地库 | B2 | B2-S8a+14a+13a | B2-S8a+14a+13a (A-07) | B2 挖土开始→柱子结束 | 2026-07-23 | 2026-12-10 | 140 天 | 1401m²+7200m³+41nos | 3/3/0/3 | 2026-07-20~2026-12-10
下部 地库 | B2 | B2-S9 | B2-S9 (A-04) | B2 挖土开始→柱子结束 | 2026-08-21 | 2026-12-16 | 117 天 | 871m²+4300m³+24nos | 1/1/0/1 | 2026-08-18~2026-12-16
下部 地库 | B1 | A-01+03 | A-01+03 (B2-S14) | B1 挖土开始→柱子结束 | — | 2026-08-27 | — | 971m²+16nos | 0/1/1/1 | 2026-04-01~2026-08-27 | 无独立挖土(挂邻区)
下部 地库 | B1 | A-02+B-01 | A-02+B-01 (B2-S13) | B1 挖土开始→柱子结束 | — | 2026-08-11 | — | 1180m²+20nos | 0/1/1/1 | 2026-04-01~2026-08-11 | 无独立挖土(挂邻区)
下部 地库 | B1 | A-04 | A-04 (B2-S9) | B1 挖土开始→柱子结束 | — | 2026-09-25 | — | 563m²+7nos | 0/1/1/1 | 2026-07-01~2026-09-25 | 无独立挖土(挂邻区)
下部 地库 | B1 | A-05+06 | A-05+06 (B2-S8) | B1 挖土开始→柱子结束 | — | 2026-09-23 | — | 999m²+23nos | 0/2/2/2 | 2026-04-01~2026-09-23 | 无独立挖土(挂邻区)
下部 地库 | B1 | A-07 | A-07 (B2-S8a+14a+13a) | B1 挖土开始→柱子结束 | — | 2026-08-14 | — | 571m²+12nos | 0/1/1/1 | 2026-04-01~2026-08-14 | 无独立挖土(挂邻区)
下部 地库 | B1 | B-02 | B-02 (B2-S10) | B1 挖土开始→柱子结束 | — | 2026-08-27 | — | 720m²+9nos | 0/1/1/1 | 2026-04-01~2026-08-27 | 无独立挖土(挂邻区)
下部 地库 | B1 | B-03 | B-03 (B2-S11) | B1 挖土开始→柱子结束 | — | 2026-08-12 | — | 1201m²+41nos | 0/1/1/1 | 2026-04-01~2026-12-30 | 无独立挖土(挂邻区)
下部 地库 | B1 | B-04+04A | B-04+04A (B2-S12) | B1 挖土开始→柱子结束 | — | 2026-07-16 | — | 1121m²+51nos | 0/2/2/2 | 2026-04-01~2026-07-16 | 无独立挖土(挂邻区)
下部 地库 | B1 | C-01a+b | C-01a+b (ZSlab 7, B2-S2+S2a) | B1 挖土开始→柱子结束 | 2026-05-19 | 2026-09-14 | 118 天 | 1343m²+13000m³+23nos | 1/1/1/1 | 2026-04-01~2027-04-06
下部 地库 | B1 | C-02 | C-02 (ZSlab 8+8A, B2-S1+1a) | B1 挖土开始→柱子结束 | 2026-07-01 | 2026-10-23 | 114 天 | 1457m²+21000m³+35nos | 1/1/1/1 | 2026-06-26~2027-04-30
下部 地库 | B1 | D-01 | D-01 (ZSlab 11a+11b, B2-S7) | B1 挖土开始→柱子结束 | 2026-08-01 | 2026-11-26 | 117 天 | 1349m²+11000m³+35nos | 1/2/1/1 | 2026-07-29~2026-11-26
下部 地库 | B1 | D-02 | D-02 (ZSlab 9a+9b, B2-S6+6a) | B1 挖土开始→柱子结束 | 2026-09-21 | 2027-01-15 | 116 天 | 1611m²+13200m³+29nos | 1/1/1/1 | 2026-09-18~2027-01-15
下部 地库 | B1 | E-01 | E-01 (ZSlab 12, B2-S3) | B1 挖土开始→柱子结束 | 2026-07-14 | 2026-11-09 | 118 天 | 1415m²+13800m³+13nos | 2/1/1/1 | 2026-04-01~2026-11-09
下部 地库 | B1 | F-01 | F-01 (ZSlab 13, B2-S4) | B1 挖土开始→柱子结束 | 2026-07-24 | 2026-12-01 | 130 天 | 1941m²+19000m³+23nos | 1/1/1/1 | 2026-07-21~2027-05-26
下部 地库 | B1 | F-02 | F-02 (ZSlab 10, B2-S5) | B1 挖土开始→柱子结束 | 2026-09-07 | 2026-12-07 | 91 天 | 1001m²+9000m³+40nos | 1/1/1/1 | 2026-09-04~2027-05-18
下部 地库 | B1 | S-1 | S-1(A-01+03) | B1 挖土开始→柱子结束 | — | 2026-11-20 | — | 976m²+22nos | 0/1/1/1 | 2026-09-24~2026-11-20 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-2 | S-2(A-02+B-01+04+04A) | B1 挖土开始→柱子结束 | — | 2026-10-08 | — | 40nos | 0/1/1/1 | 2026-08-12~2026-10-08 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-3 | S-3(B-02+03) | B1 挖土开始→柱子结束 | — | 2026-11-24 | — | 1915m²+70nos | 0/1/1/1 | 2026-08-28~2026-11-24 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-4 | S-4(A-04) | B1 挖土开始→柱子结束 | — | 2026-11-24 | — | 1514m²+24nos | 0/1/1/1 | 2026-09-28~2026-11-24 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-5 | S-5(F-02, ZSlab10) | B1 挖土开始→柱子结束 | — | 2027-02-03 | — | 1510m²+41nos | 0/1/1/1 | 2026-12-08~2027-02-03 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-6 | S-6(E-01, ZSlab12) | B1 挖土开始→柱子结束 | — | 2027-02-05 | — | 1364m²+30nos | 0/1/1/1 | 2026-12-10~2027-02-05 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-7 | S-7(D-01,ZSlab11a+b) | B1 挖土开始→柱子结束 | — | 2027-01-25 | — | 1539m²+47nos | 0/1/1/1 | 2026-11-27~2027-01-25 | 无独立挖土(挂邻区)
下部 地库 | B1 | S-8 | S-8(D-02, ZSlab9a+b) | B1 挖土开始→柱子结束 | — | 2027-04-20 | — | 836m²+9nos | 0/1/1/1 | 2027-02-08~2027-04-20 | 无独立挖土(挂邻区)
下半部 | L1 | 2.1 | POD2.1(ZSlab7-1, C-01b, B2-S2-2) | L1 柱子开始→柱子结束 | 2026-06-18 | 2026-07-01 | 13 天 | 373m²+33nos | 0/2/3/1 | 2026-04-01~2026-07-15
下半部 | L1 | 2.1-T | POD2.1T(ZSlab7-2, C-02-3, B2-S2-1+S2a) | L1 柱子开始→柱子结束 | 2026-06-04 | 2026-06-17 | 13 天 | 524m²+15nos | 0/2/3/1 | 2026-04-01~2026-08-17
下半部 | L1 | 2.1CIS | POD2.1CIS(ZSlab7-3, C-01a) | L1 柱子开始→柱子结束 | 2026-06-22 | 2026-07-03 | 11 天 | 518m²+86nos | 0/2/3/1 | 2026-04-01~2026-07-28
下半部 | L1 | 2.1CIS-T | POD2.1CIST(ZSlab7-4, C-01a, S2a) | L1 柱子开始→柱子结束 | 2026-06-08 | 2026-06-19 | 11 天 | 153m²+11nos | 0/2/3/1 | 2026-04-01~2026-07-15
下半部 | L1 | 2.2 | POD2.2(ZSlab8-1, C-02-1, B2-S1+1a) | L1 柱子开始→柱子结束 | 2026-10-07 | 2026-10-20 | 13 天 | 218m²+40nos | 0/2/3/1 | 2026-06-04~2026-11-03
下半部 | L1 | 2.2-T | POD2.2T(ZSlab8-2, C-02-2, B2-S1+1a) | L1 柱子开始→柱子结束 | 2026-09-01 | 2026-09-17 | 16 天 | 634m²+88nos | 0/2/3/1 | 2026-05-05~2026-10-15
下半部 | L1 | 2.3-T | POD2.3T(ZSlab13,F-01-1, B2-S4-1) | L1 柱子开始→柱子结束 | 2026-05-05 | 2026-05-18 | 13 天 | 1174m²+76nos | 0/2/3/1 | 2026-04-01~2026-06-05
下半部 | L1 | 2.3CIS-T | POD2.3CIST(ZSlab13,F-01-2, B2-S4-2) | L1 柱子开始→柱子结束 | 2026-05-11 | 2026-05-22 | 11 天 | 501m²+46nos | 0/2/3/1 | 2026-04-21~2026-07-21
下半部 | L1 | 2.4 | POD2.4(ZSlab8A-1+ZSlab12-1, E-01-1, B2-S3-1) | L1 柱子开始→柱子结束 | — | — | — | 6nos | 0/0/1/0 | 2027-01-08~2027-01-18 | 缺开始锚点
下半部 | L1 | 2.4-T | POD2.4T(ZSlab8A-2+ZSlab12-2, E-01-2, B2-S3-2) | L1 柱子开始→柱子结束 | 2026-09-01 | 2026-09-14 | 13 天 | 1347m²+59nos | 0/2/3/1 | 2026-07-03~2026-12-09
下半部 | L1 | 2.6CIS | POD2.6CIS(ZSlab10-1, F-02-1, B2-S5-1) | L1 柱子开始→柱子结束 | 2026-08-10 | 2026-08-21 | 11 天 | 956m²+26nos | 0/2/3/1 | 2026-07-03~2026-09-18
下半部 | L1 | 2.6CIS-T | POD2.6CIST(ZSlab10-2, F-02-2, B2-S5-2) | L1 柱子开始→柱子结束 | 2026-07-03 | 2026-07-27 | 24 天 | 850m²+48nos | 0/2/3/1 | 2026-05-05~2026-09-03
上半部 | L2 | 2.1 | POD2.1 | L2 整段 | 2026-07-07 | 2026-09-23 | 78 天 | 5nos | 0/2/2/0 | 2026-07-07~2026-09-23
上半部 | L2 | 2.1-T | POD2.1T | L2 整段(含L5归还板) | 2026-08-06 | 2027-03-17 | 223 天 | 854m²+14nos | 0/2/2/2 | 2026-08-06~2027-03-17
上半部 | L2 | 2.1CIS | POD2.1CIS | L2 整段 | 2026-07-29 | 2026-10-06 | 69 天 | 559m²+67nos | 0/2/2/1 | 2026-07-29~2026-10-06
上半部 | L2 | 2.1CIS-T | POD2.1CIST | L2 整段 | 2026-09-05 | 2026-10-14 | 39 天 | 159m²+8nos | 0/2/2/1 | 2026-09-05~2026-10-14
上半部 | L2 | 2.2 | POD2.2 | L2 整段 | 2026-11-13 | 2026-12-10 | 27 天 | 46nos | 0/2/2/0 | 2026-11-13~2026-12-10
上半部 | L2 | 2.2-T | POD2.2T | L2 整段(含L5归还板) | 2026-10-16 | 2027-03-22 | 157 天 | 1413m²+95nos | 0/2/2/1 | 2026-10-16~2027-03-22
上半部 | L2 | 2.3-T | POD2.3T | L2 整段(含L5归还板) | 2026-06-08 | 2027-01-19 | 225 天 | 1173m²+68nos | 0/2/2/1 | 2026-06-08~2027-01-19
上半部 | L2 | 2.3CIS-T | POD2.3CIST | L2 整段 | 2026-07-22 | 2026-10-12 | 82 天 | 501m²+45nos | 0/2/2/1 | 2026-07-22~2026-10-12
上半部 | L2 | 2.4 | POD2.4 | L2 整段 | 2027-01-19 | 2027-02-25 | 37 天 | 521m²+6nos | 0/0/1/1 | 2027-01-19~2027-02-25
上半部 | L2 | 2.4-T | POD2.4T | L2 整段(含L5归还板) | 2026-10-05 | 2027-03-11 | 157 天 | 700m²+54nos | 0/2/2/1 | 2026-10-05~2027-03-11
上半部 | L2 | 2.6CIS | POD2.6CIS | L2 整段 | 2026-09-21 | 2026-12-11 | 81 天 | 476m²+18nos | 0/2/2/1 | 2026-09-21~2026-12-11
上半部 | L2 | 2.6CIS-T | POD2.6CIST | L2 整段 | 2026-08-17 | 2026-10-16 | 60 天 | 794m²+35nos | 0/2/2/1 | 2026-08-17~2026-10-16
上半部 | L3 | 2.1 | POD2.1 | L3 整段 | 2026-08-18 | 2026-11-06 | 80 天 | 5nos | 0/2/2/0 | 2026-08-18~2026-11-06
上半部 | L3 | 2.1-T | POD2.1-T | L3 整段(含L5归还板) | 2026-09-17 | 2027-04-15 | 210 天 | 854m²+14nos | 0/2/2/2 | 2026-09-17~2027-04-15
上半部 | L3 | 2.1CIS | POD2.1CIS | L3 整段 | 2026-10-07 | 2027-01-19 | 104 天 | 560m²+67nos | 0/2/2/1 | 2026-10-07~2027-01-19
上半部 | L3 | 2.1CIS-T | POD2.1CIST | L3 整段 | 2026-10-15 | 2026-12-09 | 55 天 | 159m²+8nos | 0/2/2/1 | 2026-10-15~2026-12-09
上半部 | L3 | 2.2 | POD2.2 | L3 整段 | 2027-01-05 | 2027-02-01 | 27 天 | 46nos | 0/2/2/0 | 2027-01-05~2027-02-01
上半部 | L3 | 2.2-T | POD2.2-T | L3 整段(含L5归还板) | 2026-11-27 | 2027-04-20 | 144 天 | 1413m²+95nos | 0/2/2/1 | 2026-11-27~2027-04-20
上半部 | L3 | 2.3-T | POD2.3-T | L3 整段(含L5归还板) | 2026-09-04 | 2027-02-18 | 167 天 | 1173m²+68nos | 0/2/2/1 | 2026-09-04~2027-02-18
上半部 | L3 | 2.3CIS-T | POD2.3CIST | L3 整段 | 2026-10-02 | 2026-12-23 | 82 天 | 501m²+45nos | 0/2/2/1 | 2026-10-02~2026-12-23
上半部 | L3 | 2.4 | POD2.4 | L3 整段 | 2027-02-26 | 2027-04-06 | 39 天 | 521m²+6nos | 0/0/1/1 | 2027-02-26~2027-04-06
上半部 | L3 | 2.4-T | POD2.4-T | L3 整段(含L5归还板) | 2026-11-06 | 2027-04-09 | 154 天 | 700m²+54nos | 0/2/2/1 | 2026-11-06~2027-04-09
上半部 | L3 | 2.6CIS | POD2.6CIS | L3 整段 | 2026-12-14 | 2027-02-11 | 59 天 | 476m²+18nos | 0/2/2/1 | 2026-12-14~2027-02-11
上半部 | L3 | 2.6CIS-T | POD2.6CIST | L3 整段 | 2026-10-19 | 2026-12-18 | 60 天 | 794m²+35nos | 0/2/2/1 | 2026-10-19~2026-12-18
上半部 | L4 | 2.1 | POD2.1 | L4 整段 | 2026-09-29 | 2027-01-22 | 115 天 | 666m²+5nos | 0/2/2/1 | 2026-09-29~2027-01-22
上半部 | L4 | 2.1-T | POD2.1T | L4 整段 | 2026-10-29 | 2027-01-11 | 74 天 | 503m²+14nos | 0/2/2/1 | 2026-10-29~2027-01-11
上半部 | L4 | 2.1CIS | POD2.1CIS | L4 整段 | 2027-01-20 | 2027-04-09 | 79 天 | 560m²+67nos | 0/2/2/1 | 2027-01-20~2027-04-09
上半部 | L4 | 2.1CIS-T | POD2.1CIST | L4 整段 | 2026-12-10 | 2027-02-16 | 68 天 | 159m²+8nos | 0/2/2/1 | 2026-12-10~2027-02-16
上半部 | L4 | 2.2 | POD2.2 | L4 整段 | 2027-02-16 | 2027-03-15 | 27 天 | 46nos | 0/2/2/0 | 2027-02-16~2027-03-15
上半部 | L4 | 2.2-T | POD2.2T | L4 整段 | 2027-01-22 | 2027-03-15 | 52 天 | 1412m²+95nos | 0/2/2/1 | 2027-01-22~2027-03-15
上半部 | L4 | 2.3-T | POD2.3T | L4 整段 | 2026-10-08 | 2026-12-18 | 71 天 | 1173m²+68nos | 0/2/2/1 | 2026-10-08~2026-12-18
上半部 | L4 | 2.3CIS-T | POD2.3CIST | L4 整段 | 2026-12-24 | 2027-03-19 | 85 天 | 501m²+45nos | 0/2/2/1 | 2026-12-24~2027-03-19
上半部 | L4 | 2.4-T | POD2.4T | L4 整段 | 2026-12-10 | 2027-03-10 | 90 天 | 1221m²+54nos | 0/2/2/1 | 2026-12-10~2027-03-10
上半部 | L4 | 2.6CIS | POD2.6CIS | L4 整段 | 2027-02-12 | 2027-04-14 | 61 天 | 476m²+18nos | 0/2/2/1 | 2027-02-12~2027-04-14
上半部 | L4 | 2.6CIS-T | POD2.6CIST | L4 整段 | 2026-12-21 | 2027-02-19 | 60 天 | 794m²+35nos | 0/2/2/1 | 2026-12-21~2027-02-19
上半部 | L5 | 2.1 | POD2.1 | L5 整段 | 2027-04-16 | 2027-05-27 | 41 天 | 910m² | 0/0/0/1 | 2027-04-16~2027-05-27
上半部 | L5 | 2.1-T | POD2.1T | L5 整段 | 2027-04-02 | 2027-05-21 | 49 天 | 662m² | 0/0/0/1 | 2027-04-02~2027-05-21
上半部 | L5 | 2.2 | POD2.2 | L5 整段 | 2027-03-16 | 2027-04-26 | 41 天 | 587m² | 0/0/0/1 | 2027-03-16~2027-04-26
上半部 | L5 | 2.2-T | POD2.2T | L5 整段 | 2027-03-16 | 2027-05-24 | 69 天 | 826m² | 0/0/0/1 | 2027-03-16~2027-05-24
上半部 | L5 | 2.3-T | POD2.3T | L5 整段 | 2027-03-22 | 2027-05-28 | 67 天 | 1671m² | 0/0/0/1 | 2027-03-22~2027-05-28
上半部 | L5 | 2.4-T | POD2.4T | L5 整段 | 2027-04-10 | 2027-05-29 | 49 天 | 1221m² | 0/0/0/1 | 2027-04-10~2027-05-29
上半部 | L5 | 2.6CIS | POD2.6CIS | L5 整段 | 2027-04-15 | 2027-05-13 | 28 天 | 476m² | 0/0/0/1 | 2027-04-15~2027-05-13
上半部 | L5 | 2.6CIS-T | POD2.6CIST | L5 整段 | 2027-02-22 | 2027-04-30 | 67 天 | 794m² | 0/0/0/1 | 2027-02-22~2027-04-30

## 3_EB_逐条
EB — 逐条活动（楼层/小区/工作量）
楼层 | 小区 | 专业 Trade | 活动编号 | 活动名称 Task Name | 工作量 Qty | 开始 | 完成 | 时长 (天) | 状态
B2 | 3.3 | COL | P1_CN_10280 | CON¦EB¦COL¦NT¦ Columns Work [7nos-CX15-CY39, CX15-CY40, CX15-CY40-1, CX16-CY39, CX17-CY41, CX18-CY38, CX18-CY39] | 7nos | 2026-09-18 | 2026-09-28 | 10 | NotStart
B2 | EB2-2.1 | PIL | P1_CN_10070 | CON¦EB¦PIL¦CJ1-2¦Pilecap [1nos P65-85] Core wall pilecap [CW3B] | 1nos | 2026-04-01 | 2026-06-16 | 76 | NotStart
B2 | EB2-2.1 | PIL | P1_CN_10090 | CON¦EB¦PIL¦CJ1-2¦Pilecap [8 nos P86-88, P97-98, P96, P94-95, P89-91, P65-85, P92, P93] | 8nos | 2026-06-17 | 2026-07-10 | 23 | NotStart
B2 | EB2-2.1 | CRW | P1_CN_10080 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW3B/P1-ST-01B] at B2 | 1nos | 2026-06-17 | 2026-07-28 | 41 | NotStart
B2 | EB2-2.1 | COL | P1_CN_10110 | CON¦EB¦COL¦T¦ Columns Work [4nos-CX22-CY43-2, CX24-CY44-1, CX25-CY42-1, CX25-CY42+1nos-CX25-CY44] at B2 | 5nos | 2026-06-17 | 2026-07-15 | 28 | NotStart
B2 | EB2-2.1 | CRW | P1_CN_10100 | CON¦EB¦CRW¦T¦ Temp Staircase at B2 Zone 4.1[1 nos] | 1nos | 2026-08-03 | 2026-10-23 | 81 | NotStart
B2 | EB2-2.2 | PIL | P1_CN_10130 | CON¦EB¦PIL¦CJ2¦Pilecap [4nos-P38-40, P120-121, P52-54, P55-57] | 4nos | 2026-04-09 | 2026-06-19 | 71 | NotStart
B2 | EB2-2.2 | COL | P1_CN_10140 | CON¦EB¦COL¦T¦ Columns Work [3nos-CX18-CY43-1, CX20-CY43-1, CX20-CY42-1+1nos-CX19-CY43-1] | 4nos | 2026-06-22 | 2026-06-30 | 8 | NotStart
B2 | EB2-2.3 | PIL | P1_CN_10160 | CON¦EB¦PIL¦CJ3¦Pilecap [6nos-P20, P21, P24-25, P22-23, P34-35, P36-37] | 6nos | 2026-06-22 | 2026-06-30 | 8 | NotStart
B2 | EB2-2.3 | COL | P1_CN_10170 | CON¦EB¦COL¦T¦ Columns Work [2nos-CX15-CY43-1,CX17-CY42-1+4 nos-CX14-CY42,CX14-CY43-1,CX15-CY41,CX17-CY42] | 6nos | 2026-07-01 | 2026-07-09 | 8 | NotStart
B2 | EB2-2.4 | PIL | P1_CN_10190 | CON¦EB¦PIL¦CJ4¦Pilecap [4nos-P1,P3,P4,P5] | 4nos | 2026-07-13 | 2026-07-21 | 8 | NotStart
B2 | EB2-2.4 | COL | P1_CN_10200 | CON¦EB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX12-CY42, CX13-CY41-1, CX13-CY43-1] | 3nos | 2026-07-22 | 2026-07-30 | 8 | NotStart
B2 | EB2-3.1A-1 | PIL | P1_CN_10220 | CON¦EB¦PIL¦Pilecap Work [4nos–P58-60, P61-63, P125-127, P128-130] | 4nos | 2026-07-23 | 2026-07-31 | 8 | NotStart
B2 | EB2-3.1A-1 | COL | P1_CN_10230 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [4nos-CX22-CY40, CX24-CY39, CX24-CY40, CX22-CY38] | 4nos | 2026-08-03 | 2026-08-11 | 8 | NotStart
B2 | EB2-3.1A-2+3.2-2 | COL | P1_CN_10340 | CON¦EB¦COL¦NT¦ Columns[8nos-CX22-CY37,CX23-CY37,CX19-CY39-1,CX19-CY39-2,CX19-CY41,CX20-CY37,CX20-CY38-1,CX20-CY38-2] | 8nos | 2026-09-18 | 2026-09-28 | 10 | NotStart
B2 | EB2-3.1A-2+3.2-2 | PIL | P1_CN_10310 | CON¦EB¦PIL¦Pilecap Work [2 nos-P64, P131] | 2nos | 2027-04-21 | 2027-05-10 | 19 | NotStart
B2 | EB2-3.2-1 | COL | P1_CN_10250 | CON¦EB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX21-CY38, CX21-CY40, CX21-CY41] | 3nos | 2026-08-12 | 2026-08-20 | 8 | NotStart
B2 | EB2-3.4+3.5 | COL | P1_CN_10320 | CON¦EB¦COL¦NT¦Columns Work [1nos-CX14-CY41] | 1nos | 2026-09-18 | 2026-09-28 | 10 | NotStart
B2 | EB2-3.4+3.5 | CRW | P1_CN_10330 | CON¦EB¦CRW¦Staircase / Lift Wall [Rebar + Formwork + Casting] [1nos-ST06] | 1nos | 2026-09-18 | 2026-11-19 | 62 | NotStart
B1 | S2.1 | DEM | P1_CN_10060 | CON¦EB¦DEM¦CJ1-1¦Demolition [284.62 m²] at B1 Zone 2.1 | 285m² | 2026-05-21 | 2026-06-03 | 13 | NotStart
B1 | S2.1 | DEM | P1_CN_10300 | CON¦EB¦DEM¦CJ1-2¦Demolition [1470.79 m²] at B1 Zone 2.1 | 1471m² | 2026-06-04 | 2026-09-09 | 97 | NotStart
B1 | S2.1 | SLB | P1_CN_10370 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [1061 m²] + Beam Casting [12 nos] at B1 Zone 2.1 | 1061m²+12nos | 2026-07-01 | 2026-07-20 | 19 | NotStart
B1 | S2.1 | COL | P1_CN_10400 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-CX22-CY43-2, CX24-CY44-1] at B1 Zone 2.1 | 2nos | 2026-07-21 | 2026-07-29 | 8 | NotStart
B1 | S2.1 | CRW | P1_CN_10380 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos CW3B/P1-ST-01B] at B1 Zone 2.1 | 1nos | 2026-07-29 | 2026-09-08 | 41 | NotStart
B1 | S2.1 | CRW | P1_CN_10360 | CON¦EB¦CRW¦T¦Temp Staircase at B1 Zone 2.1 [1nos] | 1nos | 2026-08-03 | 2026-10-23 | 81 | NotStart
B1 | S2.1 | CRW | P1_CN_10390 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at B1 Zone 2.1 | — | 2026-09-09 | 2026-09-17 | 8 | NotStart
B1 | S2.2 | DEM | P1_CN_10120 | CON¦EB¦DEM¦CJ2¦Demolition [629.95 m²] at B1 Zone 2.2 | 630m² | 2026-06-04 | 2026-06-12 | 8 | NotStart
B1 | S2.2 | SLB | P1_CN_10420 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [614 m²] at B1 Zone 4.1 | 614m² | 2026-07-01 | 2026-07-20 | 19 | NotStart
B1 | S2.2 | COL | P1_CN_10430 | CON¦EB¦COL¦T¦ Columns Work [3nos-CX18-CY43-1, CX20-CY43-1, CX20-CY42-1 + 1nos-CX19-CY43-1] | 4nos | 2026-07-21 | 2026-07-29 | 8 | NotStart
B1 | S2.3 | DEM | P1_CN_10150 | CON¦EB¦DEM¦CJ3¦Demolition [789.4 m²] at B1 Zone 2.3 | 789m² | 2026-06-15 | 2026-06-23 | 8 | NotStart
B1 | S2.3 | SLB | P1_CN_10450 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [780 m²] at B1 Zone 2.3 | 780m² | 2026-07-10 | 2026-07-23 | 13 | NotStart
B1 | S2.3 | COL | P1_CN_10460 | CON¦EB¦COL¦T¦ Columns Work [2nos-CX15-CY43-1, CX17-CY42-1 + 2nos-CX15-CY41, CX17-CY42] | 4nos | 2026-07-22 | 2026-07-30 | 8 | NotStart
B1 | S2.4 | DEM | P1_CN_10180 | CON¦EB¦DEM¦CJ4¦Demolition [509.55 m²] at B1 Zone 2.4 | 510m² | 2026-06-24 | 2026-07-02 | 8 | NotStart
B1 | S2.4 | SLB | P1_CN_10480 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [599 m²] + Beam Casting [4 nos] at B1 Zone 2.4 | 599m²+4nos | 2026-07-31 | 2026-08-10 | 10 | NotStart
B1 | S2.4 | COL | P1_CN_10490 | CON¦EB¦COL¦NT¦ Columns Work [5nos-CX12-CY42, CX13-CY41-1, CX13-CY43-1, CX14-CY43-1, CX14-CY42] | 5nos | 2026-08-11 | 2026-08-19 | 8 | NotStart
B1 | S5 | DEM | P1_CN_10210 | CON¦EB¦DEM¦ZB-3.1-3¦Demolition [756.66 m²] at B1 Zone 3.1 | 757m² | 2026-07-03 | 2026-07-22 | 19 | NotStart
B1 | S5 | SLB | P1_CN_10510 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [380 m²] at B1 Zone 3.1 | 380m² | 2026-08-12 | 2026-08-31 | 19 | NotStart
B1 | S5 | COL | P1_CN_10520 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-CX22-CY40, CX24-CY40] | 2nos | 2026-09-01 | 2026-09-09 | 8 | NotStart
B1 | S6 | SLB | P1_CN_10540 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [1051 m²] + Beam Casting [3 nos] at L1 Zone 4.3 | 1051m²+3nos | 2026-08-21 | 2026-09-09 | 19 | NotStart
B1 | S6 | COL | P1_CN_10550 | CON¦EB¦COL¦T¦ Columns Work [2nos-CX21-CY40, CX21-CY41 + 5nos-CX17-CY41, CX18-CY39, CX19-CY39-1, CX19-CY39-2, CX19-CY41] | 7nos | 2026-09-10 | 2026-09-18 | 8 | NotStart
B1 | S6 | DEM | P1_CN_10240 | CON¦EB¦DEM¦ZB-3.1-2¦Demolition [1037.88 m²] at B1 Zone 3.2 | 1038m² | 2027-02-01 | 2027-02-21 | 20 | NotStart
B1 | S7 | SLB | P1_CN_10580 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [763 m²] + Beam Casting [13 nos] at B1 Zone 3.3+3.5 | 763m²+13nos | 2026-09-29 | 2026-10-16 | 17 | NotStart
B1 | S7 | COL | P1_CN_10590 | CON¦EB¦COL¦NT¦ Columns Work [5 nos-CX14-CY41, CX15-CY39, CX15-CY40, CX15-CY40-1, CX16-CY39] | 5nos | 2026-10-19 | 2026-10-27 | 8 | NotStart
B1 | S7 | DEM | P1_CN_10260 | CON¦EB¦DEM¦ZB-3.1-1¦Demolition [339.70 m²] at B1 Zone 3.3+3.5 | 340m² | 2027-02-22 | 2027-03-11 | 17 | NotStart
B1 | S7 | DEM | P1_CN_10270 | CON¦EB¦DEM¦ZB-3.5¦Demolition [263.88 m²] at B1 Zone 3.3+3.5 | 264m² | 2027-04-01 | 2027-04-20 | 19 | NotStart
B1 | S8 | CRW | P1_CN_10630 | CON¦EB¦CRW¦T¦ Temp Staircase at B1 Zone 4.4 [1 nos] | 1nos | 2026-09-18 | 2026-11-19 | 62 | NotStart
B1 | S8 | SLB | P1_CN_10610 | CON¦EB¦SLB¦T¦ Slab [Drop Panel] [1181 m²] + Beam Casting [10 nos] at L1 Zone OT | 1181m²+10nos | 2026-09-29 | 2026-10-16 | 17 | NotStart
B1 | S8 | CRW | P1_CN_10640 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1nos-ST06B] at B1 Zone 4.4 CIS | 1nos | 2026-09-29 | 2026-11-09 | 41 | NotStart
B1 | S8 | COL | P1_CN_10620 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-CX21-CY38, CX22-CY38, CX24-CY39] | 3nos | 2026-10-19 | 2026-10-27 | 8 | NotStart
B1 | S8 | COL | P1_CN_10621 | CON¦EB¦COL¦NT¦ Columns Work [6 nos-CX18-CY38, CX20-CY37, CX22-CY37-1, CX23-CY37, CX20-CY38-1, CX20-CY38-2] | 6nos | 2026-10-28 | 2026-11-16 | 19 | NotStart
B1 | S8 | CRW | P1_CN_10650 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at B1 Zone 4.4 | — | 2026-11-10 | 2026-11-18 | 8 | NotStart
B1 | S8 | DEM | P1_CN_10290 | CON¦EB¦DEM¦ZB-3.1-4¦Demolition [1027.83 m²] at B1 Zone 3.4 | 1028m² | 2027-03-12 | 2027-03-31 | 19 | NotStart
L1 | 4.1 | SLB | P1_CN_10760 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [770 m²] + Beam RC [8 nos] at L1 Zone 4.1 [NCIS] | 770m²+8nos | 2026-07-30 | 2026-08-18 | 19 | NotStart
L1 | 4.1 | COL | P1_CN_10770 | CON¦EB¦COL¦T¦ Columns Work [3nos-CX18-CY43-1, CX20-CY42-1, CX20-CY43-1 + 1nos-CX19-CY43-1] | 4nos | 2026-08-19 | 2026-08-27 | 8 | NotStart
L1 | 4.1 | COL | P1_CN_10780 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [4 nos] at L1 Zone 4.1 [NCIS] | 4nos | 2026-08-28 | 2026-09-01 | 4 | NotStart
L1 | 4.1 | STB | P1_CN_10790 | CON¦EB¦STB¦T¦ Steel Beam Installation [9 nos] at L1 Zone 4.1 [NCIS] | 9nos | 2026-09-02 | 2026-09-10 | 8 | NotStart
L1 | 4.1 | MBR | P1_CN_10800 | CON¦EB¦MBR¦T¦ Main Beam RC [2 nos] at L1 Zone 4.1 [NCIS] | 2nos | 2026-09-11 | 2026-09-21 | 10 | NotStart
L1 | 4.1CIS-T | SLB | P1_CN_10810 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1277 m²] + Beam RC [42 nos] at L1 Zone 4.1 CIS [CIS] | 1277m²+42nos | 2026-07-30 | 2026-08-19 | 20 | NotStart
L1 | 4.1CIS-T | COL | P1_CN_10840 | CON¦EB¦COL¦T¦ Columns Work [5nos-CX22-CY43-2, CX24-CY44-1, CX25-CY42, CX25-CY43-1, CX25-CY44] at L1 | 5nos | 2026-08-20 | 2026-09-08 | 19 | NotStart
L1 | 4.1CIS-T | WAL | P1_CN_10860 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [5nos-ST28/29,ST30/31,ST32/33,ST34/45,ST36/37] at L1 | 5nos | 2026-08-20 | 2026-09-30 | 41 | NotStart
L1 | 4.1CIS-T | COL | P1_CN_10850 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone 4.1 CIS [CIS] | 5nos | 2026-09-09 | 2026-09-11 | 2 | NotStart
L1 | 4.1CIS-T | STB | P1_CN_10870 | CON¦EB¦STB¦T¦ Steel Beam Installation [44 nos] at L1 Zone 4.1 [CIS] | 44nos | 2026-09-14 | 2026-09-18 | 4 | NotStart
L1 | 4.1CIS-T | CRW | P1_CN_10820 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1nos-CW3B/ST01-01B] at L1 Zone 4.1 CIS [CIS] | 1nos | 2026-09-18 | 2026-10-29 | 41 | NotStart
L1 | 4.1CIS-T | MBR | P1_CN_10880 | CON¦EB¦MBR¦T¦ Main Beam RC [24 nos] at L1 Zone 4.1 [CIS] | 24nos | 2026-09-21 | 2026-09-29 | 8 | NotStart
L1 | 4.1CIS-T | CRW | P1_CN_10890 | CON¦EB¦CRW¦T¦ Temp Staircase at B1 Zone 4.1 1 nos-ST-C1 | 1nos | 2026-10-28 | 2027-01-19 | 83 | NotStart
L1 | 4.1CIS-T | CRW | P1_CN_10830 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L1 Zone 4.1 [CIS] | — | 2026-10-30 | 2026-11-09 | 10 | NotStart
L1 | 4.2 | SLB | P1_CN_10710 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [718 m²] + Beam RC [17 nos] at L1 Zone 4.2 [NCIS] | 718m²+17nos | 2026-08-11 | 2026-09-08 | 28 | NotStart
L1 | 4.2 | COL | P1_CN_10720 | CON¦EB¦COL¦NT¦ Columns Work [5nos-CX12-CY42, CX13-CY41-1, CX13-CY43-1, CX14-CY42, CX14-CY43-1] | 5nos | 2026-09-07 | 2026-09-15 | 8 | NotStart
L1 | 4.2 | COL | P1_CN_10730 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone 4.2 [NCIS] | 5nos | 2026-09-16 | 2026-09-18 | 2 | NotStart
L1 | 4.2 | STB | P1_CN_10740 | CON¦EB¦STB¦NT¦ Steel Beam Installation [22 nos] at L1 Zone 4.2 [NCIS] | 22nos | 2026-09-21 | 2026-09-23 | 2 | NotStart
L1 | 4.2 | MBR | P1_CN_10750 | CON¦EB¦MBR¦NT¦ Main Beam RC [5 nos] at L1 Zone 4.2 [NCIS] | 5nos | 2026-09-23 | 2026-10-01 | 8 | NotStart
L1 | 4.2-T | SLB | P1_CN_10660 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [737 m²] + Beam RC [1 nos] at L1 Zone 4.2 [NCIS] | 737m²+1nos | 2026-07-31 | 2026-08-19 | 19 | NotStart
L1 | 4.2-T | COL | P1_CN_10670 | CON¦EB¦COL¦T¦ Columns Work [2nos-CX15-CY43-1, CX17-CY42-1 +2nos-CX15-CY41, CX17-CY42] at L1 Zone 4 | 4nos | 2026-08-18 | 2026-08-26 | 8 | NotStart
L1 | 4.2-T | COL | P1_CN_10680 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [4 nos] at L1 Zone 4.2 [NCIS] | 4nos | 2026-08-27 | 2026-08-31 | 4 | NotStart
L1 | 4.2-T | STB | P1_CN_10690 | CON¦EB¦STB¦T¦ Steel Beam Installation [21 nos] at L1 Zone 4.2 [NCIS] | 21nos | 2026-09-01 | 2026-09-03 | 2 | NotStart
L1 | 4.2-T | MBR | P1_CN_10700 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L1 Zone 4.2 [NCIS] | 3nos | 2026-09-04 | 2026-09-14 | 10 | NotStart
L1 | 4.3-T | SLB | P1_CN_10960 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [741 m²] + Beam RC [13 nos] at L1 Zone 4.3 [NCIS] | 741m²+13nos | 2026-09-21 | 2026-10-19 | 28 | NotStart
L1 | 4.3-T | COL | P1_CN_10970 | CON¦EB¦COL¦T¦ Columns Work [3nos-CX21-CY40, CX21-CY41, CX22-CY40 + 3nos-CX19-CY39, CX19-CY39-1, CX19-CY41] | 6nos | 2026-10-20 | 2026-10-28 | 8 | NotStart
L1 | 4.3-T | COL | P1_CN_10980 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L1 Zone 4.3 [NCIS] | 6nos | 2026-10-29 | 2026-11-02 | 4 | NotStart
L1 | 4.3-T | STB | P1_CN_10990 | CON¦EB¦STB¦T¦ Steel Beam Installation [23 nos] at L1 Zone 4.3 [NCIS] | 23nos | 2026-11-03 | 2026-11-09 | 6 | NotStart
L1 | 4.3-T | MBR | P1_CN_11000 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L1 Zone 4.3 [NCIS] | 3nos | 2026-11-10 | 2026-11-18 | 8 | NotStart
L1 | 4.3CIS-T | SLB | P1_CN_11010 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [493 m²] + Beam RC [17 nos] at L1 Zone 4.3 [CIS] | 493m²+17nos | 2026-09-10 | 2026-09-29 | 19 | NotStart
L1 | 4.3CIS-T | WAL | P1_CN_11040 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2nos-ST40/41,ST39/38] at L1 Zone 4.3 CIS [CIS] | 2nos | 2026-09-30 | 2026-11-10 | 41 | NotStart
L1 | 4.3CIS-T | COL | P1_CN_11020 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos-CX24-CY40] | 1nos | 2026-09-30 | 2026-10-08 | 8 | NotStart
L1 | 4.3CIS-T | COL | P1_CN_11030 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L1 Zone 4.3 [CIS] | 1nos | 2026-10-09 | 2026-10-13 | 4 | NotStart
L1 | 4.3CIS-T | STB | P1_CN_11060 | CON¦EB¦STB¦T¦ Steel Beam Installation [17 nos] at L1 Zone 4.3 [CIS] | 17nos | 2026-10-14 | 2026-10-20 | 6 | NotStart
L1 | 4.3CIS-T | MBR | P1_CN_11070 | CON¦EB¦MBR¦T¦ Main Beam RC [8 nos] at L1 Zone 4.3 [CIS] | 8nos | 2026-10-21 | 2026-10-29 | 8 | NotStart
L1 | 4.3CIS-T | CRW | P1_CN_11050 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L1 Zone 4.3 [CIS] | — | 2026-11-11 | 2026-11-19 | 8 | NotStart
L1 | 4.4 | SLB | P1_CN_10900 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1209 m²] + Beam RC [39 nos] at L1 Zone 4.4 [NCIS] | 1209m²+39nos | 2026-10-28 | 2026-11-16 | 19 | NotStart
L1 | 4.4 | COL | P1_CN_10920 | CON¦EB¦COL¦NT¦Columns Work [8nos-CX14-CY41,CX15-CY39,CX15-CY40,CX15-CY40-1,CX16-CY39,CX17-CY41,CX18-CY39,CX19-CY39-2] | 8nos | 2026-11-12 | 2026-12-01 | 19 | NotStart
L1 | 4.4 | CRW | P1_CN_10910 | CON¦EB¦CRW¦T¦ Temp Staircase at B1 Zone 4.4 [1 nos-ST-06B] | 1nos | 2026-11-20 | 2027-01-21 | 62 | NotStart
L1 | 4.4 | COL | P1_CN_10930 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [8 nos] at L1 Zone 4.4 [NCIS] | 8nos | 2026-12-02 | 2026-12-04 | 2 | NotStart
L1 | 4.4 | STB | P1_CN_10940 | CON¦EB¦STB¦NT¦ Steel Beam Installation [? nos] at L1 Zone 4.4 [NCIS] | — | 2026-12-07 | 2026-12-11 | 4 | NotStart
L1 | 4.4 | MBR | P1_CN_10950 | CON¦EB¦MBR¦NT¦ Main Beam RC [8 nos] at L1 Zone 4.4 [NCIS] | 8nos | 2026-12-14 | 2026-12-22 | 8 | NotStart
L1 | 4.4-OT | SLB | P1_CN_20330* | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1328 m²] + Beam RC [62 nos] at L1 Zone 4.4 [NCIS] | 1328m²+62nos | 2026-12-23 | 2027-01-11 | 19 | NotStart
L1 | 4.4-OT | COL | P1_CN_20340* | CON¦EB¦COL¦NT¦ Columns Work [3nos-CX21-CY38, CX22-CY38, CX24-CY39 + 7nos] at L1 Zone 4.4 [NCIS] | 10nos | 2027-01-07 | 2027-01-26 | 19 | NotStart
L1 | 4.4-OT | COL | P1_CN_20350* | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [10 nos] at L1 Zone 4.4 [NCIS] | 10nos | 2027-01-27 | 2027-01-29 | 2 | NotStart
L1 | 4.4-OT | STB | P1_CN_20360* | CON¦EB¦STB¦NT¦ Steel Beam Installation [40 nos] at L1 Zone 4.4 [NCIS] | 40nos | 2027-02-01 | 2027-02-05 | 4 | NotStart
L1 | 4.4-OT | MBR | P1_CN_20370* | CON¦EB¦MBR¦NT¦ Main Beam RC [8 nos] at L1 Zone 4.4 [NCIS] | 8nos | 2027-02-08 | 2027-02-16 | 8 | NotStart
L1 | B2.1 | DEM | P1_CN_10350 | CON¦EB¦DEM¦CJ1-2¦Demolition [288.06 m²] at L1 Zone 2.1 | 288m² | 2026-04-01 | 2026-04-10 | 9 | NotStart
L1 | B2.1 | DEM | P1_CN_20320 | CON¦EB¦DEM¦CJ1-1¦Demolition [859.69 m²] at L1 Zone 2.1 | 860m² | 2026-04-13 | 2026-04-22 | 9 | NotStart
L1 | B2.2 | DEM | P1_CN_10410 | CON¦EB¦DEM¦CJ2¦Demolition [645.2 m²] at L1 Zone 2.2 | 645m² | 2026-04-01 | 2026-04-10 | 9 | NotStart
L1 | B2.3 | DEM | P1_CN_10440 | CON¦EB¦DEM¦CJ3¦Demolition [910.67 m²] at L1 Zone 2.3 | 911m² | 2026-04-13 | 2026-05-20 | 37 | NotStart
L1 | B2.4 | DEM | P1_CN_10470 | CON¦EB¦DEM¦CJ4¦Demolition [490.75 m²] at L1 Zone 2.4 | 491m² | 2026-05-21 | 2026-06-12 | 22 | NotStart
L1 | B3.1 | DEM | P1_CN_10500 | CON¦EB¦DEM¦ZB-3.1-3¦Demolition [594.77 m²] at L1 Zone 3.1 | 595m² | 2026-06-15 | 2026-06-23 | 8 | NotStart
L1 | B3.1 | DEM | P1_CN_20310 | CON¦EB¦DEM¦MK¦Demolition [1280.65 m²] at L1 Zone 3.1 | 1281m² | 2026-06-24 | 2026-07-03 | 9 | NotStart
L1 | B3.2 | DEM | P1_CN_10530 | CON¦EB¦DEM¦ZB-3.1-2¦Demolition [729.94 m²] at L1 Zone 3.2 | 730m² | 2027-02-01 | 2027-02-18 | 17 | NotStart
L1 | B3.3+3.5 | DEM | P1_CN_10560 | CON¦EB¦DEM¦ZB-3.1-1¦Demolition [449.95 m²] at L1 Zone 3.3+3.5 | 450m² | 2027-02-19 | 2027-03-10 | 19 | NotStart
L1 | B3.3+3.5 | DEM | P1_CN_10570 | CON¦EB¦DEM¦ZB-3.1.6-8¦Demolition [2079.21 m²] at L1 Zone 3.3+3.5 | 2079m² | 2027-04-02 | 2027-04-21 | 19 | NotStart
L1 | B3.4 | DEM | P1_CN_10600 | CON¦EB¦DEM¦CJ4-M28¦Demolition [311.01 m²] at L1 Zone 3.4 | 311m² | 2027-03-11 | 2027-03-30 | 19 | NotStart
L2 | 4.1 | COL | P1_CN_11160 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX18-CY43-1,CX20-42-1,CX19-CY43-1] at L2 Zone 4.1 | 3nos | 2026-09-22 | 2026-09-30 | 8 | NotStart
L2 | 4.1 | COL | P1_CN_11170 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L2 Zone 4.1 [NCIS] | 3nos | 2026-10-01 | 2026-10-05 | 4 | NotStart
L2 | 4.1 | STB | P1_CN_11180 | CON¦EB¦STB¦T¦ Steel Beam Installation [9 nos] at L2 Zone 4.1 [NCIS] | 9nos | 2026-10-06 | 2026-10-14 | 8 | NotStart
L2 | 4.1 | MBR | P1_CN_11190 | CON¦EB¦MBR¦T¦ Main Beam RC [2 nos] at L2 Zone 4.1 [NCIS] | 2nos | 2026-10-15 | 2026-10-23 | 8 | NotStart
L2 | 4.1CIS-T | SLB | P1_CN_11200 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1272 m²] at L2 Zone 4.1 CIS [CIS] | 1272m² | 2026-09-30 | 2026-10-20 | 20 | NotStart
L2 | 4.1CIS-T | COL | P1_CN_11230 | CON¦EB¦COL¦T¦ Columns Work [7nos-CX25-CY42, CX25-CY43-1, CX25-CY44, CX24-CY44-1, CX22-CY43-2, CX20-CY43-1, WF-B2C64] | 7nos | 2026-10-21 | 2026-11-09 | 19 | NotStart
L2 | 4.1CIS-T | COL | P1_CN_11240 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L2 Zone 4.1 CIS [CIS] | 7nos | 2026-11-10 | 2026-11-12 | 2 | NotStart
L2 | 4.1CIS-T | CRW | P1_CN_11210 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1nos-CW3B/P1-ST-01B] at L2 Zone 4.1 CIS [CIS] | 1nos | 2026-11-10 | 2026-12-21 | 41 | NotStart
L2 | 4.1CIS-T | WAL | P1_CN_11250 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [5nos-ST28/29,ST30/31,ST32/33,ST34/45,ST36/37] at L2 | 5nos | 2026-11-10 | 2026-12-21 | 41 | NotStart
L2 | 4.1CIS-T | STB | P1_CN_11260 | CON¦EB¦STB¦T¦ Steel Beam Installation [44 nos] at L2 Zone 4.1 CIS [CIS] | 44nos | 2026-11-13 | 2026-11-19 | 6 | NotStart
L2 | 4.1CIS-T | MBR | P1_CN_11270 | CON¦EB¦MBR¦T¦ Main Beam RC [24 nos] at L2 Zone 4.1 CIS [CIS] | 24nos | 2026-11-20 | 2026-11-30 | 10 | NotStart
L2 | 4.1CIS-T | CRW | P1_CN_11220 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone 4.1 [CIS] | — | 2026-12-22 | 2026-12-30 | 8 | NotStart
L2 | 4.2 | COL | P1_CN_11120 | CON¦EB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX14-CY42,CX15-CY41,CX17-CY42] at L2 Zone 4.2 | 3nos | 2026-09-30 | 2026-10-08 | 8 | NotStart
L2 | 4.2 | COL | P1_CN_11130 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L2 Zone 4.2 [NCIS] | 3nos | 2026-10-09 | 2026-10-13 | 4 | NotStart
L2 | 4.2 | STB | P1_CN_11140 | CON¦EB¦STB¦NT¦ Steel Beam Installation [22 nos] at L2 Zone 4.2 [NCIS] | 22nos | 2026-10-14 | 2026-10-16 | 2 | NotStart
L2 | 4.2 | MBR | P1_CN_11150 | CON¦EB¦MBR¦NT¦ Main Beam RC [5 nos] at L2 Zone 4.2 [NCIS] | 5nos | 2026-10-16 | 2026-10-26 | 10 | NotStart
L2 | 4.2-T | COL | P1_CN_11080 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX15-CY43-1,CX17-CY42-1,CX14-CY43-1] at L2 Zone 4 | 3nos | 2026-09-15 | 2026-09-23 | 8 | NotStart
L2 | 4.2-T | COL | P1_CN_11090 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L2 Zone 4.2 [NCIS] | 3nos | 2026-09-24 | 2026-09-28 | 4 | NotStart
L2 | 4.2-T | STB | P1_CN_11100 | CON¦EB¦STB¦T¦ Steel Beam Installation [21 nos] at L2 Zone 4.2 [NCIS] | 21nos | 2026-09-29 | 2026-10-01 | 2 | NotStart
L2 | 4.2-T | MBR | P1_CN_11110 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L2 Zone 4.2 [NCIS] | 3nos | 2026-10-01 | 2026-10-09 | 8 | NotStart
L2 | 4.3-T | COL | P1_CN_11320 | CON¦EB¦COL¦T¦ Columns Work [7nos-CX20-CY38, CX21-CY38, CX22-CY38, CX19-CY39, CX21-CY40, CX19-CY41, CX21-CY41] | 7nos | 2026-11-19 | 2026-12-08 | 19 | NotStart
L2 | 4.3-T | COL | P1_CN_11330 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L2 Zone 4.3 [NCIS] | 7nos | 2026-12-09 | 2026-12-11 | 2 | NotStart
L2 | 4.3-T | STB | P1_CN_11340 | CON¦EB¦STB¦T¦ Steel Beam Installation [23 nos] at L2 Zone 4.3 [NCIS] | 23nos | 2026-12-14 | 2026-12-18 | 4 | NotStart
L2 | 4.3-T | MBR | P1_CN_11350 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L2 Zone 4.3 [NCIS] | 3nos | 2026-12-21 | 2026-12-29 | 8 | NotStart
L2 | 4.3CIS-T | SLB | P1_CN_11360 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [374 m²] at L2 Zone 4.3 CIS [CIS] | 374m² | 2026-10-30 | 2026-11-18 | 19 | NotStart
L2 | 4.3CIS-T | COL | P1_CN_11370 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX22-CY40, CX24-CY40, CX24-CY39] at L2 | 3nos | 2026-11-19 | 2026-11-27 | 8 | NotStart
L2 | 4.3CIS-T | WAL | P1_CN_11390 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [3nos-ST42/43,ST40/41,ST39/38] at L2 Zone 4.3 CIS [CIS] | 3nos | 2026-11-20 | 2026-12-31 | 41 | NotStart
L2 | 4.3CIS-T | COL | P1_CN_11380 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L2 Zone 4.3 CIS [CIS] | 3nos | 2026-11-30 | 2026-12-02 | 2 | NotStart
L2 | 4.3CIS-T | STB | P1_CN_11410 | CON¦EB¦STB¦T¦ Steel Beam Installation [17 nos] at L2 Zone 4.3 CIS [CIS] | 17nos | 2026-12-03 | 2026-12-09 | 6 | NotStart
L2 | 4.3CIS-T | MBR | P1_CN_11420 | CON¦EB¦MBR¦T¦ Main Beam RC [8 nos] at L2 Zone 4.3 CIS [CIS] | 8nos | 2026-12-10 | 2026-12-18 | 8 | NotStart
L2 | 4.3CIS-T | CRW | P1_CN_11400 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone 4.3 [CIS] | — | 2027-01-01 | 2027-01-11 | 10 | NotStart
L2 | 4.4 | COL | P1_CN_11280 | CON¦EB¦COL¦NT¦ Columns Work [5nos-CX15-CY40, CX15-CY40-1, CX17-CY41, CX15-CY39, CX18-CY39] at L2 Zone 4.4 [NCIS] | 5nos | 2026-12-18 | 2027-01-06 | 19 | NotStart
L2 | 4.4 | COL | P1_CN_11290 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L2 Zone 4.4 [NCIS] | 5nos | 2027-01-07 | 2027-01-11 | 4 | NotStart
L2 | 4.4 | STB | P1_CN_11300 | CON¦EB¦STB¦NT¦ Steel Beam Installation [40 nos] at L2 Zone 4.4 [NCIS] | 40nos | 2027-01-12 | 2027-01-18 | 6 | NotStart
L2 | 4.4 | MBR | P1_CN_11310 | CON¦EB¦MBR¦NT¦ Main Beam RC [8 nos] at L2 Zone 4.4 [NCIS] | 8nos | 2027-01-19 | 2027-01-27 | 8 | NotStart
L3 | 4.1 | COL | P1_CN_11510 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX18-CY43-1,CX20-42-1,CX19-CY43-1] at L3 Zone 4.1 | 3nos | 2026-10-26 | 2026-11-03 | 8 | NotStart
L3 | 4.1 | COL | P1_CN_11520 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L3 Zone 4.1 [NCIS] | 3nos | 2026-11-04 | 2026-11-06 | 2 | NotStart
L3 | 4.1 | STB | P1_CN_11530 | CON¦EB¦STB¦T¦ Steel Beam Installation [9 nos] at L3 Zone 4.1 [NCIS] | 9nos | 2026-11-09 | 2026-11-11 | 2 | NotStart
L3 | 4.1 | MBR | P1_CN_11540 | CON¦EB¦MBR¦T¦ Main Beam RC [2 nos] at L3 Zone 4.1 [NCIS] | 2nos | 2026-11-12 | 2026-11-20 | 8 | NotStart
L3 | 4.1CIS-T | SLB | P1_CN_11550 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1272 m²] at L3 Zone 4.1 CIS [CIS] | 1272m² | 2026-12-01 | 2026-12-14 | 13 | NotStart
L3 | 4.1CIS-T | COL | P1_CN_11580 | CON¦EB¦COL¦T¦ Columns Work [7nos-CX25-CY42, CX25-CY43-1, CX25-CY44, CX24-CY44-1, CX22-CY43-2, CX20-CY43-1, WF-B2C64] | 7nos | 2026-12-15 | 2027-01-01 | 17 | NotStart
L3 | 4.1CIS-T | CRW | P1_CN_11560 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1nos-CW3B/P1-ST-01B] at L3 Zone 4.1 CIS [CIS] | 1nos | 2026-12-31 | 2027-02-10 | 41 | NotStart
L3 | 4.1CIS-T | WAL | P1_CN_11600 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [5nos-ST28/29,ST30/31,ST32/33,ST34/45,ST36/37] at L3 | 5nos | 2026-12-31 | 2027-02-10 | 41 | NotStart
L3 | 4.1CIS-T | COL | P1_CN_11590 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L3 Zone 4.1 CIS [CIS] | 7nos | 2027-01-04 | 2027-01-06 | 2 | NotStart
L3 | 4.1CIS-T | STB | P1_CN_11610 | CON¦EB¦STB¦T¦ Steel Beam Installation [44 nos] at L3 Zone 4.1 CIS [CIS] | 44nos | 2027-01-07 | 2027-01-13 | 6 | NotStart
L3 | 4.1CIS-T | MBR | P1_CN_11620 | CON¦EB¦MBR¦T¦ Main Beam RC [24 nos] at L3 Zone 4.1 CIS [CIS] | 24nos | 2027-01-14 | 2027-01-22 | 8 | NotStart
L3 | 4.1CIS-T | CRW | P1_CN_11570 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone 4.1 [CIS] | — | 2027-02-11 | 2027-02-19 | 8 | NotStart
L3 | 4.2 | COL | P1_CN_11470 | CON¦EB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX14-CY42,CX15-CY41,CX17-CY42] at L3 Zone 4.2 | 3nos | 2026-10-27 | 2026-11-04 | 8 | NotStart
L3 | 4.2 | COL | P1_CN_11480 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L3 Zone 4.2 [NCIS] | 3nos | 2026-11-05 | 2026-11-09 | 4 | NotStart
L3 | 4.2 | STB | P1_CN_11490 | CON¦EB¦STB¦NT¦ Steel Beam Installation [22 nos] at L3 Zone 4.2 [NCIS] | 22nos | 2026-11-10 | 2026-11-12 | 2 | NotStart
L3 | 4.2 | MBR | P1_CN_11500 | CON¦EB¦MBR¦NT¦ Main Beam RC [5 nos] at L3 Zone 4.2 [NCIS] | 5nos | 2026-11-12 | 2026-11-20 | 8 | NotStart
L3 | 4.2-T | COL | P1_CN_11430 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX15-CY43-1,CX17-CY42-1,CX14-CY43-1] at L3 Zone 4 | 3nos | 2026-10-12 | 2026-10-20 | 8 | NotStart
L3 | 4.2-T | COL | P1_CN_11440 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L3 Zone 4.2 [NCIS] | 3nos | 2026-10-21 | 2026-10-23 | 2 | NotStart
L3 | 4.2-T | STB | P1_CN_11450 | CON¦EB¦STB¦T¦ Steel Beam Installation [21 nos] at L3 Zone 4.2 [NCIS] | 21nos | 2026-10-26 | 2026-10-28 | 2 | NotStart
L3 | 4.2-T | MBR | P1_CN_11460 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L3 Zone 4.2 [NCIS] | 3nos | 2026-10-29 | 2026-11-06 | 8 | NotStart
L3 | 4.3-T | COL | P1_CN_11670 | CON¦EB¦COL¦T¦ Columns Work [7nos-CX20-CY38, CX21-CY38, CX22-CY38, CX19-CY39, CX21-CY40, CX19-CY41, CX21-CY41] | 7nos | 2026-12-30 | 2027-01-18 | 19 | NotStart
L3 | 4.3-T | COL | P1_CN_11680 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L3 Zone 4.3 [NCIS] | 7nos | 2027-01-19 | 2027-01-21 | 2 | NotStart
L3 | 4.3-T | STB | P1_CN_11690 | CON¦EB¦STB¦T¦ Steel Beam Installation [23 nos] at L3 Zone 4.3 [NCIS] | 23nos | 2027-01-22 | 2027-01-28 | 6 | NotStart
L3 | 4.3-T | MBR | P1_CN_11700 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L3 Zone 4.3 [NCIS] | 3nos | 2027-01-29 | 2027-02-08 | 10 | NotStart
L3 | 4.3CIS-T | SLB | P1_CN_11710 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [374 m²] at L3 Zone 4.3 CIS [CIS] | 374m² | 2026-12-10 | 2026-12-29 | 19 | NotStart
L3 | 4.3CIS-T | COL | P1_CN_11720 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX22-CY40, CX24-CY40, CX24-CY39] at L3 | 3nos | 2026-12-30 | 2027-01-07 | 8 | NotStart
L3 | 4.3CIS-T | COL | P1_CN_11730 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L3 Zone 4.3 CIS [CIS] | 3nos | 2027-01-08 | 2027-01-12 | 4 | NotStart
L3 | 4.3CIS-T | WAL | P1_CN_11740 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [3nos-ST42/43,ST40/41,ST39/38] at L3 Zone 4.3 CIS [CIS] | 3nos | 2027-01-12 | 2027-02-22 | 41 | NotStart
L3 | 4.3CIS-T | STB | P1_CN_11760 | CON¦EB¦STB¦T¦ Steel Beam Installation [17 nos] at L3 Zone 4.3 CIS [CIS] | 17nos | 2027-01-13 | 2027-01-19 | 6 | NotStart
L3 | 4.3CIS-T | MBR | P1_CN_11770 | CON¦EB¦MBR¦T¦ Main Beam RC [8 nos] at L3 Zone 4.3 CIS [CIS] | 8nos | 2027-01-20 | 2027-01-28 | 8 | NotStart
L3 | 4.3CIS-T | CRW | P1_CN_11750 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone 4.3 [CIS] | — | 2027-02-23 | 2027-03-03 | 8 | NotStart
L3 | 4.4 | COL | P1_CN_11630 | CON¦EB¦COL¦NT¦ Columns Work [5nos-CX15-CY40, CX15-CY40-1, CX17-CY41, CX15-CY39, CX18-CY39] at L3 Zone 4.4 [NCIS] | 5nos | 2027-01-25 | 2027-02-11 | 17 | NotStart
L3 | 4.4 | COL | P1_CN_11640 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L3 Zone 4.4 [NCIS] | 5nos | 2027-02-12 | 2027-02-16 | 4 | NotStart
L3 | 4.4 | STB | P1_CN_11650 | CON¦EB¦STB¦NT¦ Steel Beam Installation [40 nos] at L3 Zone 4.4 [NCIS] | 40nos | 2027-02-17 | 2027-02-23 | 6 | NotStart
L3 | 4.4 | MBR | P1_CN_11660 | CON¦EB¦MBR¦NT¦ Main Beam RC [8 nos] at L3 Zone 4.4 [NCIS] | 8nos | 2027-02-24 | 2027-03-04 | 8 | NotStart
L4 | 4.1 | SLB | P1_CN_11870 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [589 m²] at L4 Zone 4.1 [NCIS] | 589m² | 2026-11-23 | 2026-12-21 | 28 | NotStart
L4 | 4.1 | COL | P1_CN_11880 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX18-CY43-1,CX20-42-1,CX19-CY43-1] at L4 Zone 4.1 | 3nos | 2026-12-22 | 2026-12-30 | 8 | NotStart
L4 | 4.1 | COL | P1_CN_11890 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L4 Zone 4.1 [NCIS] | 3nos | 2026-12-31 | 2027-01-04 | 4 | NotStart
L4 | 4.1 | STB | P1_CN_11900 | CON¦EB¦STB¦T¦ Steel Beam Installation [9 nos] at L4 Zone 4.1 [NCIS] | 9nos | 2027-01-05 | 2027-01-13 | 8 | NotStart
L4 | 4.1 | MBR | P1_CN_11910 | CON¦EB¦MBR¦T¦ Main Beam RC [2 nos] at L4 Zone 4.1 [NCIS] | 2nos | 2027-01-14 | 2027-01-22 | 8 | NotStart
L4 | 4.1CIS-T | SLB | P1_CN_11920 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1272 m²] at L4 Zone 4.1 CIS [CIS] | 1272m² | 2027-01-23 | 2027-02-05 | 13 | NotStart
L4 | 4.1CIS-T | COL | P1_CN_11950 | CON¦EB¦COL¦T¦ Columns Work [7nos-CX25-CY42, CX25-CY43-1, CX25-CY44, CX24-CY44-1, CX22-CY43-2, CX20-CY43-1, WF-B2C64] | 7nos | 2027-02-08 | 2027-02-25 | 17 | NotStart
L4 | 4.1CIS-T | CRW | P1_CN_11930 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1nos-CW3B/ST01-01B] at L4 Zone 4.1 CIS [CIS] | 1nos | 2027-02-22 | 2027-04-02 | 39 | NotStart
L4 | 4.1CIS-T | WAL | P1_CN_11970 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [5nos-ST28/29,ST30/31,ST32/33,ST34/45,ST36/37] at L4 | 5nos | 2027-02-22 | 2027-04-02 | 39 | NotStart
L4 | 4.1CIS-T | COL | P1_CN_11960 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L4 Zone 4.1 CIS [CIS] | 7nos | 2027-02-26 | 2027-03-02 | 4 | NotStart
L4 | 4.1CIS-T | STB | P1_CN_11980 | CON¦EB¦STB¦T¦ Steel Beam Installation [44 nos] at L4 Zone 4.1 CIS [CIS] | 44nos | 2027-03-03 | 2027-03-09 | 6 | NotStart
L4 | 4.1CIS-T | MBR | P1_CN_11990 | CON¦EB¦MBR¦T¦ Main Beam RC [24 nos] at L4 Zone 4.1 CIS [CIS] | 24nos | 2027-03-10 | 2027-03-18 | 8 | NotStart
L4 | 4.1CIS-T | CRW | P1_CN_11940 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone 4.1 [CIS] | — | 2027-04-05 | 2027-04-13 | 8 | NotStart
L4 | 4.2 | SLB | P1_CN_11820 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [887 m²] at L4 Zone 4.2 [NCIS] | 887m² | 2026-12-02 | 2026-12-30 | 28 | NotStart
L4 | 4.2 | COL | P1_CN_11830 | CON¦EB¦COL¦NT¦ Columns Work [3nos-CX14-CY42,CX15-CY41,CX17-CY42] at L4 Zone 4.2 [NCIS] | 3nos | 2027-01-01 | 2027-01-11 | 10 | NotStart
L4 | 4.2 | COL | P1_CN_11840 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L4 Zone 4.2 [NCIS] | 3nos | 2027-01-12 | 2027-01-14 | 2 | NotStart
L4 | 4.2 | STB | P1_CN_11850 | CON¦EB¦STB¦NT¦ Steel Beam Installation [22 nos] at L4 Zone 4.2 [NCIS] | 22nos | 2027-01-15 | 2027-01-19 | 4 | NotStart
L4 | 4.2 | MBR | P1_CN_11860 | CON¦EB¦MBR¦NT¦ Main Beam RC [5 nos] at L4 Zone 4.2 [NCIS] | 5nos | 2027-01-20 | 2027-01-28 | 8 | NotStart
L4 | 4.2-T | COL | P1_CN_11780 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX15-CY43-1,CX17-CY42-1,CX14-CY43-1] at L4 Zone 4 | 3nos | 2026-11-09 | 2026-11-17 | 8 | NotStart
L4 | 4.2-T | COL | P1_CN_11790 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L4 Zone 4.2 [NCIS] | 3nos | 2026-11-18 | 2026-11-20 | 2 | NotStart
L4 | 4.2-T | STB | P1_CN_11800 | CON¦EB¦STB¦T¦ Steel Beam Installation [21 nos] at L4 Zone 4.2 [NCIS] | 21nos | 2026-11-23 | 2026-11-25 | 2 | NotStart
L4 | 4.2-T | MBR | P1_CN_11810 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L4 Zone 4.2 [NCIS] | 3nos | 2026-11-25 | 2026-12-03 | 8 | NotStart
L4 | 4.3-T | SLB | P1_CN_12050 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [943 m²] at L4 Zone 4.3 [NCIS] | 943m² | 2026-12-30 | 2027-01-27 | 28 | NotStart
L4 | 4.3-T | COL | P1_CN_12060 | CON¦EB¦COL¦T¦ Columns Work [7nos-CX20-CY38, CX21-CY38, CX22-CY38, CX19-CY39, CX21-CY40, CX19-CY41, CX21-CY41] | 7nos | 2027-02-09 | 2027-02-26 | 17 | NotStart
L4 | 4.3-T | COL | P1_CN_12070 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L4 Zone 4.3 [NCIS] | 7nos | 2027-03-01 | 2027-03-03 | 2 | NotStart
L4 | 4.3-T | STB | P1_CN_12080 | CON¦EB¦STB¦T¦ Steel Beam Installation [23 nos] at L4 Zone 4.3 [NCIS] | 23nos | 2027-03-04 | 2027-03-10 | 6 | NotStart
L4 | 4.3-T | MBR | P1_CN_12090 | CON¦EB¦MBR¦T¦ Main Beam RC [3 nos] at L4 Zone 4.3 [NCIS] | 3nos | 2027-03-11 | 2027-03-19 | 8 | NotStart
L4 | 4.3CIS-T | SLB | P1_CN_12100 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [374 m²] at L4 Zone 4.3 CIS [CIS] | 374m² | 2027-01-29 | 2027-02-17 | 19 | NotStart
L4 | 4.3CIS-T | COL | P1_CN_12110 | CON¦EB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3nos-CX22-CY40, CX24-CY40, CX24-CY39] at L4 Zo | 3nos | 2027-02-18 | 2027-02-26 | 8 | NotStart
L4 | 4.3CIS-T | COL | P1_CN_12120 | CON¦EB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L4 Zone 4.3 CIS [CIS] | 3nos | 2027-03-01 | 2027-03-03 | 2 | NotStart
L4 | 4.3CIS-T | STB | P1_CN_12150 | CON¦EB¦STB¦T¦ Steel Beam Installation [17 nos] at L4 Zone 4.3 CIS [CIS] | 17nos | 2027-03-04 | 2027-03-10 | 6 | NotStart
L4 | 4.3CIS-T | WAL | P1_CN_12130 | CON¦EB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [3nos-ST42/43,ST40/41,ST39/38] at L4 Zone 4.3 CIS [CIS] | 3nos | 2027-03-04 | 2027-04-14 | 41 | NotStart
L4 | 4.3CIS-T | MBR | P1_CN_12160 | CON¦EB¦MBR¦T¦ Main Beam RC [8 nos] at L4 Zone 4.3 CIS [CIS] | 8nos | 2027-03-11 | 2027-03-19 | 8 | NotStart
L4 | 4.3CIS-T | CRW | P1_CN_12140 | CON¦EB¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone 4.3 [CIS] | — | 2027-04-15 | 2027-04-23 | 8 | NotStart
L4 | 4.4 | SLB | P1_CN_12000 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [750 m²] at L4 Zone 4.4 [NCIS] | 750m² | 2027-03-05 | 2027-03-24 | 19 | NotStart
L4 | 4.4 | COL | P1_CN_12010 | CON¦EB¦COL¦NT¦ Columns Work [5nos-CX15-CY40, CX15-CY40-1, CX17-CY41, CX15-CY39, CX18-CY39] at L4 Zone 4.4 [NCIS] | 5nos | 2027-03-22 | 2027-04-08 | 17 | NotStart
L4 | 4.4 | COL | P1_CN_12020 | CON¦EB¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L4 Zone 4.4 [NCIS] | 5nos | 2027-04-09 | 2027-04-13 | 4 | NotStart
L4 | 4.4 | STB | P1_CN_12030 | CON¦EB¦STB¦NT¦ Steel Beam Installation [40 nos] at L4 Zone 4.4 [NCIS] | 40nos | 2027-04-14 | 2027-04-20 | 6 | NotStart
L4 | 4.4 | MBR | P1_CN_12040 | CON¦EB¦MBR¦NT¦ Main Beam RC [8 nos] at L4 Zone 4.4 [NCIS] | 8nos | 2027-04-21 | 2027-04-29 | 8 | NotStart
L5 | 1 | SLB | P1_CN_12170 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [323 m²] at L5 Zone 4.2 [NCIS] | 323m² | 2026-12-04 | 2027-02-11 | 69 | NotStart
L5 | 2 | SLB | P1_CN_12180 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [882 m²] at L2 Zone 4.2 [NCIS] | 882m² | 2027-02-09 | 2027-03-09 | 28 | NotStart
L5 | 2 | SLB | P1_CN_12190 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [882 m²] at L3 Zone 4.2 [NCIS] | 882m² | 2027-03-10 | 2027-04-07 | 28 | NotStart
L5 | 2 | SLB | P1_CN_12310 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [943 m²] at L2 Zone 4.3 [NCIS] | 943m² | 2027-03-22 | 2027-04-19 | 28 | NotStart
L5 | 2 | SLB | P1_CN_12330 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1317 m²] at L5 Zone 4.3 [CIS] | 1317m² | 2027-03-22 | 2027-05-28 | 67 | NotStart
L5 | 2 | SLB | P1_CN_12270 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [750 m²] at L2 Zone 4.4 [NCIS] | 750m² | 2027-03-25 | 2027-04-22 | 28 | NotStart
L5 | 2 | SLB | P1_CN_12200 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [549 m²] at L5 Zone 4.2 [NCIS] | 549m² | 2027-04-08 | 2027-05-19 | 41 | NotStart
L5 | 2 | SLB | P1_CN_12320 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [943 m²] at L3 Zone 4.3 [NCIS] | 943m² | 2027-04-20 | 2027-05-18 | 28 | NotStart
L5 | 2 | SLB | P1_CN_12280 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [750 m²] at L3 Zone 4.4 [NCIS] | 750m² | 2027-04-23 | 2027-05-21 | 28 | NotStart
L5 | 2 | SLB | P1_CN_12290 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [750m²] at L5 Zone 4.4 [NCIS] | 750m² | 2027-04-30 | 2027-05-28 | 28 | NotStart
L5 | 4.1 | CRW | P1_CN_12220 | CON¦EB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1nos-CW3B/P1-ST-01B] at L5 Zone 4.1 CIS [CIS] | 1nos | 2027-04-16 | 2027-05-27 | 41 | NotStart
L5 | 4.1 | CRW | P1_CN_12210 | CON¦EB¦CRW¦T¦ Staircase Flange from L5 Zone 4.1 [CIS] | — | 2027-04-30 | 2027-05-19 | 19 | NotStart
L5 | 4.1CIS | SLB | P1_CN_12260 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [589 m²] at L5 Zone 4.1 [NCIS] | 589m² | 2027-01-25 | 2027-03-05 | 39 | NotStart
L5 | 4.1CIS | SLB | P1_CN_12240 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [589 m²] at L2 Zone 4.1 [NCIS] | 589m² | 2027-03-08 | 2027-04-16 | 39 | NotStart
L5 | 4.1CIS | SLB | P1_CN_12250 | CON¦EB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [589 m²] at L3 Zone 4.1 [NCIS] | 589m² | 2027-04-19 | 2027-05-28 | 39 | NotStart
L5 | 4.1CIST | SLB | P1_CN_12230 | CON¦EB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1272 m²] at L5 Zone 4.1 [CIS] | 1272m² | 2027-03-19 | 2027-05-27 | 69 | NotStart
L5 | 4.3 | MBR | P1_CN_12300 | CON¦EB¦MBR¦T¦ Staircase Flange from L5 Zone 4.1 [CIS] | — | 2027-04-30 | 2027-05-19 | 19 | NotStart

## 4_NB_逐条
NB — 逐条活动（楼层/小区/工作量）
楼层 | 小区 | 专业 Trade | 活动编号 | 活动名称 Task Name | 工作量 Qty | 开始 | 完成 | 时长 (天) | 状态
B2 | B2-S1+1a | EAR | P1_CN_12440 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S1a | — | 2026-08-27 | 2026-08-29 | 2 | NotStart
B2 | B2-S1+1a | EXC | P1_CN_12450 | CON¦NB¦EXC¦ Excavation [3200 m³] at Zone B2-S1a | 3200m³ | 2026-08-30 | 2026-09-19 | 20 | NotStart
B2 | B2-S1+1a | DEM | P1_CN_12460 | CON¦NB¦DEM¦CJ3¦Demolition Existing Wall | — | 2026-09-20 | 2026-09-26 | 6 | NotStart
B2 | B2-S1+1a | DEM | P1_CN_12470 | CON¦NB¦DEM¦CJ4¦Demolition Existing Wall | — | 2026-09-27 | 2026-10-03 | 6 | NotStart
B2 | B2-S1+1a | SLB | P1_CN_12480 | CON¦NB¦SLB¦ B2 Slab [636 m²] + Pilecap Casting [5 nos ] at Zone B2-S1a | 636m²+5nos | 2026-10-04 | 2026-11-02 | 29 | NotStart
B2 | B2-S1+1a | EAR | P1_CN_12500 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S1 | — | 2026-10-21 | 2026-10-23 | 2 | NotStart
B2 | B2-S1+1a | EXC | P1_CN_12510 | CON¦NB¦EXC¦ Excavation [5000 m³] at Zone B2-S1 | 5000m³ | 2026-10-26 | 2026-12-02 | 37 | NotStart
B2 | B2-S1+1a | COL | P1_CN_12490 | CON¦NB¦COL¦ Columns Work [4nos WF-B2C24, WF-B2C25, WF-B2C33, WF-B2C34 + 1nos] | 5nos | 2026-11-03 | 2026-12-30 | 57 | NotStart
B2 | B2-S1+1a | CRW | P1_CN_12540 | CON¦NB¦CRW¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW4/ST-44B] at B2 Zone B2-S1 | 1nos | 2026-11-03 | 2027-01-25 | 83 | NotStart
B2 | B2-S1+1a | SLB | P1_CN_12520 | CON¦NB¦SLB¦ B2 Slab [999 m²] + Pilecap Casting [8 nos] at Zone B2-S1 | 999m²+8nos | 2026-11-03 | 2026-12-14 | 41 | NotStart
B2 | B2-S1+1a | COL | P1_CN_12530 | CON¦NB¦COL¦ Columns Work [3nos WF-B2C31, WF-B2C35, WF-B2C36 + 4nos] | 7nos | 2026-12-15 | 2027-01-04 | 20 | NotStart
B2 | B2-S10 | EAR | P1_CN_13120 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S10 | — | 2026-09-21 | 2026-09-23 | 2 | NotStart
B2 | B2-S10 | EXC | P1_CN_13130 | CON¦NB¦EXC¦ Excavation [4900 m³] at Zone B2-S10 | 4900m³ | 2026-09-24 | 2026-09-30 | 6 | NotStart
B2 | B2-S10 | SLB | P1_CN_13140 | CON¦NB¦SLB¦ B2 Slab [955 m²] + Pilecap Casting [11 nos] at Zone B2-S10 | 955m²+11nos | 2026-10-01 | 2026-10-29 | 28 | NotStart
B2 | B2-S10 | COL | P1_CN_13150 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [11 nos] at B2 Zone B2-S10 | 11nos | 2026-10-30 | 2026-12-28 | 59 | NotStart
B2 | B2-S11 | EAR | P1_CN_13220 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S11 | — | 2026-06-19 | 2026-06-23 | 4 | NotStart
B2 | B2-S11 | EXC | P1_CN_13230 | CON¦NB¦EXC¦ Excavation [3100 m³] at Zone B2-S11 | 3100m³ | 2026-06-24 | 2026-07-13 | 19 | NotStart
B2 | B2-S11 | SLB | P1_CN_13240 | CON¦NB¦SLB¦ B2 Slab + Pilecap Casting [610 m²] at Zone B2-S11 | 610m² | 2026-07-14 | 2026-08-11 | 28 | NotStart
B2 | B2-S11 | COL | P1_CN_13250 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [8 nos] at B2 Zone B2-S11 | 8nos | 2026-08-12 | 2026-10-08 | 57 | NotStart
B2 | B2-S11 | WAL | P1_CN_13260 | CON¦NB¦WAL¦Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-47B] at B2 Zone B2-S11 | 1nos | 2026-10-09 | 2026-12-31 | 83 | NotStart
B2 | B2-S12 | EAR | P1_CN_13160 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S12 | — | 2026-08-03 | 2026-08-05 | 2 | NotStart
B2 | B2-S12 | EXC | P1_CN_13170 | CON¦NB¦EXC¦ Excavation [6600 m³] at Zone B2-S12 | 6600m³ | 2026-08-06 | 2026-09-03 | 28 | NotStart
B2 | B2-S12 | SLB | P1_CN_13180 | CON¦NB¦SLB¦ B2 Slab [1291 m²] + Pilecap Casting [14 nos] at Zone B2-S12 | 1291m²+14nos | 2026-09-04 | 2026-10-02 | 28 | NotStart
B2 | B2-S12 | COL | P1_CN_13190 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [14 nos] at B2 Zone B2-S12 | 14nos | 2026-10-05 | 2026-12-01 | 57 | NotStart
B2 | B2-S12 | CRW | P1_CN_13200 | CON¦NB¦CRW¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-S-09] at B2 Zone B2-S12 | 1nos | 2026-10-05 | 2026-11-13 | 39 | NotStart
B2 | B2-S12 | WAL | P1_CN_13210 | CON¦NB¦WAL¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-09] at B2 Zone B2-S12 | 1nos | 2026-11-16 | 2026-12-25 | 39 | NotStart
B2 | B2-S13 | EAR | P1_CN_13040 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S13 | — | 2026-08-04 | 2026-08-06 | 2 | NotStart
B2 | B2-S13 | EXC | P1_CN_13050 | CON¦NB¦EXC¦ Excavation [3400 m³] at Zone B2-S13 | 3400m³ | 2026-08-07 | 2026-08-17 | 10 | NotStart
B2 | B2-S13 | SLB | P1_CN_13060 | CON¦NB¦SLB¦ B2 Slab [695 m²] + Pilecap Casting [9 nos] at Zone B2-S13 | 695m²+9nos | 2026-09-01 | 2026-09-29 | 28 | NotStart
B2 | B2-S13 | COL | P1_CN_13070 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [9 nos] at B2 Zone B2-S13 | 9nos | 2026-09-30 | 2026-11-26 | 57 | NotStart
B2 | B2-S14 | EAR | P1_CN_13000 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S14 | — | 2026-07-01 | 2026-07-03 | 2 | NotStart
B2 | B2-S14 | EXC | P1_CN_13010 | CON¦NB¦EXC¦ Excavation [3200 m³] at Zone B2-S14 | 3200m³ | 2026-07-06 | 2026-08-03 | 28 | NotStart
B2 | B2-S14 | SLB | P1_CN_13020 | CON¦NB¦SLB¦ B2 Slab [622 m²] + Pilecap Casting [9 nos] at Zone B2-S14 | 622m²+9nos | 2026-08-04 | 2026-09-01 | 28 | NotStart
B2 | B2-S14 | COL | P1_CN_13030 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [9 nos] at B2 Zone B2-S14 | 9nos | 2026-09-02 | 2026-10-29 | 57 | NotStart
B2 | B2-S2+S2a | EAR | P1_CN_12340 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S2a | — | 2026-07-17 | 2026-07-30 | 13 | NotStart
B2 | B2-S2+S2a | EXC | P1_CN_12350 | CON¦NB¦EXC¦ Excavation [3400 m³] at Zone B2-S2a | 3400m³ | 2026-07-31 | 2026-08-28 | 28 | NotStart
B2 | B2-S2+S2a | DEM | P1_CN_12360 | CON¦NB¦DEM¦CJ2¦Demolition Existing Wall | — | 2026-08-31 | 2026-09-08 | 8 | NotStart
B2 | B2-S2+S2a | SLB | P1_CN_12370 | CON¦NB¦SLB¦ B2 Slab [664 m²] + Pilecap Casting [7 nos] at Zone B2-S2a | 664m²+7nos | 2026-09-09 | 2026-10-20 | 41 | NotStart
B2 | B2-S2+S2a | COL | P1_CN_12380 | CON¦NB¦COL¦ Columns Work [4nos WF-B2C39, WF-B2C44, WF-B2C45, WF-B2C54 + 1nos] | 5nos | 2026-10-21 | 2026-11-18 | 28 | NotStart
B2 | B2-S2+S2a | WAL | P1_CN_12430 | CON¦NB¦WAL¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos CW3A/P1-ST-02B] at B2 Zone B2-S2 | 1nos | 2026-10-21 | 2027-01-12 | 83 | NotStart
B2 | B2-S2+S2a | EAR | P1_CN_12390 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S2 | — | 2026-12-03 | 2026-12-05 | 2 | NotStart
B2 | B2-S2+S2a | EXC | P1_CN_12400 | CON¦NB¦EXC¦ Excavation [5300 m³] at Zone B2-S2 | 5300m³ | 2026-12-06 | 2027-01-02 | 27 | NotStart
B2 | B2-S2+S2a | SLB | P1_CN_12410 | CON¦NB¦SLB¦ B2 Slab [1047 m²] + Pilecap Casting [7 nos] at Zone B2-S2 | 1047m²+7nos | 2027-01-04 | 2027-02-01 | 28 | NotStart
B2 | B2-S2+S2a | COL | P1_CN_12420 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos WF-B2C40 + 5nos] | 6nos | 2027-02-02 | 2027-03-31 | 57 | NotStart
B2 | B2-S3 | EAR | P1_CN_12690 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S3 | — | 2026-08-04 | 2026-08-06 | 2 | NotStart
B2 | B2-S3 | EXC | P1_CN_12700 | CON¦NB¦EXC¦ Excavation [6800 m³] at Zone B2-S3 | 6800m³ | 2026-08-07 | 2026-09-15 | 39 | NotStart
B2 | B2-S3 | SLB | P1_CN_12710 | CON¦NB¦SLB¦ B2 Slab [1354 m²] + Pilecap Casting [10 nos] at Zone B2-S3 | 1354m²+10nos | 2026-09-16 | 2026-10-14 | 28 | NotStart
B2 | B2-S3 | COL | P1_CN_12720 | CON¦NB¦COL¦ Columns Work [5 nos-WF-B2C29, WF-B2C30, WF-B2C32, WF-B2C37, WF-B2C38 + 4 nos] | 9nos | 2026-10-15 | 2026-12-11 | 57 | NotStart
B2 | B2-S3 | CRW | P1_CN_12730 | CON¦NB¦CRW¦ Core Wall / Staircase [Starter + Jumps + Casting + Curing] [1 nos-CW5/ST-05B] at B2 Zone B2-S3 | 1nos | 2026-12-14 | 2027-03-05 | 81 | NotStart
B2 | B2-S4 | EAR | P1_CN_12740 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S4 | — | 2026-10-05 | 2026-10-07 | 2 | NotStart
B2 | B2-S4 | EXC | P1_CN_12750 | CON¦NB¦EXC¦ Excavation [6600 m³] at Zone B2-S4 | 6600m³ | 2026-10-08 | 2026-11-05 | 28 | NotStart
B2 | B2-S4 | SLB | P1_CN_12760 | CON¦NB¦SLB¦ B2 Slab [1308 m²] + Pilecap Casting [10 nos] at Zone B2-S4 | 1308m²+10nos | 2026-11-11 | 2026-12-09 | 28 | NotStart
B2 | B2-S4 | COL | P1_CN_12770 | CON¦NB¦COL¦ Columns Work [9nos-WF-B2C41, WF-B2C42, WF-B2C43, WF-B2C48, WF-B2C49, WF-B2C53, WF-B2C50, WF-B2C52, WF-B2C58] | 9nos | 2026-12-10 | 2027-02-05 | 57 | NotStart
B2 | B2-S4 | CRW | P1_CN_12780 | CON¦NB¦CRW¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2b] at B2 Zone B2-S4 | 1nos | 2026-12-10 | 2027-03-03 | 83 | NotStart
B2 | B2-S5 | EAR | P1_CN_12790 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S5 | — | 2026-10-09 | 2026-10-11 | 2 | NotStart
B2 | B2-S5 | EXC | P1_CN_12800 | CON¦NB¦EXC¦ Excavation [7500 m³] at Zone B2-S5 | 7500m³ | 2026-10-12 | 2026-11-10 | 29 | NotStart
B2 | B2-S5 | SLB | P1_CN_12810 | CON¦NB¦SLB¦ B2 Slab [1496 m²] + Pilecap Casting [15 nos] at Zone B2-S5 | 1496m²+15nos | 2026-11-11 | 2026-12-01 | 20 | NotStart
B2 | B2-S5 | COL | P1_CN_12820 | CON¦NB¦COL¦Columns Work [3 nos-WF-B2C59, WF-B2C63, WF-B2C66 + 8 nos] at B2 Zone B2-S5 | 11nos | 2026-12-02 | 2027-01-28 | 57 | NotStart
B2 | B2-S5 | CRW | P1_CN_12830 | CON¦NB¦CRW¦Core Wall [Starter + Jumps + Casting + Curing] [2 nos-CW8/ST-03B,CW2A] at B2 Zone B2-S5 | 2nos | 2026-12-02 | 2027-02-23 | 83 | NotStart
B2 | B2-S6+6a | EAR | P1_CN_12600 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S6a | — | 2026-10-21 | 2026-10-23 | 2 | NotStart
B2 | B2-S6+6a | EXC | P1_CN_12610 | CON¦NB¦EXC¦ Excavation [3100 m³] at Zone B2-S6a | 3100m³ | 2026-10-24 | 2026-11-13 | 20 | NotStart
B2 | B2-S6+6a | SLB | P1_CN_12620 | CON¦NB¦SLB¦ B2 Slab [633 m²] + Pilecap Casting [7 nos] at Zone B2-S6a | 633m²+7nos | 2026-11-16 | 2026-12-03 | 17 | NotStart
B2 | B2-S6+6a | EAR | P1_CN_12640 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S6 | — | 2026-11-16 | 2026-11-18 | 2 | NotStart
B2 | B2-S6+6a | EXC | P1_CN_12650 | CON¦NB¦EXC¦ Excavation [4000 m³] at Zone B2-S6 | 4000m³ | 2026-11-19 | 2026-12-17 | 28 | NotStart
B2 | B2-S6+6a | COL | P1_CN_12630 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [7 nos] at B2 Zone B2-S6a | 7nos | 2026-12-04 | 2027-02-01 | 59 | NotStart
B2 | B2-S6+6a | SLB | P1_CN_12660 | CON¦NB¦SLB¦ B2 Slab [832 m²] + Pilecap Casting [4 nos] at Zone B2-S6 | 832m²+4nos | 2026-12-18 | 2027-01-06 | 19 | NotStart
B2 | B2-S6+6a | COL | P1_CN_12670 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos] at B2 Zone B2-S6 | 4nos | 2027-01-07 | 2027-03-05 | 57 | NotStart
B2 | B2-S6+6a | WAL | P1_CN_12680 | CON¦NB¦WAL¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos] at B2 Zone B2-S6 | 1nos | 2027-03-08 | 2027-05-28 | 81 | NotStart
B2 | B2-S7 | EAR | P1_CN_12550 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S7 | — | 2026-10-21 | 2026-10-23 | 2 | NotStart
B2 | B2-S7 | EXC | P1_CN_12560 | CON¦NB¦EXC¦ Excavation [5100 m³] at Zone B2-S7 | 5100m³ | 2026-10-26 | 2026-12-02 | 37 | NotStart
B2 | B2-S7 | SLB | P1_CN_12570 | CON¦NB¦SLB¦ B2 Slab [1030 m²] + Pilecap Casting [6 nos] at Zone B2-S7 | 1030m²+6nos | 2026-12-03 | 2026-12-31 | 28 | NotStart
B2 | B2-S7 | COL | P1_CN_12580 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [6 nos] at B2 Zone B2-S7 | 6nos | 2027-01-01 | 2027-03-01 | 59 | NotStart
B2 | B2-S7 | CRW | P1_CN_12590 | CON¦NB¦CRW¦Core Wall [Starter + Jumps + Casting + Curing] [1 nos] at B2 Zone B2-S7 | 1nos | 2027-03-02 | 2027-05-24 | 83 | NotStart
B2 | B2-S8 | EAR | P1_CN_12960 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S8 | — | 2026-09-15 | 2026-09-17 | 2 | NotStart
B2 | B2-S8 | EXC | P1_CN_12970 | CON¦NB¦EXC¦ Excavation [4900 m³] at Zone B2-S8 | 4900m³ | 2026-09-18 | 2026-10-01 | 13 | NotStart
B2 | B2-S8 | SLB | P1_CN_12980 | CON¦NB¦SLB¦ B2 Slab [989m²] + Pilecap Casting [12 nos] at Zone B2-S8 | 989m²+12nos | 2026-10-02 | 2026-10-30 | 28 | NotStart
B2 | B2-S8 | COL | P1_CN_12990 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [12 nos] at B2 Zone B2-S8 | 12nos | 2026-11-02 | 2026-12-29 | 57 | NotStart
B2 | B2-S8a+14a+13a | EAR | P1_CN_12840 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S14a | — | 2026-07-20 | 2026-07-22 | 2 | NotStart
B2 | B2-S8a+14a+13a | EXC | P1_CN_12850 | CON¦NB¦EXC¦ Excavation [2100 m³] at Zone B2-S14a | 2100m³ | 2026-07-23 | 2026-08-11 | 19 | NotStart
B2 | B2-S8a+14a+13a | SLB | P1_CN_12860 | CON¦NB¦SLB¦ B2 Slab [398 m²] + Pilecap Casting [8 nos] at Zone B2-S14a | 398m²+8nos | 2026-08-12 | 2026-08-31 | 19 | NotStart
B2 | B2-S8a+14a+13a | EAR | P1_CN_12880 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S13a | — | 2026-08-12 | 2026-08-14 | 2 | NotStart
B2 | B2-S8a+14a+13a | EXC | P1_CN_12890 | CON¦NB¦EXC¦ Excavation [1900 m³] at Zone B2-S13a | 1900m³ | 2026-08-17 | 2026-08-26 | 9 | NotStart
B2 | B2-S8a+14a+13a | SLB | P1_CN_12900 | CON¦NB¦SLB¦ B2 Slab [374 m²] + Pilecap Casting [5 nos] at Zone B2-S13a | 374m²+5nos | 2026-08-27 | 2026-09-15 | 19 | NotStart
B2 | B2-S8a+14a+13a | EAR | P1_CN_12920 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S8a | — | 2026-08-27 | 2026-08-31 | 4 | NotStart
B2 | B2-S8a+14a+13a | COL | P1_CN_12870 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [7 nos] at B2 Zone B2-S14a | 7nos | 2026-09-01 | 2026-10-28 | 57 | NotStart
B2 | B2-S8a+14a+13a | EXC | P1_CN_12930 | CON¦NB¦EXC¦ Excavation [3200 m³] at Zone B2-S8a | 3200m³ | 2026-09-01 | 2026-09-14 | 13 | NotStart
B2 | B2-S8a+14a+13a | SLB | P1_CN_12940 | CON¦NB¦SLB¦ B2 Slab [629 m²] + Pilecap Casting [8 nos] at Zone B2-S8a | 629m²+8nos | 2026-09-15 | 2026-10-13 | 28 | NotStart
B2 | B2-S8a+14a+13a | COL | P1_CN_12910 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [5 nos] at B2 Zone B2-S13a | 5nos | 2026-09-16 | 2026-11-12 | 57 | NotStart
B2 | B2-S8a+14a+13a | COL | P1_CN_12950 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-B2C60, WF-B2C64 + 6 nos] at B2 Zone B2-S8a | 8nos | 2026-10-14 | 2026-12-10 | 57 | NotStart
B2 | B2-S9 | EAR | P1_CN_13080 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone B2-S9 | — | 2026-08-18 | 2026-08-20 | 2 | NotStart
B2 | B2-S9 | EXC | P1_CN_13090 | CON¦NB¦EXC¦ Excavation [4300 m³] at Zone B2-S9 | 4300m³ | 2026-08-21 | 2026-09-18 | 28 | NotStart
B2 | B2-S9 | SLB | P1_CN_13100 | CON¦NB¦SLB¦ B2 Slab [871 m²] + Pilecap Casting [12 nos] at Zone B2-S9 | 871m²+12nos | 2026-09-21 | 2026-10-19 | 28 | NotStart
B2 | B2-S9 | COL | P1_CN_13110 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [12 nos] at B2 Zone B2-S9 | 12nos | 2026-10-20 | 2026-12-16 | 57 | NotStart
B1 | A-01+03 | SLB | P1_CN_13800 | CON¦NB¦SLB¦ Slab Casting [971 m²] + Beam Works [6 nos] at Zone A-01+03 | 971m²+6nos | 2026-04-01 | 2026-06-30 | 90 | NotStart
B1 | A-01+03 | COL | P1_CN_13810 | CON¦NB¦COL¦ Columns Work [10 nos-MK-B2C71, 72, 82, 83, 30, 31, 44, 45, 57, 58] at B1 Zone A-01+03 | 10nos | 2026-07-01 | 2026-08-27 | 57 | NotStart
B1 | A-02+B-01 | SLB | P1_CN_13840 | CON¦NB¦SLB¦ Slab Casting [1180 m²] + Beam Works [5 nos] at Zone B-01 | 1180m²+5nos | 2026-04-01 | 2026-05-28 | 57 | NotStart
B1 | A-02+B-01 | COL | P1_CN_13850 | CON¦NB¦COL¦ Columns Work [15 nos-MK-B2C73, 74, 75, 84, 85, 86, 32, 33, 34, 46, 47, 48, 59, 60, 61] at B1 Zone B-01 | 15nos | 2026-05-29 | 2026-08-11 | 74 | NotStart
B1 | A-04 | SLB | P1_CN_13890 | CON¦NB¦SLB¦ Slab Casting [563 m²] + Beam Works at Zone A-04 | 563m² | 2026-07-01 | 2026-07-29 | 28 | NotStart
B1 | A-04 | COL | P1_CN_13900 | CON¦NB¦COL¦ Columns Work [7 nos-MK-B2C4, 5, 15, 41, WF-B2C67, 68, 69] at B1 Zone A-04 | 7nos | 2026-07-30 | 2026-09-25 | 57 | NotStart
B1 | A-05+06 | SLB | P1_CN_13750 | CON¦NB¦SLB¦ Slab Casting [428 m²] + Beam Works at Zone A-05 | 428m² | 2026-04-01 | 2026-07-07 | 97 | NotStart
B1 | A-05+06 | SLB | P1_CN_13780 | CON¦NB¦SLB¦ Slab [571 m²] + Beam Works [7 nos] at Zone A-06 | 571m²+7nos | 2026-04-01 | 2026-07-07 | 97 | NotStart
B1 | A-05+06 | COL | P1_CN_13760 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [7 nos-MK-B2C66, 69, 70, 79, 80, 81, 68] at B1 Zone A-05 | 7nos | 2026-07-08 | 2026-09-03 | 57 | NotStart
B1 | A-05+06 | COL | P1_CN_13790 | CON¦NB¦COL¦ Columns Work [9 nos-MK-B2C27, 28, 29, 40, 42, 43, 53, 55, 56] at B1 Zone A-06 | 9nos | 2026-07-08 | 2026-09-23 | 77 | NotStart
B1 | A-07 | SLB | P1_CN_13720 | CON¦NB¦SLB¦ Slab Casting [571 m²] + Beam Works [4 nos] at Zone A-07 | 571m²+4nos | 2026-04-01 | 2026-06-08 | 68 | NotStart
B1 | A-07 | COL | P1_CN_13730 | CON¦NB¦COL¦Columns Work [8 nos-MK-B2C89, 90, 91, 92, 93, 93a, 94, 94a] at B1 Zone A-07 | 8nos | 2026-06-09 | 2026-08-14 | 66 | NotStart
B1 | B-02 | SLB | P1_CN_13930 | CON¦NB¦SLB¦ Slab Casting [720 m²] + Beam Works at Zone B-02 | 720m² | 2026-04-01 | 2026-06-30 | 90 | NotStart
B1 | B-02 | COL | P1_CN_13940 | CON¦NB¦COL¦ Columns Work [9 nos-MK-B2C1, 3, 6, 7, 8, 17, 18, 19, 41] at B1 Zone B-02 | 9nos | 2026-07-01 | 2026-08-27 | 57 | NotStart
B1 | B-03 | SLB | P1_CN_14030 | CON¦NB¦SLB¦ Slab Casting [1201 m²] + Beam Works [24 nos] at Zone B-03 | 1201m²+24nos | 2026-04-01 | 2026-06-04 | 64 | NotStart
B1 | B-03 | COL | P1_CN_14040 | CON¦NB¦COL¦ Columns Work [15 nos-MK-B2C9, 10, 11, 12, 20, 21, 22, 23, 24, 25, 26, 35, 36, 37, 39] | 15nos | 2026-06-05 | 2026-08-12 | 68 | NotStart
B1 | B-03 | CRW | P1_CN_14060 | CON¦NB¦CRW¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-ST-47B] at B1 Zone B-03 | 1nos | 2026-08-13 | 2026-10-07 | 55 | NotStart
B1 | B-03 | WAL | P1_CN_14070 | CON¦NB¦WAL¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-09B] at B1 Zone B-03 | 1nos | 2026-10-08 | 2026-12-30 | 83 | NotStart
B1 | B-04+04A | SLB | P1_CN_14000 | CON¦NB¦SLB¦ Slab Casting [317 m²] + Beam Works [8 nos] at B1 Zone B-04A | 317m²+8nos | 2026-04-01 | 2026-05-08 | 37 | NotStart
B1 | B-04+04A | SLB | P1_CN_13970 | CON¦NB¦SLB¦ Slab Casting [804 m²] + Beam Works [29 nos] at B1 Zone B-04 | 804m²+29nos | 2026-04-01 | 2026-05-08 | 37 | NotStart
B1 | B-04+04A | COL | P1_CN_13980 | CON¦NB¦COL¦ Columns Work [10 nos-MK-B2C50a, 51, 52, 64, 65, 76, 77, 78, 87, 88] at B1 Zone B-04+04A | 10nos | 2026-05-11 | 2026-07-16 | 66 | NotStart
B1 | B-04+04A | COL | P1_CN_14010 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-MK-B2C49, 50, 62, 63] at B1 Zone B-04A | 4nos | 2026-05-11 | 2026-07-16 | 66 | NotStart
B1 | C-01a+b | EAR | P1_CN_13270 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone C-01 | — | 2026-04-01 | 2026-05-18 | 47 | NotStart
B1 | C-01a+b | EXC | P1_CN_13280 | CON¦NB¦EXC¦ Excavation [13000 m³] at Zone C-01 | 13000m³ | 2026-05-19 | 2026-06-25 | 37 | NotStart
B1 | C-01a+b | SLB | P1_CN_13290 | CON¦NB¦SLB¦ Slab Casting [1343 m²] + Beam Works [10 nos] at Zone C-01 | 1343m²+10nos | 2026-06-26 | 2026-07-16 | 20 | NotStart
B1 | C-01a+b | COL | P1_CN_13300 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [6 nos-WF-B2C54, 60, 64, 39, 44, 45 + 6 nos] | 12nos | 2026-07-17 | 2026-09-14 | 59 | NotStart
B1 | C-01a+b | WAL | P1_CN_13310 | CON¦NB¦WAL¦Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-CW4/ST-44B] at B1 Zone C-01a+b | 1nos | 2027-01-13 | 2027-04-06 | 83 | NotStart
B1 | C-02 | EAR | P1_CN_13320 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone C-02 | — | 2026-06-26 | 2026-06-30 | 4 | NotStart
B1 | C-02 | EXC | P1_CN_13330 | CON¦NB¦EXC¦ Excavation [21000 m³] at Zone C-02 | 21000m³ | 2026-07-01 | 2026-07-28 | 27 | NotStart
B1 | C-02 | SLB | P1_CN_13340 | CON¦NB¦SLB¦ Slab Casting [1457 m²] + Beam Works [29 nos] at Zone C-02 | 1457m²+29nos | 2026-07-29 | 2026-08-26 | 28 | NotStart
B1 | C-02 | COL | P1_CN_13350 | CON¦NB¦COL¦Columns Work [Rebar + Formwork + Casting + Curing] [5 nos-WF-B2C24, 25, 33, 34, 35] at B1-L1 Zone C-02 | 5nos | 2026-08-27 | 2026-10-23 | 57 | NotStart
B1 | C-02 | WAL | P1_CN_13360 | CON¦NB¦WAL¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW3A/ST-02B] at B1-L1 Zone C-02 | 1nos | 2027-02-08 | 2027-04-30 | 81 | NotStart
B1 | D-01 | EAR | P1_CN_13370 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone D-01 | — | 2026-07-29 | 2026-07-31 | 2 | NotStart
B1 | D-01 | EXC | P1_CN_13380 | CON¦NB¦EXC¦ Excavation [11000 m³] at Zone D-01 | 11000m³ | 2026-08-01 | 2026-08-30 | 29 | NotStart
B1 | D-01 | SLB | P1_CN_13390 | CON¦NB¦SLB¦Slab Casting [1349 m²] + Beam Works [22 nos] at Zone D-01 | 1349m²+22nos | 2026-09-25 | 2026-10-15 | 20 | NotStart
B1 | D-01 | COL | P1_CN_13410 | CON¦NB¦COL¦Columns Work [9 nos-WF-B2C6, 7, 9, 14, 15, 16, 22, 23, 21 at B1 Zone D-01 | 9nos | 2026-10-16 | 2026-11-05 | 20 | NotStart
B1 | D-01 | COL | P1_CN_13420 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-WF-B1TC1, 2, 3, 4] at B1 Zone D-01 | 4nos | 2026-11-06 | 2026-11-26 | 20 | NotStart
B1 | D-02 | EAR | P1_CN_13450 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone D-02 | — | 2026-09-18 | 2026-09-20 | 2 | NotStart
B1 | D-02 | EXC | P1_CN_13460 | CON¦NB¦EXC¦ Excavation [13200 m³] at Zone D-02 | 13200m³ | 2026-09-21 | 2026-10-20 | 29 | NotStart
B1 | D-02 | SLB | P1_CN_13470 | CON¦NB¦SLB¦ Slab Casting [1611 m²] + Beam Works [15 nos] at Zone D-02 | 1611m²+15nos | 2026-10-21 | 2026-11-18 | 28 | NotStart
B1 | D-02 | COL | P1_CN_13490 | CON¦NB¦COL¦ Columns Work [14 nos-WF-B2C1, 2, 3, 3a, 4, 5, 10, 11, 12, 13, 18, 19, 17, 20] at B1-L1 Zone D-02 | 14nos | 2026-11-19 | 2027-01-15 | 57 | NotStart
B1 | E-01 | EAR | P1_CN_13520 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone E-01 | — | 2026-04-01 | 2026-06-18 | 78 | NotStart
B1 | E-01 | EXC | P1_CN_13530 | CON¦NB¦EXC¦ Excavation [13800 m³] at Zone E-01 | 13800m³ | 2026-07-14 | 2026-08-12 | 29 | NotStart
B1 | E-01 | EXC | P1_CN_13540 | CON¦NB¦EXC¦ Piling Work [3 nos] at Zone E-01 | 3nos | 2026-07-24 | 2026-08-12 | 19 | NotStart
B1 | E-01 | SLB | P1_CN_13550 | CON¦NB¦SLB¦ Slab Casting [1415 m²] + Beam Works at Zone E-01 | 1415m² | 2026-08-13 | 2026-09-10 | 28 | NotStart
B1 | E-01 | COL | P1_CN_13560 | CON¦NB¦COL¦ Columns Work [7 nos-WF-B2C31, 32, 36, 37, 38, 29, 30 + 2 nos] at B1-L1 Zone E-01 | 9nos | 2026-09-11 | 2026-11-09 | 59 | NotStart
B1 | E-01 | CRW | P1_CN_13570 | CON¦NB¦CRW¦ Core Wall / Staircase [Starter + Jumps + Casting + Curing] [1 nos-CW5/ST-05B] at B1-L1 Zone E-01 | 1nos | 2026-09-11 | 2026-11-09 | 59 | NotStart
B1 | F-01 | EAR | P1_CN_13600 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone F-01 | — | 2026-07-21 | 2026-07-23 | 2 | NotStart
B1 | F-01 | EXC | P1_CN_13610 | CON¦NB¦EXC¦ Excavation [19000 m³] at Zone F-01 | 19000m³ | 2026-07-24 | 2026-09-03 | 41 | NotStart
B1 | F-01 | SLB | P1_CN_13620 | CON¦NB¦SLB¦ Slab Casting [1941 m²] + Beam Works [8 nos] at Zone F-01 | 1941m²+8nos | 2026-09-04 | 2026-10-02 | 28 | NotStart
B1 | F-01 | COL | P1_CN_13630 | CON¦NB¦COL¦ Columns Work [9 nos-WF-B2C40, 41, 42, 43, 48, 49, 53, 50, 58 + 5 nos] at B1-L1 Zone F-01 | 14nos | 2026-10-05 | 2026-12-01 | 57 | NotStart
B1 | F-01 | CRW | P1_CN_13640 | CON¦NB¦CRW¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2B] at B1-L1 Zone F-01 | 1nos | 2027-03-04 | 2027-05-26 | 83 | NotStart
B1 | F-02 | EAR | P1_CN_13650 | CON¦NB¦EAR¦ Earthworks / Site Cleaning / Kingpost ECC Casting at Zone F-02 | — | 2026-09-04 | 2026-09-06 | 2 | NotStart
B1 | F-02 | EXC | P1_CN_13660 | CON¦NB¦EXC¦ Excavation [9000 m³] at Zone F-02 | 9000m³ | 2026-09-07 | 2026-09-17 | 10 | NotStart
B1 | F-02 | SLB | P1_CN_13670 | CON¦NB¦SLB¦ Slab Casting [1001 m²] + Beam Works [32 nos] at Zone F-02 | 1001m²+32nos | 2026-09-18 | 2026-10-08 | 20 | NotStart
B1 | F-02 | COL | P1_CN_13680 | CON¦NB¦COL¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C59, 66, 63 + 3 nos] at B1-L1 Zone F-02 | 6nos | 2026-10-09 | 2026-12-07 | 59 | NotStart
B1 | F-02 | CRW | P1_CN_13690 | CON¦NB¦CRW¦ Core Wall [Starter + Jumps + Casting + Curing] [2 nos-CW8/ST-03B,CW2A] at B1-L1 Zone F-02 | 2nos | 2027-02-24 | 2027-05-18 | 83 | NotStart
B1 | S-1 | SLB | P1_CN_13820 | CON¦NB¦SLB¦ B1M Slab Casting [976 m²] + Beam Works [8 nos] at Zone B1M-S1 | 976m²+8nos | 2026-09-24 | 2026-10-22 | 28 | NotStart
B1 | S-1 | COL | P1_CN_13830 | CON¦NB¦COL¦Columns Work [14 nos-MK-B2C58, 59, 60, 72, 73, 74, 83, 84, 85, 92, 93, 93a, 94, 94a] at B1M Zone B1M-S1 | 14nos | 2026-10-23 | 2026-11-20 | 28 | NotStart
B1 | S-2 | SLB | P1_CN_13870 | CON¦NB¦SLB¦ B1M Slab Casting [1113] m²] + Beam Works [28 nos] at Zone B1M-S2 | 28nos | 2026-08-12 | 2026-09-09 | 28 | NotStart
B1 | S-2 | COL | P1_CN_13880 | CON¦NB¦COL¦Columns Work [12 nos-MK-B2C61, 62, 63, 64, 65, 75, 76, 77, 78, 86, 87, 88] at B1M Zone B1M-S2 | 12nos | 2026-09-10 | 2026-10-08 | 28 | NotStart
B1 | S-3 | SLB | P1_CN_13950 | CON¦NB¦SLB¦ B1M Slab Casting [1915 m²] + Beam Works [45 nos] at Zone B1M-3 | 1915m²+45nos | 2026-08-28 | 2026-09-25 | 28 | NotStart
B1 | S-3 | COL | P1_CN_13960 | CON¦NB¦COL¦B1M Columns Work [25 nos-MK-B2C3,8,9,10,11,12,19,20,21,22,23,24,25,26,34,35,36,37,39,48,49,50,50a,51,52] | 25nos | 2026-10-27 | 2026-11-24 | 28 | NotStart
B1 | S-4 | SLB | P1_CN_13910 | CON¦NB¦SLB¦ B1M Slab Casting [1514 m²] + Beam Works [5 nos] at Zone B1M-S4 | 1514m²+5nos | 2026-09-28 | 2026-10-26 | 28 | NotStart
B1 | S-4 | COL | P1_CN_13920 | CON¦NB¦COL¦B1M Columns Work [19 nos-MK-B2C1, 2, 4, 5, 6, 7, 15, 16, 17, 18, 30, 31, 32, 33, 45, 46, 47, WF-B2C68, 69] | 19nos | 2026-10-27 | 2026-11-24 | 28 | NotStart
B1 | S-5 | SLB | P1_CN_13700 | CON¦NB¦SLB¦ B1M Slab Casting [1510 m²] + Beam Works [30 nos] at Zone B1M-5 | 1510m²+30nos | 2026-12-08 | 2027-01-05 | 28 | NotStart
B1 | S-5 | COL | P1_CN_13710 | CON¦NB¦COL¦ Columns Work [5 nos-WF-B2C59, 63, 58, 53, 66 + 6 nos] at Zone B1M-5 | 11nos | 2027-01-06 | 2027-02-03 | 28 | NotStart
B1 | S-6 | SLB | P1_CN_13580 | CON¦NB¦SLB¦ B1M Slab Casting [1364 m²] + Beam Works [22 nos] at Zone B1M-6 | 1364m²+22nos | 2026-12-10 | 2027-01-07 | 28 | NotStart
B1 | S-6 | COL | P1_CN_13590 | CON¦NB¦COL¦ B1M Columns Work [5 nos-WF-B2C24, 29, 30, 38, 43 + 3nos] at Zone B1M-6 | 8nos | 2027-01-08 | 2027-02-05 | 28 | NotStart
B1 | S-7 | SLB | P1_CN_13430 | CON¦NB¦SLB¦ B1M Slab Casting [1539 m²] + Beam Works [33 nos] at Zone B1M-S7 | 1539m²+33nos | 2026-11-27 | 2026-12-25 | 28 | NotStart
B1 | S-7 | COL | P1_CN_13440 | CON¦NB¦COL¦ Columns Work [14 nos-WF-B2C5, 6, 7, 9, 13, 14, 15, 16, 20, 21, 22, 23] at Zone B1M-S7 | 14nos | 2026-12-28 | 2027-01-25 | 28 | NotStart
B1 | S-8 | SLB | P1_CN_13500 | CON¦NB¦SLB¦ B1M Slab Casting [836 m²] + Beam Works at Zone B1M-S8 | 836m² | 2027-02-08 | 2027-02-19 | 11 | NotStart
B1 | S-8 | COL | P1_CN_13510 | CON¦NB¦COL¦ Columns Work [9 nos-WF-B2C2, 3a, 4, 10, 11, 12, 17, 18, 19] at Zone B1M-S8 | 9nos | 2027-02-22 | 2027-04-20 | 57 | NotStart
L1 | 2.1 | SLB | P1_CN_14140 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [373 m²] + Beam RC [25 nos] at L1 Zone 2.1 [NCIS] | 373m²+25nos | 2026-04-01 | 2026-05-04 | 33 | NotStart
L1 | 2.1 | CRW | P1_CN_14150 | CON¦NB¦CRW¦NT¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos] at L1 Zone 2.1 [NCIS] | 1nos | 2026-05-05 | 2026-07-06 | 62 | NotStart
L1 | 2.1 | COL | P1_CN_14160 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-MK-B2C46,WF-B2C47] at L1 Zone 2.1 [NCIS] | 2nos | 2026-06-18 | 2026-06-26 | 8 | NotStart
L1 | 2.1 | COL | P1_CN_14170 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L1 Zone 2.1 [NCIS] | 2nos | 2026-06-29 | 2026-07-01 | 2 | NotStart
L1 | 2.1 | STB | P1_CN_14180 | CON¦NB¦STB¦NT¦ Steel Beam Installation at L1 Zone 2.1 [NCIS] | — | 2026-07-02 | 2026-07-06 | 4 | NotStart
L1 | 2.1 | MBR | P1_CN_14190 | CON¦NB¦MBR¦NT¦ Main Beam RC [3 nos] at L1 Zone 2.1 [NCIS] | 3nos | 2026-07-07 | 2026-07-15 | 8 | NotStart
L1 | 2.1-T | SLB | P1_CN_14080 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [524 m²] + Beam RC [1 nos] at L1 Zone 2.1 [NCIS] | 524m²+1nos | 2026-04-01 | 2026-06-03 | 63 | NotStart
L1 | 2.1-T | COL | P1_CN_14100 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C39,40,44] at L1 Zone 2.1 [NCIS] | 3nos | 2026-06-04 | 2026-06-12 | 8 | NotStart
L1 | 2.1-T | CRW | P1_CN_14090 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW3A/ST-02,02A,02B] at L1 Zone 2.1 [NCIS] | 1nos | 2026-06-04 | 2026-08-05 | 62 | NotStart
L1 | 2.1-T | COL | P1_CN_14110 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [3 nos] at L1 Zone 2.1 [NCIS] | 3nos | 2026-06-15 | 2026-06-17 | 2 | NotStart
L1 | 2.1-T | STB | P1_CN_14120 | CON¦NB¦STB¦T¦ Steel Beam Installation at L1 Zone 2.1 [NCIS] | — | 2026-06-18 | 2026-08-05 | 48 | NotStart
L1 | 2.1-T | MBR | P1_CN_14130 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L1 Zone 2.1 [NCIS] | 7nos | 2026-08-06 | 2026-08-14 | 8 | NotStart
L1 | 2.1-T | MEP | P1_CN_20300 | CON¦NB¦MEP¦T¦ Transformer Room at L1 Zone 2.1 [NCIS] | — | 2026-08-17 | 2026-08-17 | 0 | NotStart
L1 | 2.1CIS | SLB | P1_CN_14250 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [518 m²] + Beam RC [21 nos] at L1 Zone 2.1 [CIS] | 518m²+21nos | 2026-04-01 | 2026-06-03 | 63 | NotStart
L1 | 2.1CIS | WAL | P1_CN_14280 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST24/25, ST 26/27] at L1 Zone 2.1 [CIS] | 2nos | 2026-06-04 | 2026-07-18 | 44 | NotStart
L1 | 2.1CIS | COL | P1_CN_14260 | CON¦NB¦COL¦NT¦ Columns Work [5 nos-WF-1C104,WF-B2C51,55,56,57] at L1 Zone 2.1 [CIS] | 5nos | 2026-06-22 | 2026-06-30 | 8 | NotStart
L1 | 2.1CIS | COL | P1_CN_14270 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone 2.1 [CIS] | 5nos | 2026-07-01 | 2026-07-03 | 2 | NotStart
L1 | 2.1CIS | STB | P1_CN_14290 | CON¦NB¦STB¦NT¦ Steel Beam Installation [38 nos] at L1 Zone 2.1 [CIS] | 38nos | 2026-07-04 | 2026-07-18 | 14 | NotStart
L1 | 2.1CIS | MBR | P1_CN_14300 | CON¦NB¦MBR¦NT¦ Main Beam RC [15 nos] at L1 Zone 2.1 [CIS] | 15nos | 2026-07-20 | 2026-07-28 | 8 | NotStart
L1 | 2.1CIS-T | SLB | P1_CN_14200 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [153 m²] + Beam RC [3 nos] at L1 Zone 2.1 [CIS] | 153m²+3nos | 2026-04-01 | 2026-06-05 | 65 | NotStart
L1 | 2.1CIS-T | COL | P1_CN_14210 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C18,27] at L1 Zone 2.1 [CIS] | 2nos | 2026-06-08 | 2026-06-16 | 8 | NotStart
L1 | 2.1CIS-T | COL | P1_CN_14220 | CON¦NB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L1 Zone 2.1 [CIS] | 2nos | 2026-06-17 | 2026-06-19 | 2 | NotStart
L1 | 2.1CIS-T | STB | P1_CN_14230 | CON¦NB¦STB¦T¦ Steel Beam Installation at L1 Zone 2.1 [CIS] | — | 2026-06-22 | 2026-06-30 | 8 | NotStart
L1 | 2.1CIS-T | MBR | P1_CN_14240 | CON¦NB¦MBR¦T¦ Main Beam RC [4 nos] at L1 Zone 2.1 [CIS] | 4nos | 2026-07-07 | 2026-07-15 | 8 | NotStart
L1 | 2.2 | SLB | P1_CN_14370 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [218 m²] + Beam RC at L1 Zone 2.2 [NCIS] | 218m² | 2026-06-04 | 2026-06-23 | 19 | NotStart
L1 | 2.2 | COL | P1_CN_14380 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-B2C26] at L1 Zone 2.2 [NCIS] | 1nos | 2026-10-07 | 2026-10-15 | 8 | NotStart
L1 | 2.2 | COL | P1_CN_14390 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [1 nos] at L1 Zone 2.2 [NCIS] | 1nos | 2026-10-16 | 2026-10-20 | 4 | NotStart
L1 | 2.2 | STB | P1_CN_14400 | CON¦NB¦STB¦NT¦ Steel Beam Installation [26 nos] at L1 Zone 2.2 [NCIS] | 26nos | 2026-10-21 | 2026-10-23 | 2 | NotStart
L1 | 2.2 | MBR | P1_CN_14410 | CON¦NB¦MBR¦NT¦ Main Beam RC [12 nos] at L1 Zone 2.2 [NCIS] | 12nos | 2026-10-26 | 2026-11-03 | 8 | NotStart
L1 | 2.2-T | SLB | P1_CN_14310 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [634 m²] + Beam RC [1 nos] at L1 Zone 2.2 [NCIS] | 634m²+1nos | 2026-05-05 | 2026-06-03 | 29 | NotStart
L1 | 2.2-T | WAL | P1_CN_14340 | CON¦NB¦WAL¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW4/ST-44B,49] at L1 Zone 2.2 [NCIS] | 1nos | 2026-08-27 | 2026-10-07 | 41 | NotStart
L1 | 2.2-T | COL | P1_CN_14320 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [5 nos-WF-B2C24,25,33,34,35] at L1 Zone 2.2 [NCIS] | 5nos | 2026-09-01 | 2026-09-14 | 13 | NotStart
L1 | 2.2-T | COL | P1_CN_14330 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone 2.2 [NCIS] | 5nos | 2026-09-15 | 2026-09-17 | 2 | NotStart
L1 | 2.2-T | STB | P1_CN_14350 | CON¦NB¦STB¦T¦ Steel Beam Installation [66 nos] at L1 Zone 2.2 [NCIS] | 66nos | 2026-09-18 | 2026-10-06 | 18 | NotStart
L1 | 2.2-T | MBR | P1_CN_14360 | CON¦NB¦MBR¦T¦ Main Beam RC [10 nos] at L1 Zone 2.2 [NCIS] | 10nos | 2026-10-07 | 2026-10-15 | 8 | NotStart
L1 | 2.3-T | SLB | P1_CN_14420 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1174 m²] + Beam RC [8 nos] at L1 Zone 2.3 [NCIS] | 1174m²+8nos | 2026-04-01 | 2026-05-04 | 33 | NotStart
L1 | 2.3-T | COL | P1_CN_14430 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [5 nos-WF-B2CC41,42,43,48,49] at L1 Zone 2.3 [NCIS] | 5nos | 2026-05-05 | 2026-05-13 | 8 | NotStart
L1 | 2.3-T | COL | P1_CN_14440 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone 2.3 [NCIS] | 5nos | 2026-05-14 | 2026-05-18 | 4 | NotStart
L1 | 2.3-T | STB | P1_CN_14450 | CON¦NB¦STB¦T¦ Steel Beam Installation [51 nos] at L1 Zone 2.3 [NCIS] | 51nos | 2026-05-19 | 2026-05-27 | 8 | NotStart
L1 | 2.3-T | MBR | P1_CN_14460 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L1 Zone 2.3 [NCIS] | 7nos | 2026-05-28 | 2026-06-05 | 8 | NotStart
L1 | 2.3CIS-T | SLB | P1_CN_14470 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [501 m²] + Beam RC [5 nos] at L1 Zone 2.3 [CIS] | 501m²+5nos | 2026-04-21 | 2026-05-08 | 17 | NotStart
L1 | 2.3CIS-T | CRW | P1_CN_14480 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2B] at L1 Zone 2.3 [CIS] | 1nos | 2026-05-11 | 2026-07-10 | 60 | NotStart
L1 | 2.3CIS-T | COL | P1_CN_14490 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-B2C50] at L1 Zone 2.3 [CIS] | 1nos | 2026-05-11 | 2026-05-19 | 8 | NotStart
L1 | 2.3CIS-T | COL | P1_CN_14500 | CON¦NB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L1 Zone 2.3 [CIS] | 1nos | 2026-05-20 | 2026-05-22 | 2 | NotStart
L1 | 2.3CIS-T | STB | P1_CN_14510 | CON¦NB¦STB¦T¦ Steel Beam Installation [26 nos] at L1 Zone 2.3 [CIS] | 26nos | 2026-05-25 | 2026-07-02 | 38 | NotStart
L1 | 2.3CIS-T | MBR | P1_CN_14520 | CON¦NB¦MBR¦T¦ Main Beam RC [12 nos] at L1 Zone 2.3 [CIS] | 12nos | 2026-07-13 | 2026-07-21 | 8 | NotStart
L1 | 2.4 | MBR | P1_CN_14590 | CON¦NB¦MBR¦NT¦ Main Beam RC [6 nos] at L1 Zone 2.4 [NCIS] | 6nos | 2027-01-08 | 2027-01-18 | 10 | NotStart
L1 | 2.4-T | SLB | P1_CN_14530 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1347 m²] + Beam RC [5 nos] at L1 Zone 2.4 [NCIS] | 1347m²+5nos | 2026-07-03 | 2026-07-31 | 28 | NotStart
L1 | 2.4-T | COL | P1_CN_14550 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-WF-B2C31,32,36,37 + 2 nos] at L1 Zone 2.4 [NCIS] | 6nos | 2026-09-01 | 2026-09-09 | 8 | NotStart
L1 | 2.4-T | COL | P1_CN_14560 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L1 Zone 2.4 [NCIS] | 6nos | 2026-09-10 | 2026-09-14 | 4 | NotStart
L1 | 2.4-T | STB | P1_CN_14570 | CON¦NB¦STB¦T¦ Steel Beam Installation [35 nos] at L1 Zone 2.4 [NCIS] | 35nos | 2026-09-15 | 2026-09-23 | 8 | NotStart
L1 | 2.4-T | MBR | P1_CN_14580 | CON¦NB¦MBR¦T¦ Main Beam RC [6 nos] at L1 Zone 2.4 [NCIS] | 6nos | 2026-09-24 | 2026-10-02 | 8 | NotStart
L1 | 2.4-T | CRW | P1_CN_14540 | CON¦NB¦CRW¦T¦ Core Wall / Staircase [Starter + Jumps + Casting + Curing] [1 nos-CW5] at L1 Zone 2.4 [NCIS] | 1nos | 2026-11-10 | 2026-12-09 | 29 | NotStart
L1 | 2.6CIS | SLB | P1_CN_14670 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [956 m²] + Beam RC [4 nos] at L1 Zone 2.6 [CIS] | 956m²+4nos | 2026-07-03 | 2026-08-07 | 35 | NotStart
L1 | 2.6CIS | COL | P1_CN_14680 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-1C53 + 3 nos] at L1 Zone 2.6 [CIS] | 4nos | 2026-08-10 | 2026-08-18 | 8 | NotStart
L1 | 2.6CIS | WAL | P1_CN_14700 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-20/21,22/23,CW8] at L1 Zone 2.6 [CIS] | 2nos | 2026-08-10 | 2026-09-18 | 39 | NotStart
L1 | 2.6CIS | COL | P1_CN_14690 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [4 nos] at L1 Zone 2.6 [CIS] | 4nos | 2026-08-19 | 2026-08-21 | 2 | NotStart
L1 | 2.6CIS | STB | P1_CN_14710 | CON¦NB¦STB¦NT¦ Steel Beam Installation [7 nos] at L1 Zone 2.6 [CIS] | 7nos | 2026-08-24 | 2026-09-01 | 8 | NotStart
L1 | 2.6CIS | MBR | P1_CN_14720 | CON¦NB¦MBR¦NT¦ Main Beam RC [5 nos] at L1 Zone 2.6 [CIS] | 5nos | 2026-09-02 | 2026-09-10 | 8 | NotStart
L1 | 2.6CIS-T | SLB | P1_CN_14600 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [850 m²] + Beam RC [9 nos] at L1 Zone 2.6 [CIS] | 850m²+9nos | 2026-05-05 | 2026-07-02 | 58 | NotStart
L1 | 2.6CIS-T | COL | P1_CN_14620 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-WF-B2C59,58,63,66] at L1 Zone 2.6 [CIS] | 4nos | 2026-07-03 | 2026-07-22 | 19 | NotStart
L1 | 2.6CIS-T | CRW | P1_CN_14610 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2A] at L1 Zone 2.6 [CIS] | 1nos | 2026-07-03 | 2026-09-03 | 62 | NotStart
L1 | 2.6CIS-T | WAL | P1_CN_14640 | CON¦NB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-03/3B] at L1 Zone 2.6 [CIS] | 1nos | 2026-07-03 | 2026-08-13 | 41 | NotStart
L1 | 2.6CIS-T | COL | P1_CN_14630 | CON¦NB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [4 nos] at L1 Zone 2.6 [CIS] | 4nos | 2026-07-23 | 2026-07-27 | 4 | NotStart
L1 | 2.6CIS-T | STB | P1_CN_14650 | CON¦NB¦STB¦T¦ Steel Beam Installation [16 nos] at L1 Zone 2.6 [CIS] | 16nos | 2026-07-28 | 2026-08-05 | 8 | NotStart
L1 | 2.6CIS-T | MBR | P1_CN_14660 | CON¦NB¦MBR¦T¦ Main Beam RC [13 nos] at L1 Zone 2.6 [CIS] | 13nos | 2026-08-06 | 2026-08-14 | 8 | NotStart
L2 | 2.1 | CRW | P1_CN_14780 | CON¦NB¦CRW¦NT¦ Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone 2.1 [NCIS] | — | 2026-07-07 | 2026-08-17 | 41 | NotStart
L2 | 2.1 | COL | P1_CN_14790 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-B2C46] at L2 Zone 2.1 [NCIS] | 1nos | 2026-08-27 | 2026-09-04 | 8 | NotStart
L2 | 2.1 | COL | P1_CN_14800 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [1 nos] at L2 Zone 2.1 [NCIS] | 1nos | 2026-09-07 | 2026-09-09 | 2 | NotStart
L2 | 2.1 | STB | P1_CN_14810 | CON¦NB¦STB¦NT¦ Steel Beam Installation at L2 Zone 2.1 [NCIS] | — | 2026-09-10 | 2026-09-14 | 4 | NotStart
L2 | 2.1 | MBR | P1_CN_14820 | CON¦NB¦MBR¦NT¦ Main Beam RC [3 nos] at L2 Zone 2.1 [NCIS] | 3nos | 2026-09-15 | 2026-09-23 | 8 | NotStart
L2 | 2.1-T | CRW | P1_CN_14730 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW3A/ST-02,02A] at L2 Zone 2.1 [NCIS] | 1nos | 2026-08-06 | 2026-09-16 | 41 | NotStart
L2 | 2.1-T | COL | P1_CN_14740 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C39,40,44] at L2 Zone 2.1 [NCIS] | 3nos | 2026-08-15 | 2026-08-21 | 6 | NotStart
L2 | 2.1-T | COL | P1_CN_14750 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [3 nos] at L2 Zone 2.1 [NCIS] | 3nos | 2026-08-24 | 2026-08-26 | 2 | NotStart
L2 | 2.1-T | STB | P1_CN_14760 | CON¦NB¦STB¦T¦ Steel Beam Installation at L2 Zone 2.1 [NCIS] | — | 2026-08-27 | 2026-09-14 | 18 | NotStart
L2 | 2.1-T | MBR | P1_CN_14770 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L2 Zone 2.1 [NCIS] | 7nos | 2026-09-17 | 2026-09-25 | 8 | NotStart
L2 | 2.1CIS | SLB | P1_CN_14890 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [559 m²] at L2 Zone 2.1 [CIS] | 559m² | 2026-07-29 | 2026-08-27 | 29 | NotStart
L2 | 2.1CIS | COL | P1_CN_14900 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-1C104 + 5 nos] at L2 Zone 2.1 [CIS] | 6nos | 2026-08-28 | 2026-09-07 | 10 | NotStart
L2 | 2.1CIS | WAL | P1_CN_14920 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-24/25,ST-26/27] at L2 Zone 2.1 [CIS] | 2nos | 2026-08-28 | 2026-09-26 | 29 | NotStart
L2 | 2.1CIS | COL | P1_CN_14910 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L2 Zone 2.1 [CIS] | 6nos | 2026-09-08 | 2026-09-10 | 2 | NotStart
L2 | 2.1CIS | STB | P1_CN_14930 | CON¦NB¦STB¦NT¦ Steel Beam Installation [38 nos] at L2 Zone 2.1 [CIS] | 38nos | 2026-09-11 | 2026-09-26 | 15 | NotStart
L2 | 2.1CIS | MBR | P1_CN_14940 | CON¦NB¦MBR¦NT¦ Main Beam RC [15 nos] at L2 Zone 2.1 [CIS] | 15nos | 2026-09-28 | 2026-10-06 | 8 | NotStart
L2 | 2.1CIS-T | SLB | P1_CN_14830 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [159 m²] at L2 Zone 2.1 [CIS] | 159m² | 2026-09-05 | 2026-09-18 | 13 | NotStart
L2 | 2.1CIS-T | COL | P1_CN_14840 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C45,54] at L2 Zone 2.1 [CIS] | 2nos | 2026-09-21 | 2026-09-29 | 8 | NotStart
L2 | 2.1CIS-T | COL | P1_CN_14850 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L2 Zone 2.1 [CIS] | 2nos | 2026-09-30 | 2026-10-02 | 2 | NotStart
L2 | 2.1CIS-T | STB | P1_CN_14860 | CON¦NB¦STB¦T¦ Steel Beam Installation at L2 Zone 2.1 [CIS] | — | 2026-10-05 | 2026-10-05 | 0 | NotStart
L2 | 2.1CIS-T | MBR | P1_CN_14870 | CON¦NB¦MBR¦T¦ Main Beam RC [4 nos] at L2 Zone 2.1 [CIS] | 4nos | 2026-10-06 | 2026-10-14 | 8 | NotStart
L2 | 2.2 | COL | P1_CN_15000 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-WF-B2C18,19,20,26] at L2 Zone 2.2 [NCIS] | 4nos | 2026-11-13 | 2026-11-23 | 10 | NotStart
L2 | 2.2 | COL | P1_CN_15010 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [4 nos] at L2 Zone 2.2 [NCIS] | 4nos | 2026-11-24 | 2026-11-26 | 2 | NotStart
L2 | 2.2 | STB | P1_CN_15020 | CON¦NB¦STB¦NT¦ Steel Beam Installation [26 nos] at L2 Zone 2.2 [NCIS] | 26nos | 2026-11-27 | 2026-12-01 | 4 | NotStart
L2 | 2.2 | MBR | P1_CN_15030 | CON¦NB¦MBR¦NT¦ Main Beam RC [12 nos] at L2 Zone 2.2 [NCIS] | 12nos | 2026-12-02 | 2026-12-10 | 8 | NotStart
L2 | 2.2-T | CRW | P1_CN_14970 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW4/ST-44/49] at L2 Zone 2.2 [NCIS] | 1nos | 2026-10-16 | 2026-11-26 | 41 | NotStart
L2 | 2.2-T | COL | P1_CN_14950 | CON¦NB¦COL¦T¦ Columns Work [9 nos-WF-B2C24,25,31,33,34,35,36,27,WF-1C17A] at L2 Zone 2.2 [NCIS] | 9nos | 2026-10-21 | 2026-11-09 | 19 | NotStart
L2 | 2.2-T | COL | P1_CN_14960 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [9 nos] at L2 Zone 2.2 [NCIS] | 9nos | 2026-11-10 | 2026-11-12 | 2 | NotStart
L2 | 2.2-T | STB | P1_CN_14980 | CON¦NB¦STB¦T¦ Steel Beam Installation [66 nos] at L2 Zone 2.2 [NCIS] | 66nos | 2026-11-13 | 2026-12-01 | 18 | NotStart
L2 | 2.2-T | MBR | P1_CN_14990 | CON¦NB¦MBR¦T¦ Main Beam RC [10 nos] at L2 Zone 2.2 [NCIS] | 10nos | 2026-12-02 | 2026-12-10 | 8 | NotStart
L2 | 2.3-T | COL | P1_CN_15040 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [5 nos-WF-B2C41,42,43,48,49] at L2 Zone 2.3 [NCIS] | 5nos | 2026-06-08 | 2026-06-16 | 8 | NotStart
L2 | 2.3-T | COL | P1_CN_15050 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [5 nos] at L2 Zone 2.3 [NCIS] | 5nos | 2026-06-17 | 2026-06-19 | 2 | NotStart
L2 | 2.3-T | STB | P1_CN_15060 | CON¦NB¦STB¦T¦ Steel Beam Installation [51 nos] at L2 Zone 2.3 [NCIS] | 51nos | 2026-06-22 | 2026-06-30 | 8 | NotStart
L2 | 2.3-T | MBR | P1_CN_15070 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L2 Zone 2.3 [NCIS] | 7nos | 2026-07-01 | 2026-07-09 | 8 | NotStart
L2 | 2.3CIS-T | SLB | P1_CN_15080 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [501 m²] at L2 Zone 2.3 [CIS] | 501m² | 2026-07-22 | 2026-08-20 | 29 | NotStart
L2 | 2.3CIS-T | COL | P1_CN_15100 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C50,58,59] at L2 Zone 2.3 [CIS] | 3nos | 2026-08-21 | 2026-08-31 | 10 | NotStart
L2 | 2.3CIS-T | CRW | P1_CN_15090 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2B] at L2 Zone 2.3 [CIS] | 1nos | 2026-08-21 | 2026-10-01 | 41 | NotStart
L2 | 2.3CIS-T | COL | P1_CN_15110 | CON¦NB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L2 Zone 2.3 [CIS] | 3nos | 2026-09-01 | 2026-09-03 | 2 | NotStart
L2 | 2.3CIS-T | STB | P1_CN_15120 | CON¦NB¦STB¦T¦ Steel Beam Installation [26 nos] at L2 Zone 2.3 [CIS] | 26nos | 2026-09-04 | 2026-10-01 | 27 | NotStart
L2 | 2.3CIS-T | MBR | P1_CN_15130 | CON¦NB¦MBR¦T¦ Main Beam RC [12 nos] at L2 Zone 2.3 [CIS] | 12nos | 2026-10-02 | 2026-10-12 | 10 | NotStart
L2 | 2.4 | SLB | P1_CN_15190 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [521 m²] at L2 Zone 2.4 [NCIS] | 521m² | 2027-01-19 | 2027-02-16 | 28 | NotStart
L2 | 2.4 | MBR | P1_CN_15200 | CON¦NB¦MBR¦NT¦ Main Beam RC [6 nos] at L2 Zone 2.4 [NCIS] | 6nos | 2027-02-17 | 2027-02-25 | 8 | NotStart
L2 | 2.4-T | COL | P1_CN_15150 | CON¦NB¦COL¦T¦ Columns Work [6 nos-WF-B2C32,37,38,29,30,WF-1C21A] at L2 Zone 2.4 [NCIS] | 6nos | 2026-10-05 | 2026-10-13 | 8 | NotStart
L2 | 2.4-T | COL | P1_CN_15160 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L2 Zone 2.4 [NCIS] | 6nos | 2026-10-14 | 2026-10-16 | 2 | NotStart
L2 | 2.4-T | STB | P1_CN_15170 | CON¦NB¦STB¦T¦ Steel Beam Installation [35 nos] at L2 Zone 2.4 [NCIS] | 35nos | 2026-10-19 | 2026-10-27 | 8 | NotStart
L2 | 2.4-T | MBR | P1_CN_15180 | CON¦NB¦MBR¦T¦ Main Beam RC [6 nos] at L2 Zone 2.4 [NCIS] | 6nos | 2026-10-28 | 2026-11-05 | 8 | NotStart
L2 | 2.4-T | CRW | P1_CN_15140 | CON¦NB¦CRW¦T¦ Core Wall / Staircase [Starter + Jumps + Casting + Curing] [1 nos] at L2 Zone 2.4 [NCIS] | 1nos | 2026-12-11 | 2027-01-09 | 29 | NotStart
L2 | 2.6CIS | SLB | P1_CN_15280 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [476 m²] at L2 Zone 2.6 [CIS] | 476m² | 2026-09-21 | 2026-10-30 | 39 | NotStart
L2 | 2.6CIS | COL | P1_CN_15290 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C67,69] at L2 Zone 2.6 [CIS] | 2nos | 2026-09-29 | 2026-10-07 | 8 | NotStart
L2 | 2.6CIS | COL | P1_CN_15300 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L2 Zone 2.6 [CIS] | 2nos | 2026-10-08 | 2026-10-12 | 4 | NotStart
L2 | 2.6CIS | STB | P1_CN_15320 | CON¦NB¦STB¦NT¦ Steel Beam Installation [7 nos] at L2 Zone 2.6 [CIS] | 7nos | 2026-10-13 | 2026-10-21 | 8 | NotStart
L2 | 2.6CIS | MBR | P1_CN_15330 | CON¦NB¦MBR¦NT¦ Main Beam RC [5 nos] at L2 Zone 2.6 [CIS] | 5nos | 2026-10-22 | 2026-10-30 | 8 | NotStart
L2 | 2.6CIS | WAL | P1_CN_15310 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-20/21,22/23,CW8] at L2 Zone 2.6 [CIS] | 2nos | 2026-11-02 | 2026-12-11 | 39 | NotStart
L2 | 2.6CIS-T | SLB | P1_CN_15210 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [794 m²] at L2 Zone 2.6 [CIS] | 794m² | 2026-08-17 | 2026-09-03 | 17 | NotStart
L2 | 2.6CIS-T | COL | P1_CN_15230 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C63,66] at L2 Zone 2.6 [CIS] | 2nos | 2026-09-04 | 2026-09-23 | 19 | NotStart
L2 | 2.6CIS-T | CRW | P1_CN_15220 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2A] at L2 Zone 2.6 [CIS] | 1nos | 2026-09-04 | 2026-10-15 | 41 | NotStart
L2 | 2.6CIS-T | WAL | P1_CN_15250 | CON¦NB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-03] at L2 Zone 2.6 [CIS] | 1nos | 2026-09-04 | 2026-10-15 | 41 | NotStart
L2 | 2.6CIS-T | COL | P1_CN_15240 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L2 Zone 2.6 [CIS] | 2nos | 2026-09-24 | 2026-09-28 | 4 | NotStart
L2 | 2.6CIS-T | STB | P1_CN_15260 | CON¦NB¦STB¦T¦ Steel Beam Installation [16 nos] at L2 Zone 2.6 [CIS] | 16nos | 2026-09-29 | 2026-10-07 | 8 | NotStart
L2 | 2.6CIS-T | MBR | P1_CN_15270 | CON¦NB¦MBR¦T¦ Main Beam RC [13 nos] at L2 Zone 2.6 [CIS] | 13nos | 2026-10-08 | 2026-10-16 | 8 | NotStart
L3 | 2.1 | CRW | P1_CN_15390 | CON¦NB¦CRW¦NT¦ Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone 2.1 [NCIS] | — | 2026-08-18 | 2026-09-28 | 41 | NotStart
L3 | 2.1 | COL | P1_CN_15400 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-B2C46] at L3 Zone 2.1 [NCIS] | 1nos | 2026-10-12 | 2026-10-20 | 8 | NotStart
L3 | 2.1 | COL | P1_CN_15410 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [1 nos] at L3 Zone 2.1 [NCIS] | 1nos | 2026-10-21 | 2026-10-23 | 2 | NotStart
L3 | 2.1 | STB | P1_CN_15420 | CON¦NB¦STB¦NT¦ Steel Beam Installation at L3 Zone 2.1 [NCIS] | — | 2026-10-26 | 2026-10-28 | 2 | NotStart
L3 | 2.1 | MBR | P1_CN_15430 | CON¦NB¦MBR¦NT¦ Main Beam RC [3 nos] at L3 Zone 2.1 [NCIS] | 3nos | 2026-10-29 | 2026-11-06 | 8 | NotStart
L3 | 2.1-T | CRW | P1_CN_15340 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW3A/ST-02,02A] at L3 Zone 2.1 [NCIS] | 1nos | 2026-09-17 | 2026-10-28 | 41 | NotStart
L3 | 2.1-T | COL | P1_CN_15350 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C39,40,44] at L3 Zone 2.1 [NCIS] | 3nos | 2026-09-28 | 2026-10-06 | 8 | NotStart
L3 | 2.1-T | COL | P1_CN_15360 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [3 nos] at L3 Zone 2.1 [NCIS] | 3nos | 2026-10-07 | 2026-10-09 | 2 | NotStart
L3 | 2.1-T | STB | P1_CN_15370 | CON¦NB¦STB¦T¦ Steel Beam Installation at L3 Zone 2.1 [NCIS] | — | 2026-10-12 | 2026-10-28 | 16 | NotStart
L3 | 2.1-T | MBR | P1_CN_15380 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L3 Zone 2.1 [NCIS] | 7nos | 2026-10-29 | 2026-11-06 | 8 | NotStart
L3 | 2.1CIS | SLB | P1_CN_15490 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [560 m²] at L3 Zone 2.1 [CIS] | 560m² | 2026-10-07 | 2026-11-05 | 29 | NotStart
L3 | 2.1CIS | WAL | P1_CN_15520 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-24/25,ST-26/27] at L3 Zone 2.1 [CIS] | 2nos | 2026-11-06 | 2026-12-17 | 41 | NotStart
L3 | 2.1CIS | COL | P1_CN_15500 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-1C104 + 5 nos] at L3 Zone 2.1 [CIS] | 6nos | 2026-11-30 | 2026-12-08 | 8 | NotStart
L3 | 2.1CIS | COL | P1_CN_15510 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L3 Zone 2.1 [CIS] | 6nos | 2026-12-09 | 2026-12-11 | 2 | NotStart
L3 | 2.1CIS | STB | P1_CN_15530 | CCON¦NB¦STB¦NT¦ Steel Beam Installation [38 nos] at L3 Zone 2.1 [CIS] | 38nos | 2026-12-14 | 2027-01-08 | 25 | NotStart
L3 | 2.1CIS | MBR | P1_CN_15540 | CON¦NB¦MBR¦NT¦ Main Beam RC [15 nos] at L3 Zone 2.1 [CIS] | 15nos | 2027-01-11 | 2027-01-19 | 8 | NotStart
L3 | 2.1CIS-T | SLB | P1_CN_15440 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [159 m²] at L3 Zone 2.1 [CIS] | 159m² | 2026-10-15 | 2026-11-13 | 29 | NotStart
L3 | 2.1CIS-T | COL | P1_CN_15450 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C45,54] at L3 Zone 2.1 [CIS] | 2nos | 2026-11-16 | 2026-11-24 | 8 | NotStart
L3 | 2.1CIS-T | COL | P1_CN_15460 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L3 Zone 2.1 [CIS] | 2nos | 2026-11-25 | 2026-11-27 | 2 | NotStart
L3 | 2.1CIS-T | STB | P1_CN_15470 | CON¦NB¦STB¦T¦ Steel Beam Installation at L3 Zone 2.1 [CIS] | — | 2026-11-30 | 2026-11-30 | 0 | NotStart
L3 | 2.1CIS-T | MBR | P1_CN_15480 | CON¦NB¦MBR¦T¦ Main Beam RC [4 nos] at L3 Zone 2.1 [CIS] | 4nos | 2026-12-01 | 2026-12-09 | 8 | NotStart
L3 | 2.2 | COL | P1_CN_15600 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-WF-B2C18,19,20,26] at L3 Zone 2.2 [NCIS] | 4nos | 2027-01-05 | 2027-01-13 | 8 | NotStart
L3 | 2.2 | COL | P1_CN_15610 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [4 nos] at L3 Zone 2.2 [NCIS] | 4nos | 2027-01-14 | 2027-01-18 | 4 | NotStart
L3 | 2.2 | STB | P1_CN_15620 | CON¦NB¦STB¦NT¦ Steel Beam Installation [26 nos] at L3 Zone 2.2 [NCIS] | 26nos | 2027-01-19 | 2027-01-21 | 2 | NotStart
L3 | 2.2 | MBR | P1_CN_15630 | CON¦NB¦MBR¦NT¦ Main Beam RC [12 nos] at L3 Zone 2.2 [NCIS] | 12nos | 2027-01-22 | 2027-02-01 | 10 | NotStart
L3 | 2.2-T | CRW | P1_CN_15570 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW4/ST-44/49] at L3 Zone 2.2 [NCIS] | 1nos | 2026-11-27 | 2027-01-07 | 41 | NotStart
L3 | 2.2-T | COL | P1_CN_15550 | CON¦NB¦COL¦T¦ Columns Work [9 nos-WF-B2C24,25,31,33,34,35,36,27,WF-1C17A] at L3 Zone 2.2 [NCIS] | 9nos | 2026-12-11 | 2026-12-30 | 19 | NotStart
L3 | 2.2-T | COL | P1_CN_15560 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [9 nos] at L3 Zone 2.2 [NCIS] | 9nos | 2026-12-31 | 2027-01-04 | 4 | NotStart
L3 | 2.2-T | STB | P1_CN_15580 | CON¦NB¦STB¦T¦ Steel Beam Installation [66 nos] at L3 Zone 2.2 [NCIS] | 66nos | 2027-01-05 | 2027-01-12 | 7 | NotStart
L3 | 2.2-T | MBR | P1_CN_15590 | CON¦NB¦MBR¦T¦ Main Beam RC [10 nos] at L3 Zone 2.2 [NCIS] | 10nos | 2027-01-13 | 2027-01-21 | 8 | NotStart
L3 | 2.3-T | COL | P1_CN_15640 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [5 nos-WF-B2C41,42,43,48,49] at L3 Zone 2.3 [NCIS] | 5nos | 2026-09-04 | 2026-09-14 | 10 | NotStart
L3 | 2.3-T | COL | P1_CN_15650 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [5 nos] at L3 Zone 2.3 [NCIS] | 5nos | 2026-09-15 | 2026-09-17 | 2 | NotStart
L3 | 2.3-T | STB | P1_CN_15660 | CON¦NB¦STB¦T¦ Steel Beam Installation [51 nos] at L3 Zone 2.3 [NCIS] | 51nos | 2026-09-18 | 2026-09-28 | 10 | NotStart
L3 | 2.3-T | MBR | P1_CN_15670 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L3 Zone 2.3 [NCIS] | 7nos | 2026-09-29 | 2026-10-07 | 8 | NotStart
L3 | 2.3CIS-T | SLB | P1_CN_15680 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [501 m²] at L3 Zone 2.3 [CIS] | 501m² | 2026-10-02 | 2026-11-02 | 31 | NotStart
L3 | 2.3CIS-T | COL | P1_CN_15700 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C50,58,59] at L3 Zone 2.3 [CIS] | 3nos | 2026-11-03 | 2026-11-11 | 8 | NotStart
L3 | 2.3CIS-T | CRW | P1_CN_15690 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2B] at L3 Zone 2.3 [CIS] | 1nos | 2026-11-03 | 2026-12-14 | 41 | NotStart
L3 | 2.3CIS-T | COL | P1_CN_15710 | CON¦NB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L3 Zone 2.3 [CIS] | 3nos | 2026-11-12 | 2026-11-16 | 4 | NotStart
L3 | 2.3CIS-T | STB | P1_CN_15720 | CON¦NB¦STB¦T¦ Steel Beam Installation [26 nos] at L3 Zone 2.3 [CIS] | 26nos | 2026-11-17 | 2026-12-14 | 27 | NotStart
L3 | 2.3CIS-T | MBR | P1_CN_15730 | CON¦NB¦MBR¦T¦ Main Beam RC [12 nos] at L3 Zone 2.3 [CIS] | 12nos | 2026-12-15 | 2026-12-23 | 8 | NotStart
L3 | 2.4 | SLB | P1_CN_15790 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [521 m²] at L3 Zone 2.4 [NCIS] | 521m² | 2027-02-26 | 2027-03-26 | 28 | NotStart
L3 | 2.4 | MBR | P1_CN_15800 | CON¦NB¦MBR¦NT¦ Main Beam RC [6 nos] at L3 Zone 2.4 [NCIS] | 6nos | 2027-03-29 | 2027-04-06 | 8 | NotStart
L3 | 2.4-T | COL | P1_CN_15750 | CON¦NB¦COL¦T¦ Columns Work [6 nos-WF-B2C32,37,38,29,30,WF-1C21A] at L3 Zone 2.4 [NCIS] | 6nos | 2026-11-06 | 2026-11-16 | 10 | NotStart
L3 | 2.4-T | COL | P1_CN_15760 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L3 Zone 2.4 [NCIS] | 6nos | 2026-11-17 | 2026-11-19 | 2 | NotStart
L3 | 2.4-T | STB | P1_CN_15770 | CON¦NB¦STB¦T¦ Steel Beam Installation [35 nos] at L3 Zone 2.4 [NCIS] | 35nos | 2026-11-20 | 2026-11-30 | 10 | NotStart
L3 | 2.4-T | MBR | P1_CN_15780 | CON¦NB¦MBR¦T¦ Main Beam RC [6 nos] at L3 Zone 2.4 [NCIS] | 6nos | 2026-12-01 | 2026-12-09 | 8 | NotStart
L3 | 2.4-T | CRW | P1_CN_15740 | CON¦NB¦CRW¦T¦ Core Wall / Staircase [Starter + Jumps + Casting + Curing] [1 nos] at L3 Zone 2.4 [NCIS] | 1nos | 2027-01-10 | 2027-02-08 | 29 | NotStart
L3 | 2.6CIS | SLB | P1_CN_15880 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [476 m²] at L3 Zone 2.6 [CIS] | 476m² | 2026-12-14 | 2026-12-31 | 17 | NotStart
L3 | 2.6CIS | COL | P1_CN_15890 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C67,69] at L3 Zone 2.6 [CIS] | 2nos | 2027-01-01 | 2027-01-11 | 10 | NotStart
L3 | 2.6CIS | WAL | P1_CN_15910 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-20/21,22/23,CW8] at L3 Zone 2.6 [CIS] | 2nos | 2027-01-01 | 2027-02-11 | 41 | NotStart
L3 | 2.6CIS | COL | P1_CN_15900 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L3 Zone 2.6 [CIS] | 2nos | 2027-01-12 | 2027-01-14 | 2 | NotStart
L3 | 2.6CIS | STB | P1_CN_15920 | CON¦NB¦STB¦NT¦ Steel Beam Installation [7 nos] at L3 Zone 2.6 [CIS] | 7nos | 2027-01-15 | 2027-01-25 | 10 | NotStart
L3 | 2.6CIS | MBR | P1_CN_15930 | CON¦NB¦MBR¦NT¦ Main Beam RC [5 nos] at L3 Zone 2.6 [CIS] | 5nos | 2027-01-26 | 2027-02-03 | 8 | NotStart
L3 | 2.6CIS-T | SLB | P1_CN_15810 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [794 m²] at L3 Zone 2.6 [CIS] | 794m² | 2026-10-19 | 2026-11-05 | 17 | NotStart
L3 | 2.6CIS-T | COL | P1_CN_15830 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C63,66] at L3 Zone 2.6 [CIS] | 2nos | 2026-11-06 | 2026-11-25 | 19 | NotStart
L3 | 2.6CIS-T | CRW | P1_CN_15820 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2A] at L3 Zone 2.6 [CIS] | 1nos | 2026-11-06 | 2026-12-17 | 41 | NotStart
L3 | 2.6CIS-T | WAL | P1_CN_15850 | CON¦NB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-03] at L3 Zone 2.6 [CIS] | 1nos | 2026-11-06 | 2026-12-17 | 41 | NotStart
L3 | 2.6CIS-T | COL | P1_CN_15840 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L3 Zone 2.6 [CIS] | 2nos | 2026-11-26 | 2026-11-30 | 4 | NotStart
L3 | 2.6CIS-T | STB | P1_CN_15860 | CON¦NB¦STB¦T¦ Steel Beam Installation [16 nos] at L3 Zone 2.6 [CIS] | 16nos | 2026-12-01 | 2026-12-09 | 8 | NotStart
L3 | 2.6CIS-T | MBR | P1_CN_15870 | CON¦NB¦MBR¦T¦ Main Beam RC [13 nos] at L3 Zone 2.6 [CIS] | 13nos | 2026-12-10 | 2026-12-18 | 8 | NotStart
L4 | 2.1 | CRW | P1_CN_16010 | CON¦NB¦CRW¦NT¦ Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone 2.1 [NCIS] | — | 2026-09-29 | 2026-11-09 | 41 | NotStart
L4 | 2.1 | SLB | P1_CN_16000 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [666 m²] at L4 Zone 2.1 [NCIS] | 666m² | 2026-11-09 | 2026-12-07 | 28 | NotStart
L4 | 2.1 | COL | P1_CN_16020 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-B2C46] at L4 Zone 2.1 [NCIS] | 1nos | 2026-12-28 | 2027-01-05 | 8 | NotStart
L4 | 2.1 | COL | P1_CN_16030 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [1 nos] at L4 Zone 2.1 [NCIS] | 1nos | 2027-01-06 | 2027-01-08 | 2 | NotStart
L4 | 2.1 | STB | P1_CN_16040 | CON¦NB¦STB¦NT¦ Steel Beam Installation at L4 Zone 2.1 [NCIS] | — | 2027-01-11 | 2027-01-13 | 2 | NotStart
L4 | 2.1 | MBR | P1_CN_16050 | CON¦NB¦MBR¦NT¦ Main Beam RC [3 nos] at L4 Zone 2.1 [NCIS] | 3nos | 2027-01-14 | 2027-01-22 | 8 | NotStart
L4 | 2.1-T | CRW | P1_CN_15950 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW3A/ST-02,02A] at L4 Zone 2.1 [NCIS] | 1nos | 2026-10-29 | 2026-12-09 | 41 | NotStart
L4 | 2.1-T | SLB | P1_CN_15940 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [503 m²] at L4 Zone 2.1 [NCIS] | 503m² | 2026-11-09 | 2026-12-07 | 28 | NotStart
L4 | 2.1-T | COL | P1_CN_15960 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C39,40,44] at L4 Zone 2.1 [NCIS] | 3nos | 2026-12-14 | 2026-12-22 | 8 | NotStart
L4 | 2.1-T | COL | P1_CN_15970 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [3 nos] at L4 Zone 2.1 [NCIS] | 3nos | 2026-12-23 | 2026-12-25 | 2 | NotStart
L4 | 2.1-T | STB | P1_CN_15980 | CON¦NB¦STB¦T¦ Steel Beam Installation at L4 Zone 2.1 [NCIS] | — | 2026-12-28 | 2026-12-31 | 3 | NotStart
L4 | 2.1-T | MBR | P1_CN_15990 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L4 Zone 2.1 [NCIS] | 7nos | 2027-01-01 | 2027-01-11 | 10 | NotStart
L4 | 2.1CIS | SLB | P1_CN_16110 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [560 m²] at L4 Zone 2.1 [CIS] | 560m² | 2027-01-20 | 2027-02-18 | 29 | NotStart
L4 | 2.1CIS | COL | P1_CN_16120 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [1 nos-WF-1C104 + 5 nos] at L4 Zone 2.1 [CIS] | 6nos | 2027-02-19 | 2027-03-01 | 10 | NotStart
L4 | 2.1CIS | WAL | P1_CN_16140 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-24/25,ST-26/27] at L4 Zone 2.1 [CIS] | 2nos | 2027-02-19 | 2027-04-01 | 41 | NotStart
L4 | 2.1CIS | COL | P1_CN_16130 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L4 Zone 2.1 [CIS] | 6nos | 2027-03-02 | 2027-03-04 | 2 | NotStart
L4 | 2.1CIS | STB | P1_CN_16150 | CON¦NB¦STB¦NT¦ Steel Beam Installation [38 nos] at L4 Zone 2.1 [CIS] | 38nos | 2027-03-05 | 2027-04-01 | 27 | NotStart
L4 | 2.1CIS | MBR | P1_CN_16160 | CON¦NB¦MBR¦NT¦ Main Beam RC [15 nos] at L4 Zone 2.1 [CIS] | 15nos | 2027-04-02 | 2027-04-09 | 7 | NotStart
L4 | 2.1CIS-T | SLB | P1_CN_16060 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [159 m²] at L4 Zone 2.1 [CIS] | 159m² | 2026-12-10 | 2027-01-20 | 41 | NotStart
L4 | 2.1CIS-T | COL | P1_CN_16070 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C45,54] at L4 Zone 2.1 [CIS] | 2nos | 2027-01-21 | 2027-01-29 | 8 | NotStart
L4 | 2.1CIS-T | COL | P1_CN_16080 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L4 Zone 2.1 [CIS] | 2nos | 2027-02-01 | 2027-02-03 | 2 | NotStart
L4 | 2.1CIS-T | STB | P1_CN_16090 | CON¦NB¦STB¦T¦ Steel Beam Installation at L4 Zone 2.1 [CIS] | — | 2027-02-04 | 2027-02-05 | 1 | NotStart
L4 | 2.1CIS-T | MBR | P1_CN_16100 | CON¦NB¦MBR¦T¦ Main Beam RC [4 nos] at L4 Zone 2.1 [CIS] | 4nos | 2027-02-08 | 2027-02-16 | 8 | NotStart
L4 | 2.2 | COL | P1_CN_16230 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [4 nos-WF-B2C18,19,20,26] at L4 Zone 2.2 [NCIS] | 4nos | 2027-02-16 | 2027-02-24 | 8 | NotStart
L4 | 2.2 | COL | P1_CN_16240 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [4 nos] at L4 Zone 2.2 [NCIS] | 4nos | 2027-02-25 | 2027-03-01 | 4 | NotStart
L4 | 2.2 | STB | P1_CN_16250 | CON¦NB¦STB¦NT¦ Steel Beam Installation [26 nos] at L4 Zone 2.2 [NCIS] | 26nos | 2027-03-02 | 2027-03-04 | 2 | NotStart
L4 | 2.2 | MBR | P1_CN_16260 | CON¦NB¦MBR¦NT¦ Main Beam RC [12 nos] at L4 Zone 2.2 [NCIS] | 12nos | 2027-03-05 | 2027-03-15 | 10 | NotStart
L4 | 2.2-T | COL | P1_CN_16180 | CON¦NB¦COL¦T¦ Columns Work [9 nos-WF-B2C24,25,31,33,34,35,36,27,WF-1C17A] at L4 Zone 2.2 [NCIS] | 9nos | 2027-01-22 | 2027-02-10 | 19 | NotStart
L4 | 2.2-T | SLB | P1_CN_16170 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1412 m²] at L4 Zone 2.2 [NCIS] | 1412m² | 2027-01-22 | 2027-02-19 | 28 | NotStart
L4 | 2.2-T | WAL | P1_CN_16200 | CON¦NB¦WAL¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW4/ST-44/49] at L4 Zone 2.2 [CIS] | 1nos | 2027-01-22 | 2027-03-04 | 41 | NotStart
L4 | 2.2-T | COL | P1_CN_16190 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [9 nos] at L4 Zone 2.2 [NCIS] | 9nos | 2027-02-11 | 2027-02-15 | 4 | NotStart
L4 | 2.2-T | STB | P1_CN_16210 | CON¦NB¦STB¦T¦ Steel Beam Installation [66 nos] at L4 Zone 2.2 [NCIS] | 66nos | 2027-02-16 | 2027-03-04 | 16 | NotStart
L4 | 2.2-T | MBR | P1_CN_16220 | CON¦NB¦MBR¦T¦ Main Beam RC [10 nos] at L4 Zone 2.2 [NCIS] | 10nos | 2027-03-05 | 2027-03-15 | 10 | NotStart
L4 | 2.3-T | SLB | P1_CN_16270 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1173 m²] at L4 Zone 2.3 [NCIS] | 1173m² | 2026-10-08 | 2026-11-06 | 29 | NotStart
L4 | 2.3-T | COL | P1_CN_16280 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [5 nos-WF-B2C41,42,43,48,49] at L4 Zone 2.3 [NCIS] | 5nos | 2026-11-17 | 2026-11-25 | 8 | NotStart
L4 | 2.3-T | COL | P1_CN_16290 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [5 nos] at L4 Zone 2.3 [NCIS] | 5nos | 2026-11-26 | 2026-11-30 | 4 | NotStart
L4 | 2.3-T | STB | P1_CN_16300 | CON¦NB¦STB¦T¦ Steel Beam Installation [51 nos] at L4 Zone 2.3 [NCIS] | 51nos | 2026-12-01 | 2026-12-09 | 8 | NotStart
L4 | 2.3-T | MBR | P1_CN_16310 | CON¦NB¦MBR¦T¦ Main Beam RC [7 nos] at L4 Zone 2.3 [NCIS] | 7nos | 2026-12-10 | 2026-12-18 | 8 | NotStart
L4 | 2.3CIS-T | SLB | P1_CN_16320 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [501 m²] at L4 Zone 2.3 [CIS] | 501m² | 2026-12-24 | 2027-01-27 | 34 | NotStart
L4 | 2.3CIS-T | COL | P1_CN_16340 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [3 nos-WF-B2C50,58,59] at L4 Zone 2.3 [CIS] | 3nos | 2027-01-28 | 2027-02-05 | 8 | NotStart
L4 | 2.3CIS-T | CRW | P1_CN_16330 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2B] at L4 Zone 2.3 [CIS] | 1nos | 2027-01-28 | 2027-03-10 | 41 | NotStart
L4 | 2.3CIS-T | COL | P1_CN_16350 | CON¦NB¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [3 nos] at L4 Zone 2.3 [CIS] | 3nos | 2027-02-08 | 2027-02-10 | 2 | NotStart
L4 | 2.3CIS-T | STB | P1_CN_16360 | CON¦NB¦STB¦T¦ Steel Beam Installation [26 nos] at L4 Zone 2.3 [CIS] | 26nos | 2027-02-11 | 2027-03-10 | 27 | NotStart
L4 | 2.3CIS-T | MBR | P1_CN_16370 | CON¦NB¦MBR¦T¦ Main Beam RC [12 nos] at L4 Zone 2.3 [CIS] | 12nos | 2027-03-11 | 2027-03-19 | 8 | NotStart
L4 | 2.4-T | SLB | P1_CN_16380 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1221 m²] at L4 Zone 2.4 [NCIS] | 1221m² | 2026-12-10 | 2027-01-07 | 28 | NotStart
L4 | 2.4-T | COL | P1_CN_16400 | CON¦NB¦COL¦T¦ Columns Work [6 nos-WF-B2C32,37,38,29,30,WF-1C21A] at L4 Zone 2.4 [NCIS] | 6nos | 2027-01-08 | 2027-01-18 | 10 | NotStart
L4 | 2.4-T | COL | P1_CN_16410 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [6 nos] at L4 Zone 2.4 [NCIS] | 6nos | 2027-01-19 | 2027-01-21 | 2 | NotStart
L4 | 2.4-T | STB | P1_CN_16420 | CON¦NB¦STB¦T¦ Steel Beam Installation [35 nos] at L4 Zone 2.4 [NCIS] | 35nos | 2027-01-22 | 2027-02-01 | 10 | NotStart
L4 | 2.4-T | MBR | P1_CN_16430 | CON¦NB¦MBR¦T¦ Main Beam RC [6 nos] at L4 Zone 2.4 [NCIS] | 6nos | 2027-02-02 | 2027-02-10 | 8 | NotStart
L4 | 2.4-T | CRW | P1_CN_16390 | CON¦NB¦CRW¦T¦ Core Wall / Staircase [Starter + Jumps + Casting + Curing] [1 nos] at L4 Zone 2.4 [NCIS] | 1nos | 2027-02-09 | 2027-03-10 | 29 | NotStart
L4 | 2.6CIS | SLB | P1_CN_16510 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [476 m²] at L4 Zone 2.6 [CIS] | 476m² | 2027-02-12 | 2027-03-03 | 19 | NotStart
L4 | 2.6CIS | COL | P1_CN_16520 | CON¦NB¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C67,69] at L4 Zone 2.6 [CIS] | 2nos | 2027-03-04 | 2027-03-12 | 8 | NotStart
L4 | 2.6CIS | WAL | P1_CN_16540 | CON¦NB¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [2 nos-ST-20/21,22/23,CW8] at L4 Zone 2.6 [CIS] | 2nos | 2027-03-04 | 2027-04-14 | 41 | NotStart
L4 | 2.6CIS | COL | P1_CN_16530 | CON¦NB¦COL¦NT¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L4 Zone 2.6 [CIS] | 2nos | 2027-03-15 | 2027-03-17 | 2 | NotStart
L4 | 2.6CIS | STB | P1_CN_16550 | CON¦NB¦STB¦NT¦ Steel Beam Installation [7 nos] at L4 Zone 2.6 [CIS] | 7nos | 2027-03-18 | 2027-03-26 | 8 | NotStart
L4 | 2.6CIS | MBR | P1_CN_16560 | CON¦NB¦MBR¦NT¦ Main Beam RC [5 nos] at L4 Zone 2.6 [CIS] | 5nos | 2027-03-29 | 2027-04-06 | 8 | NotStart
L4 | 2.6CIS-T | SLB | P1_CN_16440 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [794 m²] at L4 Zone 2.6 [CIS] | 794m² | 2026-12-21 | 2027-01-07 | 17 | NotStart
L4 | 2.6CIS-T | COL | P1_CN_16460 | CON¦NB¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2 nos-WF-B2C63,66] at L4 Zone 2.6 [CIS] | 2nos | 2027-01-08 | 2027-01-27 | 19 | NotStart
L4 | 2.6CIS-T | CRW | P1_CN_16450 | CON¦NB¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW2A] at L4 Zone 2.6 [CIS] | 1nos | 2027-01-08 | 2027-02-18 | 41 | NotStart
L4 | 2.6CIS-T | WAL | P1_CN_16480 | CON¦NB¦WAL¦T¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-03] at L4 Zone 2.6 [CIS] | 1nos | 2027-01-08 | 2027-02-18 | 41 | NotStart
L4 | 2.6CIS-T | COL | P1_CN_16470 | CON¦NB¦COL¦T¦ Columns Work cobel [Formwork + Rebar + Casting] [2 nos] at L4 Zone 2.6 [CIS] | 2nos | 2027-01-28 | 2027-02-01 | 4 | NotStart
L4 | 2.6CIS-T | STB | P1_CN_16490 | CON¦NB¦STB¦T¦ Steel Beam Installation [16 nos] at L4 Zone 2.6 [CIS] | 16nos | 2027-02-02 | 2027-02-10 | 8 | NotStart
L4 | 2.6CIS-T | MBR | P1_CN_16500 | CON¦NB¦MBR¦T¦ Main Beam RC [13 nos] at L4 Zone 2.6 [CIS] | 13nos | 2027-02-11 | 2027-02-19 | 8 | NotStart
L5 | 2.1 | SLB | P1_CN_16600 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [351 m²] at L2 Zone 2.1 [NCIS] | 351m² | 2027-02-17 | 2027-03-17 | 28 | NotStart
L5 | 2.1 | SLB | P1_CN_16610 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [351 m²] at L3 Zone 2.1 [NCIS] | 351m² | 2027-03-18 | 2027-04-15 | 28 | NotStart
L5 | 2.1 | SLB | P1_CN_16620 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [910 m²] at L5 Zone 2.1 [NCIS] | 910m² | 2027-04-16 | 2027-05-27 | 41 | NotStart
L5 | 2.1-T | SLB | P1_CN_16570 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [503 m²] at L2 Zone 2.1 [NCIS] | 503m² | 2027-01-25 | 2027-02-22 | 28 | NotStart
L5 | 2.1-T | SLB | P1_CN_16580 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [503 m²] at L3 Zone 2.1 [NCIS] | 503m² | 2027-02-23 | 2027-03-23 | 28 | NotStart
L5 | 2.1-T | SLB | P1_CN_16590 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [662 m²] at L5 Zone 2.1 [NCIS] | 662m² | 2027-04-02 | 2027-05-21 | 49 | NotStart
L5 | 2.2 | SLB | P1_CN_16660 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [587 m²] at L5 Zone 2.2 [NCIS] | 587m² | 2027-03-16 | 2027-04-26 | 41 | NotStart
L5 | 2.2-T | SLB | P1_CN_16630 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1413 m²] at L2 Zone 2.2 [NCIS] | 1413m² | 2027-02-22 | 2027-03-22 | 28 | NotStart
L5 | 2.2-T | SLB | P1_CN_16650 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [826 m²] at L5 Zone 2.2 [NCIS] | 826m² | 2027-03-16 | 2027-05-24 | 69 | NotStart
L5 | 2.2-T | SLB | P1_CN_16640 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1413 m²] at L3 Zone 2.2 [NCIS] | 1413m² | 2027-03-23 | 2027-04-20 | 28 | NotStart
L5 | 2.3-T | SLB | P1_CN_16670 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1173 m²] at L2 Zone 2.3 [NCIS] | 1173m² | 2026-12-21 | 2027-01-19 | 29 | NotStart
L5 | 2.3-T | SLB | P1_CN_16680 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1173 m²] at L3 Zone 2.3 [NCIS] | 1173m² | 2027-01-20 | 2027-02-18 | 29 | NotStart
L5 | 2.3-T | SLB | P1_CN_16690 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1671 m²] at L5 Zone 2.3 [CIS] | 1671m² | 2027-03-22 | 2027-05-28 | 67 | NotStart
L5 | 2.4-T | SLB | P1_CN_16700 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [700 m²] at L2 Zone 2.4 [NCIS] | 700m² | 2027-02-11 | 2027-03-11 | 28 | NotStart
L5 | 2.4-T | SLB | P1_CN_16710 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [700 m²] at L3 Zone 2.4 [NCIS] | 700m² | 2027-03-12 | 2027-04-09 | 28 | NotStart
L5 | 2.4-T | SLB | P1_CN_16720 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1221 m²] at L5 Zone 2.4 [NCIS] | 1221m² | 2027-04-10 | 2027-05-29 | 49 | NotStart
L5 | 2.6CIS | SLB | P1_CN_16740 | CON¦NB¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [476 m²] at L5 Zone 2.6 [NCIS] | 476m² | 2027-04-15 | 2027-05-13 | 28 | NotStart
L5 | 2.6CIS-T | SLB | P1_CN_16730 | CON¦NB¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [794 m²] at L5 Zone 2.6 [CIS] | 794m² | 2027-02-22 | 2027-04-30 | 67 | NotStart

## 5_MA_逐条
MA — 逐条活动（楼层/小区/工作量）
楼层 | 小区 | 专业 Trade | 活动编号 | 活动名称 Task Name | 工作量 Qty | 开始 | 完成 | 时长 (天) | 状态
Deck | Deck | CON | P1_CN_16750 | CON¦MD¦CON¦T¦Piling Work [20 nos] at Zone P-3.3[CIS] | 20nos | 2026-04-18 | 2026-05-27 | 39 | NotStart
Deck | Deck | CON | P1_CN_16790 | CON¦MD¦CON¦NT¦Piling Work [14 nos] at Zone P-3.4 | 14nos | 2026-04-20 | 2026-05-26 | 36 | NotStart
Deck | Deck | CON | P1_CN_16810 | CON¦MD¦CON¦NT¦Piling Work [14 nos] at Zone P-3.4 | 14nos | 2026-04-20 | 2026-05-27 | 37 | NotStart
Deck | Deck | CON | P1_CN_16800 | CON¦MD¦CON¦NT¦Piling Work [11 nos] at Zone P-3.4 | 11nos | 2026-05-27 | 2026-06-25 | 29 | NotStart
Deck | Deck | CON | P1_CN_16760 | CON¦MD¦CON¦T¦Piling Work [20 nos] at Zone P-3.3[CIS] | 20nos | 2026-05-28 | 2026-07-06 | 39 | NotStart
Deck | Deck | CON | P1_CN_16820 | CON¦MD¦CON¦NT¦Piling Work [23 nos] at Zone P-3.4 | 23nos | 2026-05-28 | 2026-07-30 | 63 | NotStart
Deck | Deck | CON | P1_CN_16770 | CON¦MD¦CON¦T¦Piling Work [20 nos-2 Rig] at Zone P-3.3 | 20nos | 2026-06-26 | 2026-07-25 | 29 | NotStart
Deck | Deck | CON | P1_CN_16780 | CON¦MD¦CON¦NT¦Piling Work [10 nos] at Zone P-3.3 | 10nos | 2026-08-03 | 2026-08-28 | 25 | NotStart
Deck | ZC1 | CYC | P1_CN_16830 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.2 | — | 2026-04-01 | 2026-04-10 | 9 | NotStart
Deck | ZC1 | RCW | P1_CN_16840 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [220 m² ][10nos CP63-67,CP73-77] at Zone C-1.2 | 220m²+10nos | 2026-04-11 | 2026-04-17 | 6 | NotStart
Deck | ZC1 | CYC | P1_CN_16860 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.3 | — | 2026-04-20 | 2026-05-01 | 11 | NotStart
Deck | ZC1 | CYC | P1_CN_16890 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.4 | — | 2026-05-04 | 2026-05-15 | 11 | NotStart
Deck | ZC1 | CYC | P1_CN_16920 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.5 | — | 2026-05-16 | 2026-05-25 | 9 | NotStart
Deck | ZC1 | RCWDT | P1_CN_16850 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [220 m²] at Zone C-1.2 | 220m² | 2026-05-19 | 2026-06-05 | 17 | NotStart
Deck | ZC1 | CYC | P1_CN_16950 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.6 | — | 2026-05-26 | 2026-06-08 | 13 | NotStart
Deck | ZC1 | RCW | P1_CN_16870 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [469 m²][10nos CP83-87,CP92-96] at Zone C-1.3 | 469m²+10nos | 2026-06-06 | 2026-06-12 | 6 | NotStart
Deck | ZC1 | RCW | P1_CN_16960 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [739 m²] at Zone C-1.6 | 739m² | 2026-06-09 | 2026-06-15 | 6 | NotStart
Deck | ZC1 | CYC | P1_CN_16980 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.7 | — | 2026-06-09 | 2026-06-22 | 13 | NotStart
Deck | ZC1 | RCWDT | P1_CN_16880 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [469 m²] at Zone C-1.3 | 469m² | 2026-06-15 | 2026-07-02 | 17 | NotStart
Deck | ZC1 | RCW | P1_CN_16900 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [1023 m²] at Zone C-1.4 | 1023m² | 2026-06-15 | 2026-06-23 | 8 | NotStart
Deck | ZC1 | RCWDT | P1_CN_16970 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [739 m²] at Zone C-1.6 | 739m² | 2026-06-16 | 2026-07-03 | 17 | NotStart
Deck | ZC1 | CYC | P1_CN_17010 | CON¦MD¦CYC¦ Cyclical Works at Zone C-1.1 | — | 2026-06-23 | 2026-07-06 | 13 | NotStart
Deck | ZC1 | RCWDT | P1_CN_16910 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [1023 m²] at Zone C-1.4 | 1023m² | 2026-06-24 | 2026-07-13 | 19 | NotStart
Deck | ZC1 | RCW | P1_CN_16930 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [1678 m²] at Zone C-1.5 | 1678m² | 2026-07-03 | 2026-07-13 | 10 | NotStart
Deck | ZC1 | RCW | P1_CN_17020 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [229 m²] at Zone C-1.1 | 229m² | 2026-07-07 | 2026-07-15 | 8 | NotStart
Deck | ZC1 | RCWDT | P1_CN_16940 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting at Zone [1678 m²] C-1.5 | 1678m² | 2026-07-14 | 2026-07-27 | 13 | NotStart
Deck | ZC1 | RCWDT | P1_CN_17030 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [229 m²] at Zone C-1.1 | 229m² | 2026-07-16 | 2026-08-04 | 19 | NotStart
Deck | ZC1 | RCW | P1_CN_16990 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [825 m²] at Zone C-1.7 | 825m² | 2026-07-28 | 2026-08-03 | 6 | NotStart
Deck | ZC1 | RCWDT | P1_CN_17000 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [825 m²] at Zone C-1.7 | 825m² | 2026-08-04 | 2026-08-21 | 17 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17040 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.1 | — | 2026-08-05 | 2026-08-14 | 9 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17050 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [917 m²] at Zone C-2.1 | 917m² | 2026-08-15 | 2026-08-21 | 6 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17070 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.2 | — | 2026-08-17 | 2026-08-28 | 11 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17060 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [917 m²] at Zone C-2.1 | 917m² | 2026-08-22 | 2026-09-04 | 13 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17080 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [578 m²] at Zone C-2.2 | 578m² | 2026-08-31 | 2026-09-08 | 8 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17100 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.3 | — | 2026-08-31 | 2026-09-11 | 11 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17090 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [578 m²] at Zone C-2.2 | 578m² | 2026-09-09 | 2026-09-28 | 19 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17130 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.4 | — | 2026-09-14 | 2026-09-25 | 11 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17140 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [631 m²] at Zone C-2.4 | 631m² | 2026-09-28 | 2026-10-06 | 8 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17160 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.5 | — | 2026-09-28 | 2026-10-09 | 11 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17150 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [631 m²] at Zone C-2.4 | 631m² | 2026-10-07 | 2026-10-26 | 19 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17170 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [470 m²] at Zone C-2.5 | 470m² | 2026-10-12 | 2026-10-20 | 8 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17190 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.6 | — | 2026-10-12 | 2026-10-23 | 11 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17110 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [432 m²] at Zone C-2.3 | 432m² | 2026-10-13 | 2026-10-22 | 9 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17120 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [432 m²] at Zone C-2.3 | 432m² | 2026-10-22 | 2026-11-11 | 20 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17200 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [615 m²] at Zone C-2.6 | 615m² | 2026-10-26 | 2026-11-03 | 8 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17220 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.7 | — | 2026-10-26 | 2026-11-06 | 11 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17210 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [615 m²] at Zone C-2.6 | 615m² | 2026-11-04 | 2026-11-23 | 19 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17230 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [514 m²] at Zone C-2.7 | 514m² | 2026-11-09 | 2026-11-17 | 8 | NotStart
Deck | ZC2.1+2.2 | CYC | P1_CN_17250 | CON¦MD¦CYC¦ Cyclical Works at Zone C-2.8 | — | 2026-11-09 | 2026-11-20 | 11 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17180 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [470 m²] at Zone C-2.5 | 470m² | 2026-11-11 | 2026-12-01 | 20 | NotStart
Deck | ZC2.1+2.2 | RCW | P1_CN_17260 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [526 m²] at Zone C-2.8 | 526m² | 2026-11-23 | 2026-12-01 | 8 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17240 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [514 m²] at Zone C-2.7 | 514m² | 2026-12-01 | 2026-12-21 | 20 | NotStart
Deck | ZC2.1+2.2 | RCWDT | P1_CN_17270 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [526 m²] at Zone C-2.8 | 526m² | 2026-12-02 | 2026-12-21 | 19 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17520 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.1 | — | 2026-08-24 | 2026-09-04 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17530 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [220 m²] at Zone C-3.2.1 | 220m² | 2026-09-07 | 2026-09-15 | 8 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17550 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.2 | — | 2026-09-07 | 2026-09-18 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17560 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [273 m²] at Zone C-3.2.2 | 273m² | 2026-09-21 | 2026-09-29 | 8 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17580 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.3 | — | 2026-09-21 | 2026-10-02 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17570 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [273 m²]at Zone C-3.2.2 | 273m² | 2026-09-30 | 2026-10-19 | 19 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17540 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [220 m²] at Zone C-3.2.1 | 220m² | 2026-10-05 | 2026-10-22 | 17 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17590 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [313 m²] at Zone C-3.2.3 | 313m² | 2026-10-05 | 2026-10-13 | 8 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17610 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.4 | — | 2026-10-05 | 2026-10-16 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17620 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [591 m²] at Zone C-3.2.4 | 591m² | 2026-10-19 | 2026-10-27 | 8 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17640 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.5 | — | 2026-10-19 | 2026-10-30 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17600 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [313 m²] at Zone C-3.2.3 | 313m² | 2026-10-23 | 2026-11-11 | 19 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17630 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [591 m²] at Zone C-3.2.4 | 591m² | 2026-10-28 | 2026-11-16 | 19 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17650 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [402 m²] at Zone C-3.2.5 | 402m² | 2026-11-02 | 2026-11-10 | 8 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17670 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.6 | — | 2026-11-02 | 2026-11-13 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17660 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [402 m²] at Zone C-3.2.5 | 402m² | 2026-11-12 | 2026-12-01 | 19 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17680 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [332 m²] at Zone C-3.2.6 | 332m² | 2026-11-16 | 2026-11-24 | 8 | NotStart
Deck | ZC3.1a+3.2 | CYC | P1_CN_17700 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.2.7 | — | 2026-11-16 | 2026-11-27 | 11 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17690 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [332 m²] at Zone C-3.2.6 | 332m² | 2026-11-25 | 2026-12-14 | 19 | NotStart
Deck | ZC3.1a+3.2 | RCW | P1_CN_17710 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [600 m²] at Zone C-3.2.7 | 600m² | 2026-11-30 | 2026-12-08 | 8 | NotStart
Deck | ZC3.1a+3.2 | RCWDT | P1_CN_17720 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [600 m²] at Zone C-3.2.7 | 600m² | 2026-12-09 | 2026-12-28 | 19 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17280 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.1 | — | 2026-08-24 | 2026-09-04 | 11 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17290 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [543 m²] at Zone C-3.1.1 | 543m² | 2026-09-07 | 2026-09-15 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17310 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.2 | — | 2026-09-07 | 2026-09-18 | 11 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17320 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [542 m²] at Zone C-3.1.2 | 542m² | 2026-09-21 | 2026-09-29 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17340 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.3 | — | 2026-09-21 | 2026-10-02 | 11 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17330 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [542 m²] at Zone C-3.1.2 | 542m² | 2026-09-29 | 2026-10-19 | 20 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17350 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [542 m²] at Zone C-3.1.3 | 542m² | 2026-10-05 | 2026-10-13 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17370 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.4 | — | 2026-10-05 | 2026-10-16 | 11 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17300 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [543 m²] at Zone C-3.1.1 | 543m² | 2026-10-12 | 2026-10-29 | 17 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17380 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [541 m²] at Zone C-3.1.4 | 541m² | 2026-10-19 | 2026-10-27 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17400 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.5 | — | 2026-10-19 | 2026-10-30 | 11 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17390 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [541 m²] at Zone C-3.1.4 | 541m² | 2026-10-27 | 2026-11-16 | 20 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17360 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [542 m²] at Zone C-3.1.3 | 542m² | 2026-10-30 | 2026-11-18 | 19 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17410 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [315 m²] at Zone C-3.1.5 | 315m² | 2026-11-02 | 2026-11-10 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17430 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.6 | — | 2026-11-02 | 2026-11-13 | 11 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17440 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [648 m²] at Zone C-3.1.6 | 648m² | 2026-11-16 | 2026-11-24 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17460 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.7 | — | 2026-11-16 | 2026-11-27 | 11 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17420 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [315 m²] at Zone C-3.1.5 | 315m² | 2026-11-19 | 2026-12-08 | 19 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17450 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [648 m²] at Zone C-3.1.6 | 648m² | 2026-11-24 | 2026-12-14 | 20 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17470 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [1044 m²] at Zone C-3.1.7 | 1044m² | 2026-11-30 | 2026-12-08 | 8 | NotStart
Deck | ZC3.1b | CYC | P1_CN_17490 | CON¦MD¦CYC¦ Cyclical Works at Zone C-3.1.8 | — | 2026-11-30 | 2026-12-11 | 11 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17480 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [1044 m²] at Zone C-3.1.7 | 1044m² | 2026-12-09 | 2026-12-28 | 19 | NotStart
Deck | ZC3.1b | RCW | P1_CN_17500 | CON¦MD¦RCW¦ Working Platform Preparation & Precast Beam Installation Work [573 m²] at Zone C-3.1.8 | 573m² | 2026-12-14 | 2026-12-22 | 8 | NotStart
Deck | ZC3.1b | RCWDT | P1_CN_17510 | CON¦MD¦RCWDT¦ RC Works - Beam & Slab Concreting [573 m²] at Zone C-3.1.8 | 573m² | 2026-12-22 | 2027-01-11 | 20 | NotStart
L1 | 1.1 | SLB | P1_CN_17730 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-1.1 [NCIS] | — | 2026-08-05 | 2026-10-08 | 64 | NotStart
L1 | 1.1 | COL | P1_CN_17740 | CON¦MR¦COL¦NT¦ Columns Work [5nos-WF-1C23,24,25,27,28] at L1 Zone P-1.1 [NCIS] | 5nos | 2026-10-09 | 2026-10-28 | 19 | NotStart
L1 | 1.1 | COL | P1_CN_17750 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone P-1.1 [NCIS] | 5nos | 2026-10-29 | 2026-11-06 | 8 | NotStart
L1 | 1.1 | STB | P1_CN_17760 | CON¦MR¦STB¦NT¦ Steel Beam Installation [32 nos] at L1 Zone P-1.1 [NCIS] | 32nos | 2026-11-09 | 2026-11-17 | 8 | NotStart
L1 | 1.1 | MBR | P1_CN_17770 | CON¦MR¦MBR¦NT¦ Main Beam RC [8 nos] at L1 Zone P-1.1 [NCIS] | 8nos | 2026-11-18 | 2026-11-26 | 8 | NotStart
L1 | 1.2 | SLB | P1_CN_17820 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-1.2 [NCIS] | — | 2026-06-16 | 2026-07-03 | 17 | NotStart
L1 | 1.2 | COL | P1_CN_17830 | CON¦MR¦COL¦NT¦ Columns Work [1 nos-WF-B2C53 + 9 nos] at L1 Zone P-1.2 [NCIS] | 10nos | 2026-07-06 | 2026-07-23 | 17 | NotStart
L1 | 1.2 | WAL | P1_CN_17850 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST-45/46] at L1 Zone P-1.2 [NCIS] | 1nos | 2026-07-06 | 2026-08-14 | 39 | NotStart
L1 | 1.2 | COL | P1_CN_17840 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [10 nos] at L1 Zone P-1.2 [NCIS] | 10nos | 2026-07-24 | 2026-08-03 | 10 | NotStart
L1 | 1.2 | STB | P1_CN_17870 | CON¦MR¦STB¦NT¦ Steel Beam Installation [38 nos] at L1 Zone P-1.2 [NCIS] | 38nos | 2026-08-04 | 2026-08-12 | 8 | NotStart
L1 | 1.2 | MBR | P1_CN_17880 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L1 Zone P-1.2 [NCIS] | 11nos | 2026-08-13 | 2026-08-21 | 8 | NotStart
L1 | 1.2 | CRW | P1_CN_17860 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L1 Zone P-1.2 [CIS] | — | 2026-08-17 | 2026-08-25 | 8 | NotStart
L1 | 1.2-T | COL | P1_CN_17780 | CON¦MR¦COL¦T¦ Columns Work [9nos-WF-1C35,36,40,41,45,46,50,51,52] at L1 Zone P-1.2 [NCIS] | 9nos | 2026-07-06 | 2026-08-03 | 28 | NotStart
L1 | 1.2-T | COL | P1_CN_17790 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [9 nos] at L1 Zone P-1.2 [NCIS] | 9nos | 2026-07-16 | 2026-08-04 | 19 | NotStart
L1 | 1.2-T | STB | P1_CN_17800 | CON¦MR¦STB¦T¦ Steel Beam Installation [72 nos] at L1 Zone P-1.2 [NCIS] | 72nos | 2026-07-30 | 2026-08-12 | 13 | NotStart
L1 | 1.2-T | MBR | P1_CN_17810 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L1 Zone P-1.2 [NCIS] | 9nos | 2026-08-12 | 2026-08-31 | 19 | NotStart
L1 | 3.1-T | SLB | P1_CN_18000 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-3.1 [NCIS] | — | 2026-08-24 | 2026-10-06 | 43 | NotStart
L1 | 3.1-T | COL | P1_CN_18010 | CON¦MR¦COL¦T¦ Columns Work [4nos-WF-1C57,58,65,73 + 2 nos] at L1 Zone P-3.1 [NCIS] | 6nos | 2026-10-07 | 2026-10-26 | 19 | NotStart
L1 | 3.1-T | COL | P1_CN_18020 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L1 Zone P-3.1 [NCIS] | 6nos | 2026-10-27 | 2026-10-29 | 2 | NotStart
L1 | 3.1-T | STB | P1_CN_18030 | CON¦MR¦STB¦T¦ Steel Beam Installation [29 nos] at L1 Zone P-3.1 [NCIS] | 29nos | 2026-10-30 | 2026-11-05 | 6 | NotStart
L1 | 3.1-T | MBR | P1_CN_18040 | CON¦MR¦MBR¦T¦ Main Beam RC [13 nos] at L1 Zone P-3.1 [NCIS] | 13nos | 2026-11-06 | 2026-11-13 | 7 | NotStart
L1 | 3.1CIS-T | SLB | P1_CN_18050 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-3.1 [CIS] | — | 2026-09-05 | 2026-09-18 | 13 | NotStart
L1 | 3.1CIS-T | COL | P1_CN_18070 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C59,66,67,74,83,82 + 1 nos] at L1 Zone P-3.1 [CIS] | 7nos | 2026-09-14 | 2026-09-25 | 11 | NotStart
L1 | 3.1CIS-T | CRW | P1_CN_18060 | CON¦MR¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW01] at L1 Zone P-3.1 [CIS] | 1nos | 2026-09-21 | 2026-10-19 | 28 | NotStart
L1 | 3.1CIS-T | WAL | P1_CN_18090 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [3 nos-ST-20/21, ST-04, ST-18/19 + 1 nos] ] at L1 Zone P-3.1 [CIS] | 4nos | 2026-09-21 | 2026-10-19 | 28 | NotStart
L1 | 3.1CIS-T | COL | P1_CN_18080 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L1 Zone P-3.1 [CIS] | 7nos | 2026-09-28 | 2026-09-30 | 2 | NotStart
L1 | 3.1CIS-T | STB | P1_CN_18110 | CON¦MR¦STB¦T¦ Steel Beam Installation [21 nos] at L1 Zone P-3.1 [CIS] | 21nos | 2026-10-01 | 2026-10-09 | 8 | NotStart
L1 | 3.1CIS-T | MBR | P1_CN_18120 | CON¦MR¦MBR¦T¦ Main Beam RC [6 nos] at L1 Zone P-3.1 [CIS] | 6nos | 2026-10-12 | 2026-10-20 | 8 | NotStart
L1 | 3.1CIS-T | CRW | P1_CN_18100 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L1 Zone P-3.1 [CIS] | — | 2026-10-20 | 2026-10-28 | 8 | NotStart
L1 | 3.2 | SLB | P1_CN_17930 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-3.2 [NCIS] | — | 2026-08-29 | 2026-10-17 | 49 | NotStart
L1 | 3.2 | COL | P1_CN_17940 | CON¦MR¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [5nos-WF-1C55,63,70,71] at L1 Zone P-3.2 [NCIS] | 5nos | 2026-10-18 | 2026-10-31 | 13 | NotStart
L1 | 3.2 | WAL | P1_CN_17960 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-LW10/ST-07/50] at L1 Zone P-3.2 [NCIS] | 1nos | 2026-10-19 | 2026-11-27 | 39 | NotStart
L1 | 3.2 | COL | P1_CN_17950 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone P-3.2 [NCIS] | 5nos | 2026-11-01 | 2026-11-03 | 2 | NotStart
L1 | 3.2 | STB | P1_CN_17980 | CON¦MR¦STB¦NT¦ Steel Beam Installation [40 nos] at L1 Zone P-3.2 [NCIS] | 40nos | 2026-11-04 | 2026-11-10 | 6 | NotStart
L1 | 3.2 | MBR | P1_CN_17990 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L1 Zone P-3.2 [NCIS] | 11nos | 2026-11-11 | 2026-11-17 | 6 | NotStart
L1 | 3.2 | CRW | P1_CN_17970 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L1 Zone P-3.2 [NCIS] | — | 2026-11-30 | 2026-12-08 | 8 | NotStart
L1 | 3.2-T | COL | P1_CN_17890 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos-WF-1C56] at L1 Zone P-3.2 [NCIS] | 1nos | 2026-10-19 | 2026-11-09 | 21 | NotStart
L1 | 3.2-T | COL | P1_CN_17900 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L1 Zone P-3.2 [NCIS] | 1nos | 2026-11-10 | 2026-11-12 | 2 | NotStart
L1 | 3.2-T | STB | P1_CN_17910 | CON¦MR¦STB¦T¦ Steel Beam Installation [8 nos] at L1 Zone P-3.2 [NCIS] | 8nos | 2026-11-13 | 2026-11-23 | 10 | NotStart
L1 | 3.2-T | MBR | P1_CN_17920 | CON¦MR¦MBR¦T¦ Main Beam RC [1 nos] at L1 Zone P-3.2 [NCIS] | 1nos | 2026-11-24 | 2026-12-02 | 8 | NotStart
L1 | 3.3-T | SLB | P1_CN_18220 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-3.3 [NCIS] | — | 2026-09-09 | 2026-10-13 | 34 | NotStart
L1 | 3.3-T | COL | P1_CN_18230 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos-WF-1C80] at L1 Zone P-3.3 [NCIS] | 1nos | 2026-10-14 | 2026-10-22 | 8 | NotStart
L1 | 3.3-T | COL | P1_CN_18240 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L1 Zone P-3.3 [NCIS] | 1nos | 2026-10-23 | 2026-10-27 | 4 | NotStart
L1 | 3.3-T | STB | P1_CN_18250 | CON¦MR¦STB¦T¦ Steel Beam Installation [16 nos] at L1 Zone P-3.3 [NCIS] | 16nos | 2026-10-28 | 2026-10-30 | 2 | NotStart
L1 | 3.3-T | MBR | P1_CN_18260 | CON¦MR¦MBR¦T¦ Main Beam RC [2 nos] at L1 Zone P-3.3 [NCIS] | 2nos | 2026-11-02 | 2026-11-10 | 8 | NotStart
L1 | 3.3CIS-T | SLB | P1_CN_18270 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-3.3 [CIS] | — | 2026-07-26 | 2026-08-24 | 29 | NotStart
L1 | 3.3CIS-T | COL | P1_CN_18280 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C81,90,91,92,99,100] at L1 Zone P-3.3 [CIS] | 6nos | 2026-08-25 | 2026-09-22 | 28 | NotStart
L1 | 3.3CIS-T | WAL | P1_CN_18300 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [4 nos-ST-16/17, ST-14/15, ST-12/13, ST-10/11] at L1 Zone P-3.3 [CIS] | 4nos | 2026-08-25 | 2026-09-22 | 28 | NotStart
L1 | 3.3CIS-T | COL | P1_CN_18290 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L1 Zone P-3.3 [CIS] | 6nos | 2026-09-23 | 2026-09-25 | 2 | NotStart
L1 | 3.3CIS-T | CRW | P1_CN_18310 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L1 Zone P-3.3 [CIS] | — | 2026-09-23 | 2026-10-01 | 8 | NotStart
L1 | 3.3CIS-T | STB | P1_CN_18320 | CON¦MR¦STB¦T¦ Steel Beam Installation [24 nos] at L1 Zone P-3.3 [CIS] | 24nos | 2026-09-28 | 2026-10-06 | 8 | NotStart
L1 | 3.3CIS-T | MBR | P1_CN_18330 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L1 Zone P-3.3 [CIS] | 9nos | 2026-10-07 | 2026-10-15 | 8 | NotStart
L1 | 3.4 | SLB | P1_CN_18170 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] at L1 Zone P-3.4 [NCIS] | — | 2026-10-07 | 2026-10-28 | 21 | NotStart
L1 | 3.4 | COL | P1_CN_18180 | CON¦MR¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [5nos-WF-1C78,79,88,96,97] at L1 Zone P-3.4 [NCIS] | 5nos | 2026-10-29 | 2026-11-06 | 8 | NotStart
L1 | 3.4 | COL | P1_CN_18190 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L1 Zone P-3.4 [NCIS] | 5nos | 2026-11-09 | 2026-11-11 | 2 | NotStart
L1 | 3.4 | STB | P1_CN_18200 | CON¦MR¦STB¦NT¦ Steel Beam Installation [11 nos] at L1 Zone P-3.4 [NCIS] | 11nos | 2026-11-12 | 2026-11-20 | 8 | NotStart
L1 | 3.4 | MBR | P1_CN_18210 | CON¦MR¦MBR¦NT¦ Main Beam RC [5 nos] at L1 Zone P-3.4 [NCIS] | 5nos | 2026-11-23 | 2026-12-01 | 8 | NotStart
L1 | 3.4-T | COL | P1_CN_18130 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C89,98] at L1 Zone P-3.4 [NCIS] | 2nos | 2026-10-29 | 2026-11-06 | 8 | NotStart
L1 | 3.4-T | COL | P1_CN_18140 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L1 Zone P-3.4 [NCIS] | 2nos | 2026-11-09 | 2026-11-11 | 2 | NotStart
L1 | 3.4-T | STB | P1_CN_18150 | CON¦MR¦STB¦T¦ Steel Beam Installation [32 nos] at L1 Zone P-3.4 [NCIS] | 32nos | 2026-11-12 | 2026-11-20 | 8 | NotStart
L1 | 3.4-T | MBR | P1_CN_18160 | CON¦MR¦MBR¦T¦ Main Beam RC [4 nos] at L1 Zone P-3.4 [NCIS] | 4nos | 2026-11-23 | 2026-12-01 | 8 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18340 | CON¦MR¦SLB¦L1¦POD1.2¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [3501 m²] | 3501m² | 2026-07-06 | 2026-08-03 | 28 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18350 | CON¦MR¦SLB¦L1¦POD1.1¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [540 m²] | 540m² | 2026-08-04 | 2026-09-01 | 28 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18360 | CON¦MR¦SLB¦L1¦POD3.2¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [135 m²] | 135m² | 2026-09-02 | 2026-09-21 | 19 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18370 | CON¦MR¦SLB¦L1¦POD3.2¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing][953 m²] | 953m² | 2026-09-22 | 2026-10-09 | 17 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18380 | CON¦MR¦SLB¦L1¦POD3.1¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [1979 m²] | 1979m² | 2026-10-12 | 2026-10-29 | 17 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18390 | CON¦MR¦SLB¦L1¦POD3.4¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [933 m²] | 933m² | 2026-10-30 | 2026-11-18 | 19 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18400 | CON¦MR¦SLB¦L1¦POD3.3¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [415 m²] | 415m² | 2026-11-19 | 2026-12-08 | 19 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18410 | CON¦MR¦SLB¦L1¦POD3.3¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [730 m²] | 730m² | 2026-12-09 | 2026-12-28 | 19 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18411 | CON¦MR¦SLB¦L1¦ZC3.1¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [730 m²] | 730m² | 2026-12-29 | 2027-01-15 | 17 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18412 | CON¦MR¦SLB¦L1¦ZC3.2¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [761 m²] | 761m² | 2027-01-18 | 2027-02-04 | 17 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18413 | CON¦MR¦SLB¦L1¦ZC3.1A¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [1784 m²] | 1784m² | 2027-02-05 | 2027-02-24 | 19 | NotStart
L1 | TOP SLAB | SLB | P1_CN_18414 | CON¦MR¦SLB¦L1¦ZC3.1B¦ Top Slab Construction [RC Wall + M&E + Top Slab + Slab Curing] [3406 m²] | 3406m² | 2027-02-25 | 2027-03-25 | 28 | NotStart
L2 | 1.1 | COL | P1_CN_18420 | CON¦MR¦COL¦NT¦ Columns Work [5nos-WF-1C23,24,25,27,28] at L2 Zone P-1.1 [NCIS] | 5nos | 2026-11-27 | 2026-12-16 | 19 | NotStart
L2 | 1.1 | COL | P1_CN_18430 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L2 Zone P-1.1 [NCIS] | 5nos | 2026-12-17 | 2026-12-25 | 8 | NotStart
L2 | 1.1 | STB | P1_CN_18440 | CON¦MR¦STB¦NT¦ Steel Beam Installation [32 nos] at L2 Zone P-1.1 [NCIS] | 32nos | 2026-12-28 | 2027-01-05 | 8 | NotStart
L2 | 1.1 | MBR | P1_CN_18450 | CON¦MR¦MBR¦NT¦ Main Beam RC [8 nos] at L2 Zone P-1.1 [NCIS] | 8nos | 2027-01-06 | 2027-01-14 | 8 | NotStart
L2 | 1.2 | COL | P1_CN_18500 | CON¦MR¦COL¦NT¦ Columns Work [6 nos-WF-1C30,31,33,38,43,49] at L2 Zone P-1.2 [NCIS] | 6nos | 2026-08-24 | 2026-09-10 | 17 | NotStart
L2 | 1.2 | WAL | P1_CN_18520 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST45/46] at L2 Zone P-1.2 [NCIS] | 1nos | 2026-08-26 | 2026-10-06 | 41 | NotStart
L2 | 1.2 | COL | P1_CN_18510 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L2 Zone P-1.2 [NCIS] | 6nos | 2026-09-11 | 2026-09-21 | 10 | NotStart
L2 | 1.2 | STB | P1_CN_18540 | CON¦MR¦STB¦NT¦ Steel Beam Installation [38 nos] at L2 Zone P-1.2 [NCIS] | 38nos | 2026-09-22 | 2026-09-30 | 8 | NotStart
L2 | 1.2 | MBR | P1_CN_18550 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L2 Zone P-1.2 [NCIS] | 11nos | 2026-10-01 | 2026-10-09 | 8 | NotStart
L2 | 1.2 | CRW | P1_CN_18530 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone P-1.2 [CIS] | — | 2026-10-07 | 2026-10-15 | 8 | NotStart
L2 | 1.2-T | COL | P1_CN_18460 | CON¦MR¦COL¦T¦ Columns Work [15nos-WF-1C34,35,36,39,40,41,44,45,46,47,50,51,52,53,WF-B2C53] at L2 Zone P-1.2 [NCIS] | 15nos | 2026-09-01 | 2026-09-29 | 28 | NotStart
L2 | 1.2-T | COL | P1_CN_18470 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [15 nos] at L2 Zone P-1.2 [NCIS] | 15nos | 2026-09-17 | 2026-10-06 | 19 | NotStart
L2 | 1.2-T | STB | P1_CN_18480 | CON¦MR¦STB¦T¦ Steel Beam Installation [72 nos] at L2 Zone P-1.2 [NCIS] | 72nos | 2026-10-01 | 2026-10-14 | 13 | NotStart
L2 | 1.2-T | MBR | P1_CN_18490 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L2 Zone P-1.2 [NCIS] | 9nos | 2026-10-14 | 2026-11-02 | 19 | NotStart
L2 | 3.1-T | COL | P1_CN_18660 | CON¦MR¦COL¦T¦ Columns Work [5nos-WF-1C57,58,65,72,73 + 1 nos] at L2 Zone P-3.1 [NCIS] | 6nos | 2026-11-16 | 2026-12-03 | 17 | NotStart
L2 | 3.1-T | COL | P1_CN_18670 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L2 Zone P-3.1 [NCIS] | 6nos | 2026-12-04 | 2026-12-08 | 4 | NotStart
L2 | 3.1-T | STB | P1_CN_18680 | CON¦MR¦STB¦T¦ Steel Beam Installation [29 nos] at L2 Zone P-3.1 [NCIS] | 29nos | 2026-12-09 | 2026-12-15 | 6 | NotStart
L2 | 3.1-T | MBR | P1_CN_18690 | CON¦MR¦MBR¦T¦ Main Beam RC [13 nos] at L2 Zone P-3.1 [NCIS] | 13nos | 2026-12-16 | 2026-12-23 | 7 | NotStart
L2 | 3.1CIS-T | SLB | P1_CN_18700 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [883 m²] at L2 Zone P-3.1 [CIS] | 883m² | 2026-10-21 | 2026-11-09 | 19 | NotStart
L2 | 3.1CIS-T | CRW | P1_CN_18710 | CON¦MR¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW01] at L2 Zone P-3.1 [CIS] | 1nos | 2026-10-29 | 2026-11-26 | 28 | NotStart
L2 | 3.1CIS-T | WAL | P1_CN_18740 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [3 nos-ST-20/21, ST-04, ST-18/19 + 1 nos] at L2 Zone P-3.1 [CIS] | 4nos | 2026-10-29 | 2026-11-26 | 28 | NotStart
L2 | 3.1CIS-T | COL | P1_CN_18720 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C59,66,67,74,82,83 + 1 nos] at L2 Zone P-3.1 [CIS] | 7nos | 2026-11-03 | 2026-11-16 | 13 | NotStart
L2 | 3.1CIS-T | COL | P1_CN_18730 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L2 Zone P-3.1 [CIS] | 7nos | 2026-11-17 | 2026-11-19 | 2 | NotStart
L2 | 3.1CIS-T | STB | P1_CN_18760 | CON¦MR¦STB¦T¦ Steel Beam Installation [21 nos] at L2 Zone P-3.1 [CIS] | 21nos | 2026-11-20 | 2026-11-30 | 10 | NotStart
L2 | 3.1CIS-T | CRW | P1_CN_18750 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone P-3.1 [CIS] | — | 2026-11-27 | 2026-12-07 | 10 | NotStart
L2 | 3.1CIS-T | MBR | P1_CN_18770 | CON¦MR¦MBR¦T¦ Main Beam RC [6 nos] at L2 Zone P-3.1 [CIS] | 6nos | 2026-12-01 | 2026-12-09 | 8 | NotStart
L2 | 3.2 | COL | P1_CN_18600 | CON¦MR¦COL¦NT¦ Columns Work [8nos-WF-1C55,63,70,71,54,61,68,69] at L2 Zone P-3.2 [NCIS] | 8nos | 2026-11-18 | 2026-12-01 | 13 | NotStart
L2 | 3.2 | COL | P1_CN_18610 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [8 nos] at L2 Zone P-3.2 [NCIS] | 8nos | 2026-12-02 | 2026-12-04 | 2 | NotStart
L2 | 3.2 | STB | P1_CN_18640 | CON¦MR¦STB¦NT¦ Steel Beam Installation [40 nos] at L2 Zone P-3.2 [NCIS] | 40nos | 2026-12-07 | 2026-12-15 | 8 | NotStart
L2 | 3.2 | WAL | P1_CN_18620 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-LW10/ST-07/50] at L2 Zone P-3.2 [NCIS] | 1nos | 2026-12-09 | 2027-01-19 | 41 | NotStart
L2 | 3.2 | MBR | P1_CN_18650 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L2 Zone P-3.2 [NCIS] | 11nos | 2026-12-16 | 2026-12-24 | 8 | NotStart
L2 | 3.2 | CRW | P1_CN_18630 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone P-3.2 [CIS] | — | 2027-01-20 | 2027-01-28 | 8 | NotStart
L2 | 3.2-T | COL | P1_CN_18560 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos-WF-1C56] at L2 Zone P-3.2 [NCIS] | 1nos | 2026-12-03 | 2026-12-11 | 8 | NotStart
L2 | 3.2-T | COL | P1_CN_18570 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L2 Zone P-3.2 [NCIS] | 1nos | 2026-12-14 | 2026-12-16 | 2 | NotStart
L2 | 3.2-T | STB | P1_CN_18580 | CON¦MR¦STB¦T¦ Steel Beam Installation [8 nos] at L2 Zone P-3.2 [NCIS] | 8nos | 2026-12-17 | 2026-12-25 | 8 | NotStart
L2 | 3.2-T | MBR | P1_CN_18590 | CON¦MR¦MBR¦T¦ Main Beam RC [1 nos] at L2 Zone P-3.2 [NCIS] | 1nos | 2026-12-28 | 2027-01-05 | 8 | NotStart
L2 | 3.3-T | COL | P1_CN_18860 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C79,80] at L2 Zone P-3.3 [NCIS] | 2nos | 2026-11-11 | 2026-11-19 | 8 | NotStart
L2 | 3.3-T | COL | P1_CN_18870 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L2 Zone P-3.3 [NCIS] | 2nos | 2026-11-20 | 2026-11-24 | 4 | NotStart
L2 | 3.3-T | STB | P1_CN_18880 | CON¦MR¦STB¦T¦ Steel Beam Installation [16 nos] at L2 Zone P-3.3 [NCIS] | 16nos | 2026-11-25 | 2026-11-27 | 2 | NotStart
L2 | 3.3-T | MBR | P1_CN_18890 | CON¦MR¦MBR¦T¦ Main Beam RC [2 nos] at L2 Zone P-3.3 [NCIS] | 2nos | 2026-11-30 | 2026-12-08 | 8 | NotStart
L2 | 3.3CIS-T | WAL | P1_CN_18930 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [4 nos-ST-16/17, ST-14/15, ST-12/13, ST-10/11] at L2 Zone P-3.3 [CIS] | 4nos | 2026-10-02 | 2026-10-30 | 28 | NotStart
L2 | 3.3CIS-T | SLB | P1_CN_18900 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [730 m²] at L2 Zone P-3.3 [CIS] | 730m² | 2026-10-16 | 2026-10-29 | 13 | NotStart
L2 | 3.3CIS-T | COL | P1_CN_18910 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C81,90,91,92,99,100] at L2 Zone P-3.3 [CIS] | 6nos | 2026-10-30 | 2026-11-19 | 20 | NotStart
L2 | 3.3CIS-T | CRW | P1_CN_18940 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L2 Zone P-3.3 [CIS] | — | 2026-11-02 | 2026-11-10 | 8 | NotStart
L2 | 3.3CIS-T | COL | P1_CN_18920 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L2 Zone P-3.3 [CIS] | 6nos | 2026-11-20 | 2026-11-24 | 4 | NotStart
L2 | 3.3CIS-T | STB | P1_CN_18950 | CON¦MR¦STB¦T¦ Steel Beam Installation [24 nos] at L2 Zone P-3.3 [CIS] | 24nos | 2026-11-25 | 2026-12-03 | 8 | NotStart
L2 | 3.3CIS-T | MBR | P1_CN_18960 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L2 Zone P-3.3 [CIS] | 9nos | 2026-12-04 | 2026-12-14 | 10 | NotStart
L2 | 3.4 | COL | P1_CN_18820 | CON¦MR¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C78,96] at L2 Zone P-3.4 [NCIS] | 2nos | 2026-12-02 | 2026-12-10 | 8 | NotStart
L2 | 3.4 | COL | P1_CN_18830 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L2 Zone P-3.4 [NCIS] | 2nos | 2026-12-11 | 2026-12-15 | 4 | NotStart
L2 | 3.4 | STB | P1_CN_18840 | CON¦MR¦STB¦NT¦ Steel Beam Installation [11 nos] at L2 Zone P-3.4 [NCIS] | 11nos | 2026-12-16 | 2026-12-24 | 8 | NotStart
L2 | 3.4 | MBR | P1_CN_18850 | CON¦MR¦MBR¦NT¦ Main Beam RC [5 nos] at L2 Zone P-3.4 [NCIS] | 5nos | 2026-12-25 | 2027-01-04 | 10 | NotStart
L2 | 3.4-T | COL | P1_CN_18780 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [4nos-WF-1C88,89,97,98] at L2 Zone P-3.4 [NCIS] | 4nos | 2026-12-02 | 2026-12-10 | 8 | NotStart
L2 | 3.4-T | COL | P1_CN_18790 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L2 Zone P-3.4 [NCIS] | 2nos | 2026-12-11 | 2026-12-15 | 4 | NotStart
L2 | 3.4-T | STB | P1_CN_18800 | CON¦MR¦STB¦T¦ Steel Beam Installation [32 nos] at L2 Zone P-3.4 [NCIS] | 32nos | 2026-12-16 | 2026-12-24 | 8 | NotStart
L2 | 3.4-T | MBR | P1_CN_18810 | CON¦MR¦MBR¦T¦ Main Beam RC [4 nos] at L2 Zone P-3.4 [NCIS] | 4nos | 2026-12-25 | 2027-01-04 | 10 | NotStart
L3 | 1.1 | COL | P1_CN_18970 | CON¦MR¦COL¦NT¦ Columns Work [5nos-WF-1C23,24,25,27,28] at L3 Zone P-1.1 [NCIS] | 5nos | 2027-01-15 | 2027-02-03 | 19 | NotStart
L3 | 1.1 | COL | P1_CN_18980 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [5 nos] at L3 Zone P-1.1 [NCIS] | 5nos | 2027-02-04 | 2027-02-12 | 8 | NotStart
L3 | 1.1 | STB | P1_CN_18990 | CON¦MR¦STB¦NT¦ Steel Beam Installation [32 nos] at L3 Zone P-1.1 [NCIS] | 32nos | 2027-02-15 | 2027-02-23 | 8 | NotStart
L3 | 1.1 | MBR | P1_CN_19000 | CON¦MR¦MBR¦NT¦ Main Beam RC [8 nos] at L3 Zone P-1.1 [NCIS] | 8nos | 2027-02-24 | 2027-03-04 | 8 | NotStart
L3 | 1.2 | COL | P1_CN_19050 | CON¦MR¦COL¦NT¦ Columns Work [6 nos-WF-1C30,31,33,38,43,49] at L3 Zone P-1.2 [NCIS] | 6nos | 2026-10-12 | 2026-10-29 | 17 | NotStart
L3 | 1.2 | WAL | P1_CN_19070 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST45/46] at L3 Zone P-1.2 [NCIS] | 1nos | 2026-10-16 | 2026-11-26 | 41 | NotStart
L3 | 1.2 | COL | P1_CN_19060 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L3 Zone P-1.2 [NCIS] | 6nos | 2026-10-30 | 2026-11-09 | 10 | NotStart
L3 | 1.2 | STB | P1_CN_19090 | CON¦MR¦STB¦NT¦ Steel Beam Installation [38 nos] at L3 Zone P-1.2 [NCIS] | 38nos | 2026-11-10 | 2026-11-18 | 8 | NotStart
L3 | 1.2 | MBR | P1_CN_19100 | CON¦MR¦MBR¦NT¦ Main Beam RC [1 nos] at L3 Zone P-1.2 [NCIS] | 1nos | 2026-11-19 | 2026-11-27 | 8 | NotStart
L3 | 1.2 | CRW | P1_CN_19080 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone P-1.2 [CIS] | — | 2026-11-27 | 2026-12-07 | 10 | NotStart
L3 | 1.2-T | COL | P1_CN_19010 | CON¦MR¦COL¦T¦ Columns Work [15nos-WF-1C34,35,36,39,40,41,44,45,46,47,50,51,52,53,WF-B2C53] at L3 Zone P-1.2 [NCIS] | 15nos | 2026-11-03 | 2026-12-01 | 28 | NotStart
L3 | 1.2-T | COL | P1_CN_19020 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [13 nos] at L3 Zone P-1.2 [NCIS] | 13nos | 2026-11-19 | 2026-12-08 | 19 | NotStart
L3 | 1.2-T | STB | P1_CN_19030 | CON¦MR¦STB¦T¦ Steel Beam Installation [72 nos] at L3 Zone P-1.2 [NCIS] | 72nos | 2026-12-03 | 2026-12-16 | 13 | NotStart
L3 | 1.2-T | MBR | P1_CN_19040 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L3 Zone P-1.2 [NCIS] | 9nos | 2026-12-17 | 2027-01-05 | 19 | NotStart
L3 | 3.1-T | COL | P1_CN_19210 | CON¦MR¦COL¦T¦ Columns Work [5nos-WF-1C57,58,65,72,73 + 1 nos] at L3 Zone P-3.1 [NCIS] | 6nos | 2026-12-24 | 2027-01-12 | 19 | NotStart
L3 | 3.1-T | COL | P1_CN_19220 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L3 Zone P-3.1 [NCIS] | 6nos | 2027-01-13 | 2027-01-15 | 2 | NotStart
L3 | 3.1-T | STB | P1_CN_19230 | CON¦MR¦STB¦T¦ Steel Beam Installation [29 nos] at L3 Zone P-3.1 [NCIS] | 29nos | 2027-01-18 | 2027-01-22 | 4 | NotStart
L3 | 3.1-T | MBR | P1_CN_19240 | CON¦MR¦MBR¦T¦ Main Beam RC [13 nos] at L3 Zone P-3.1 [NCIS] | 13nos | 2027-01-25 | 2027-02-01 | 7 | NotStart
L3 | 3.1CIS-T | CRW | P1_CN_19260 | CON¦MR¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW01] at L3 Zone P-3.1 [CIS] | 1nos | 2026-12-08 | 2027-01-05 | 28 | NotStart
L3 | 3.1CIS-T | WAL | P1_CN_19290 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [3 nos-ST-20/21, ST-04, ST-18/19 + 1 nos]at L3 Zone P-3.1 [CIS] | 4nos | 2026-12-08 | 2027-01-05 | 28 | NotStart
L3 | 3.1CIS-T | SLB | P1_CN_19250 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [883 m²] at L3 Zone P-3.1 [CIS] | 883m² | 2026-12-10 | 2026-12-29 | 19 | NotStart
L3 | 3.1CIS-T | COL | P1_CN_19270 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C59,66,67,74,82,83 + 1 nos] at L3 Zone P-3.1 [CIS] | 7nos | 2026-12-23 | 2027-01-05 | 13 | NotStart
L3 | 3.1CIS-T | COL | P1_CN_19280 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L3 Zone P-3.1 [CIS] | 7nos | 2027-01-06 | 2027-01-08 | 2 | NotStart
L3 | 3.1CIS-T | CRW | P1_CN_19300 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone P-3.1 [CIS] | — | 2027-01-06 | 2027-01-14 | 8 | NotStart
L3 | 3.1CIS-T | STB | P1_CN_19310 | CON¦MR¦STB¦T¦ Steel Beam Installation [21 nos] at L3 Zone P-3.1 [CIS] | 21nos | 2027-01-11 | 2027-01-19 | 8 | NotStart
L3 | 3.1CIS-T | MBR | P1_CN_19320 | CON¦MR¦MBR¦T¦ Main Beam RC [6 nos] at L3 Zone P-3.1 [CIS] | 6nos | 2027-01-20 | 2027-01-28 | 8 | NotStart
L3 | 3.2 | COL | P1_CN_19150 | CON¦MR¦COL¦NT¦ Columns Work [8nos-WF-1C55,63,70,71,54,61,68,69] at L3 Zone P-3.2 [NCIS] | 8nos | 2026-12-25 | 2027-01-13 | 19 | NotStart
L3 | 3.2 | COL | P1_CN_19160 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [8 nos] at L3 Zone P-3.2 [NCIS] | 8nos | 2027-01-14 | 2027-01-18 | 4 | NotStart
L3 | 3.2 | STB | P1_CN_19190 | CON¦MR¦STB¦NT¦ Steel Beam Installation [40 nos] at L3 Zone P-3.2 [NCIS] | 40nos | 2027-01-19 | 2027-01-27 | 8 | NotStart
L3 | 3.2 | MBR | P1_CN_19200 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L3 Zone P-3.2 [NCIS] | 11nos | 2027-01-28 | 2027-02-05 | 8 | NotStart
L3 | 3.2 | WAL | P1_CN_19170 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-LW10/ST-07/50] at L3 Zone P-3.2 [NCIS] | 1nos | 2027-01-29 | 2027-03-11 | 41 | NotStart
L3 | 3.2 | CRW | P1_CN_19180 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone P-3.2 [CIS] | — | 2027-03-12 | 2027-03-22 | 10 | NotStart
L3 | 3.2-T | COL | P1_CN_19110 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos-WF-1C56] at L3 Zone P-3.2 [NCIS] | 1nos | 2027-01-06 | 2027-01-14 | 8 | NotStart
L3 | 3.2-T | COL | P1_CN_19120 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L3 Zone P-3.2 [NCIS] | 1nos | 2027-01-15 | 2027-01-19 | 4 | NotStart
L3 | 3.2-T | STB | P1_CN_19130 | CON¦MR¦STB¦T¦ Steel Beam Installation [8 nos] at L3 Zone P-3.2 [NCIS] | 8nos | 2027-01-20 | 2027-01-28 | 8 | NotStart
L3 | 3.2-T | MBR | P1_CN_19140 | CON¦MR¦MBR¦T¦ Main Beam RC [1 nos] at L3 Zone P-3.2 [NCIS] | 1nos | 2027-01-29 | 2027-02-08 | 10 | NotStart
L3 | 3.3-T | COL | P1_CN_19410 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C79,80] at L3 Zone P-3.3 [NCIS] | 2nos | 2026-12-09 | 2026-12-17 | 8 | NotStart
L3 | 3.3-T | COL | P1_CN_19420 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L3 Zone P-3.3 [NCIS] | 2nos | 2026-12-18 | 2026-12-22 | 4 | NotStart
L3 | 3.3-T | STB | P1_CN_19430 | CON¦MR¦STB¦T¦ Steel Beam Installation [16 nos] at L3 Zone P-3.3 [NCIS] | 16nos | 2026-12-23 | 2026-12-25 | 2 | NotStart
L3 | 3.3-T | MBR | P1_CN_19440 | CON¦MR¦MBR¦T¦ Main Beam RC [2 nos] at L3 Zone P-3.3 [NCIS] | 2nos | 2026-12-28 | 2027-01-05 | 8 | NotStart
L3 | 3.3CIS-T | WAL | P1_CN_19480 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [4 nos-ST16/17, ST14/15, ST12/13, ST10/11] at L3 Zone P-3.3 [CIS] | 4nos | 2026-11-11 | 2026-12-09 | 28 | NotStart
L3 | 3.3CIS-T | CRW | P1_CN_19490 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L3 Zone P-3.3 [CIS] | — | 2026-12-10 | 2026-12-18 | 8 | NotStart
L3 | 3.3CIS-T | SLB | P1_CN_19450 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [730 m²] at L3 Zone P-3.3 [CIS] | 730m² | 2026-12-15 | 2026-12-28 | 13 | NotStart
L3 | 3.3CIS-T | COL | P1_CN_19460 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C81,90,91,92,99,100] at L3 Zone P-3.3 [CIS] | 6nos | 2026-12-29 | 2027-01-18 | 20 | NotStart
L3 | 3.3CIS-T | COL | P1_CN_19470 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L3 Zone P-3.3 [CIS] | 6nos | 2027-01-19 | 2027-01-21 | 2 | NotStart
L3 | 3.3CIS-T | STB | P1_CN_19500 | CON¦MR¦STB¦T¦ Steel Beam Installation [24 nos] at L3 Zone P-3.3 [CIS] | 24nos | 2027-01-22 | 2027-02-01 | 10 | NotStart
L3 | 3.3CIS-T | MBR | P1_CN_19510 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L3 Zone P-3.3 [CIS] | 9nos | 2027-02-02 | 2027-02-10 | 8 | NotStart
L3 | 3.4 | COL | P1_CN_19370 | CON¦MR¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C78,96] at L3 Zone P-3.4 [NCIS] | 2nos | 2027-01-05 | 2027-01-13 | 8 | NotStart
L3 | 3.4 | COL | P1_CN_19380 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L3 Zone P-3.4 [NCIS] | 2nos | 2027-01-14 | 2027-01-18 | 4 | NotStart
L3 | 3.4 | STB | P1_CN_19390 | CON¦MR¦STB¦NT¦ Steel Beam Installation [11 nos] at L3 Zone P-3.4 [NCIS] | 11nos | 2027-01-19 | 2027-01-27 | 8 | NotStart
L3 | 3.4 | MBR | P1_CN_19400 | CON¦MR¦MBR¦NT¦ Main Beam RC [5 nos] at L3 Zone P-3.4 [NCIS] | 5nos | 2027-01-28 | 2027-02-05 | 8 | NotStart
L3 | 3.4-T | COL | P1_CN_19330 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [4nos-WF-1C88,89,97,98] at L3 Zone P-3.4 [NCIS] | 4nos | 2027-01-05 | 2027-01-13 | 8 | NotStart
L3 | 3.4-T | COL | P1_CN_19340 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [4 nos] at L3 Zone P-3.4 [NCIS] | 4nos | 2027-01-14 | 2027-01-18 | 4 | NotStart
L3 | 3.4-T | STB | P1_CN_19350 | CON¦MR¦STB¦T¦ Steel Beam Installation [32 nos] at L3 Zone P-3.4 [NCIS] | 32nos | 2027-01-19 | 2027-01-27 | 8 | NotStart
L3 | 3.4-T | MBR | P1_CN_19360 | CON¦MR¦MBR¦T¦ Main Beam RC [4 nos] at L3 Zone P-3.4 [NCIS] | 4nos | 2027-01-28 | 2027-02-05 | 8 | NotStart
L4 | 1.1 | SLB | P1_CN_19520 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [540 m²] at L4 Zone P-1.1 [NCIS] | 540m² | 2027-03-05 | 2027-03-24 | 19 | NotStart
L4 | 1.2 | WAL | P1_CN_19600 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-ST45/46] at L4 Zone P-1.2 [NCIS] | 1nos | 2026-12-08 | 2027-01-18 | 41 | NotStart
L4 | 1.2 | SLB | P1_CN_19570 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [2315 m²] at L4 Zone P-1.2 [NCIS] | 2315m² | 2027-01-06 | 2027-01-25 | 19 | NotStart
L4 | 1.2 | CRW | P1_CN_19610 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone P-1.2 [CIS] | — | 2027-01-19 | 2027-01-27 | 8 | NotStart
L4 | 1.2 | COL | P1_CN_19580 | CON¦MR¦COL¦NT¦ Columns Work [6 nos-WF-1C30,31,33,38,43,49] at L4 Zone P-1.2 [NCIS] | 6nos | 2027-01-26 | 2027-02-12 | 17 | NotStart
L4 | 1.2 | COL | P1_CN_19590 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L4 Zone P-1.2 [NCIS] | 6nos | 2027-02-15 | 2027-02-23 | 8 | NotStart
L4 | 1.2 | STB | P1_CN_19620 | CON¦MR¦STB¦NT¦ Steel Beam Installation [38 nos] at L4 Zone P-1.2 [NCIS] | 38nos | 2027-02-24 | 2027-03-04 | 8 | NotStart
L4 | 1.2 | MBR | P1_CN_19630 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L4 Zone P-1.2 [NCIS] | 11nos | 2027-03-05 | 2027-03-15 | 10 | NotStart
L4 | 1.2-T | COL | P1_CN_19530 | CON¦MR¦COL¦T¦ Columns Work [15nos-WF-1C34,35,36,39,40,41,44,45,46,47,50,51,52,53,WF-B2C53] at L4 Zone P-1.2 [NCIS] | 15nos | 2027-01-06 | 2027-02-03 | 28 | NotStart
L4 | 1.2-T | COL | P1_CN_19540 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [13 nos] at L4 Zone P-1.2 [NCIS] | 13nos | 2027-01-22 | 2027-02-10 | 19 | NotStart
L4 | 1.2-T | STB | P1_CN_19550 | CON¦MR¦STB¦T¦ Steel Beam Installation [72 nos] at L4 Zone P-1.2 [NCIS] | 72nos | 2027-02-05 | 2027-02-18 | 13 | NotStart
L4 | 1.2-T | MBR | P1_CN_19560 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L4 Zone P-1.2 [NCIS] | 9nos | 2027-02-17 | 2027-03-08 | 19 | NotStart
L4 | 3.1-T | SLB | P1_CN_19750 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1096 m²] at L4 Zone P-3.1 [NCIS] | 1096m² | 2027-02-02 | 2027-02-19 | 17 | NotStart
L4 | 3.1-T | COL | P1_CN_19760 | CON¦MR¦COL¦T¦ Columns Work [5nos-WF-1C57,58,65,72,73 + 1 nos] at L4 Zone P-3.1 [NCIS] | 6nos | 2027-02-22 | 2027-03-11 | 17 | NotStart
L4 | 3.1-T | COL | P1_CN_19770 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L4 Zone P-3.1 [NCIS] | 6nos | 2027-03-12 | 2027-03-16 | 4 | NotStart
L4 | 3.1-T | STB | P1_CN_19780 | CON¦MR¦STB¦T¦ Steel Beam Installation [29 nos] at L4 Zone P-3.1 [NCIS] | 29nos | 2027-03-17 | 2027-03-23 | 6 | NotStart
L4 | 3.1-T | MBR | P1_CN_19790 | CON¦MR¦MBR¦T¦ Main Beam RC [13 nos] at L4 Zone P-3.1 [NCIS] | 13nos | 2027-03-24 | 2027-03-31 | 7 | NotStart
L4 | 3.1CIS-T | CRW | P1_CN_19810 | CON¦MR¦CRW¦T¦ Core Wall [Starter + Jumps + Casting + Curing] [1 nos-CW01] at L4 Zone P-3.1 [CIS] | 1nos | 2027-01-15 | 2027-02-12 | 28 | NotStart
L4 | 3.1CIS-T | WAL | P1_CN_19840 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [3 nos-ST-20/21, ST-04, ST-18/19 + 1 nos] at L4 Zone P-3.1 [CIS] | 4nos | 2027-01-15 | 2027-02-12 | 28 | NotStart
L4 | 3.1CIS-T | SLB | P1_CN_19800 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [883 m²] at L4 Zone P-3.1 [CIS] | 883m² | 2027-01-29 | 2027-02-17 | 19 | NotStart
L4 | 3.1CIS-T | COL | P1_CN_19820 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C59,66,67,74,82,83 + 1 nos] at L4 Zone P-3.1 [CIS] | 7nos | 2027-02-11 | 2027-02-24 | 13 | NotStart
L4 | 3.1CIS-T | CRW | P1_CN_19850 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone P-3.1 [CIS] | — | 2027-02-15 | 2027-02-23 | 8 | NotStart
L4 | 3.1CIS-T | COL | P1_CN_19830 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [7 nos] at L4 Zone P-3.1 [CIS] | 7nos | 2027-02-25 | 2027-03-01 | 4 | NotStart
L4 | 3.1CIS-T | STB | P1_CN_19860 | CON¦MR¦STB¦T¦ Steel Beam Installation [21 nos] at L4 Zone P-3.1 [CIS] | 21nos | 2027-03-02 | 2027-03-10 | 8 | NotStart
L4 | 3.1CIS-T | MBR | P1_CN_19870 | CON¦MR¦MBR¦T¦ Main Beam RC [6 nos] at L4 Zone P-3.1 [CIS] | 6nos | 2027-03-11 | 2027-03-19 | 8 | NotStart
L4 | 3.2 | SLB | P1_CN_19680 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1088 m²] at L4 Zone P-3.2 [NCIS] | 1088m² | 2027-02-08 | 2027-02-25 | 17 | NotStart
L4 | 3.2 | COL | P1_CN_19690 | CON¦MR¦COL¦NT¦ Columns Work [8nos-WF-1C55,63,70,71,54,61,68,69] at L4 Zone P-3.2 [NCIS] | 8nos | 2027-02-26 | 2027-03-17 | 19 | NotStart
L4 | 3.2 | COL | P1_CN_19700 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [8 nos] at L4 Zone P-3.2 [NCIS] | 8nos | 2027-03-18 | 2027-03-22 | 4 | NotStart
L4 | 3.2 | STB | P1_CN_19730 | CON¦MR¦STB¦NT¦ Steel Beam Installation [40 nos] at L4 Zone P-3.2 [NCIS] | 40nos | 2027-03-23 | 2027-03-31 | 8 | NotStart
L4 | 3.2 | WAL | P1_CN_19710 | CON¦MR¦WAL¦NT¦ Staircase / Lift Wall [Rebar + Formwork + Casting] [1 nos-LW10/ST-07/50] at L4 Zone P-3.2 [NCIS] | 1nos | 2027-03-23 | 2027-05-03 | 41 | NotStart
L4 | 3.2 | MBR | P1_CN_19740 | CON¦MR¦MBR¦NT¦ Main Beam RC [11 nos] at L4 Zone P-3.2 [NCIS] | 11nos | 2027-04-01 | 2027-04-09 | 8 | NotStart
L4 | 3.2 | CRW | P1_CN_19720 | CON¦MR¦CRW¦NT¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone P-3.2 [CIS] | — | 2027-05-04 | 2027-05-12 | 8 | NotStart
L4 | 3.2-T | COL | P1_CN_19640 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [1nos-WF-1C56] at L4 Zone P-3.2 [NCIS] | 1nos | 2027-02-09 | 2027-02-17 | 8 | NotStart
L4 | 3.2-T | COL | P1_CN_19650 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [1 nos] at L4 Zone P-3.2 [NCIS] | 1nos | 2027-02-18 | 2027-02-22 | 4 | NotStart
L4 | 3.2-T | STB | P1_CN_19660 | CON¦MR¦STB¦T¦ Steel Beam Installation [8 nos] at L4 Zone P-3.2 [NCIS] | 8nos | 2027-02-23 | 2027-03-03 | 8 | NotStart
L4 | 3.2-T | MBR | P1_CN_19670 | CON¦MR¦MBR¦T¦ Main Beam RC [1 nos] at L4 Zone P-3.2 [NCIS] | 1nos | 2027-03-04 | 2027-03-12 | 8 | NotStart
L4 | 3.3-T | SLB | P1_CN_19970 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [415 m²] at L4 Zone P-3.3 [NCIS] | 415m² | 2027-01-06 | 2027-01-25 | 19 | NotStart
L4 | 3.3-T | COL | P1_CN_19980 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C79,80] at L4 Zone P-3.3 [NCIS] | 2nos | 2027-01-26 | 2027-02-03 | 8 | NotStart
L4 | 3.3-T | COL | P1_CN_19990 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L4 Zone P-3.3 [NCIS] | 2nos | 2027-02-04 | 2027-02-08 | 4 | NotStart
L4 | 3.3-T | STB | P1_CN_20000 | CON¦MR¦STB¦T¦ Steel Beam Installation [16 nos] at L4 Zone P-3.3 [NCIS] | 16nos | 2027-02-09 | 2027-02-11 | 2 | NotStart
L4 | 3.3-T | MBR | P1_CN_20010 | CON¦MR¦MBR¦T¦ Main Beam RC [2 nos] at L4 Zone P-3.3 [NCIS] | 2nos | 2027-02-12 | 2027-02-22 | 10 | NotStart
L4 | 3.3CIS-T | WAL | P1_CN_20050 | CON¦MR¦WAL¦T¦ Staircase / Lift Wall [4 nos-ST-16/17, ST-14/15, ST-12/13, ST-10/11] at L4 Zone P-3.3 [CIS] | 4nos | 2026-12-21 | 2027-01-18 | 28 | NotStart
L4 | 3.3CIS-T | CRW | P1_CN_20060 | CON¦MR¦CRW¦T¦ Beam Link to Core Wall [Starter + Jumps + Casting + Curing] at L4 Zone P-3.3 [CIS] | — | 2027-01-19 | 2027-01-27 | 8 | NotStart
L4 | 3.3CIS-T | SLB | P1_CN_20020 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [730 m²] at L4 Zone P-3.3 [CIS] | 730m² | 2027-02-11 | 2027-02-24 | 13 | NotStart
L4 | 3.3CIS-T | COL | P1_CN_20030 | CON¦MR¦COL¦T¦ Columns Work [6nos-WF-1C81,90,91,92,99,100] at L4 Zone P-3.3 [CIS] | 6nos | 2027-02-25 | 2027-03-17 | 20 | NotStart
L4 | 3.3CIS-T | COL | P1_CN_20040 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [6 nos] at L4 Zone P-3.3 [CIS] | 6nos | 2027-03-18 | 2027-03-22 | 4 | NotStart
L4 | 3.3CIS-T | STB | P1_CN_20070 | CON¦MR¦STB¦T¦ Steel Beam Installation [24 nos] at L4 Zone P-3.3 [CIS] | 24nos | 2027-03-23 | 2027-03-31 | 8 | NotStart
L4 | 3.3CIS-T | MBR | P1_CN_20080 | CON¦MR¦MBR¦T¦ Main Beam RC [9 nos] at L4 Zone P-3.3 [CIS] | 9nos | 2027-04-01 | 2027-04-09 | 8 | NotStart
L4 | 3.4 | SLB | P1_CN_19920 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [933 m²] at L4 Zone P-3.4 [NCIS] | 933m² | 2027-02-08 | 2027-02-25 | 17 | NotStart
L4 | 3.4 | COL | P1_CN_19930 | CON¦MR¦COL¦NT¦ Columns Work [Rebar + Formwork + Casting + Curing] [2nos-WF-1C78,96] at L4 Zone P-3.4 [NCIS] | 2nos | 2027-02-26 | 2027-03-08 | 10 | NotStart
L4 | 3.4 | COL | P1_CN_19940 | CON¦MR¦COL¦NT¦ Columns Work Cobel [Formwork + Rebar + Casting] [2 nos] at L4 Zone P-3.4 [NCIS] | 2nos | 2027-03-09 | 2027-03-11 | 2 | NotStart
L4 | 3.4 | STB | P1_CN_19950 | CON¦MR¦STB¦NT¦ Steel Beam Installation [11 nos] at L4 Zone P-3.4 [NCIS] | 11nos | 2027-03-12 | 2027-03-22 | 10 | NotStart
L4 | 3.4 | MBR | P1_CN_19960 | CON¦MR¦MBR¦NT¦ Main Beam RC [5 nos] at L4 Zone P-3.4 [NCIS] | 5nos | 2027-03-23 | 2027-03-31 | 8 | NotStart
L4 | 3.4-T | COL | P1_CN_19880 | CON¦MR¦COL¦T¦ Columns Work [Rebar + Formwork + Casting + Curing] [4nos-WF-1C88,89,97,98] at L4 Zone P-3.4 [NCIS] | 4nos | 2027-02-08 | 2027-02-16 | 8 | NotStart
L4 | 3.4-T | COL | P1_CN_19890 | CON¦MR¦COL¦T¦ Columns Work Cobel [Formwork + Rebar + Casting] [4 nos] at L4 Zone P-3.4 [NCIS] | 4nos | 2027-02-17 | 2027-02-19 | 2 | NotStart
L4 | 3.4-T | STB | P1_CN_19900 | CON¦MR¦STB¦T¦ Steel Beam Installation [32 nos] at L4 Zone P-3.4 [NCIS] | 32nos | 2027-02-22 | 2027-03-02 | 8 | NotStart
L4 | 3.4-T | MBR | P1_CN_19910 | CON¦MR¦MBR¦T¦ Main Beam RC [4 nos] at L4 Zone P-3.4 [NCIS] | 4nos | 2027-03-03 | 2027-03-11 | 8 | NotStart
L5 | 1.1 | SLB | P1_CN_20090 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [540 m²] at L2 Zone P-1.1 [NCIS] | 540m² | 2027-03-25 | 2027-04-13 | 19 | NotStart
L5 | 1.1 | SLB | P1_CN_20100 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [540 m²] at L3 Zone P-1.1 [NCIS] | 540m² | 2027-04-14 | 2027-05-03 | 19 | NotStart
L5 | 1.2 | SLB | P1_CN_20120 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [2315 m²] at L2 Zone P-1.2 [NCIS] | 2315m² | 2027-03-16 | 2027-04-02 | 17 | NotStart
L5 | 1.2 | SLB | P1_CN_20140 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1240 m²] at L5 Zone P-1.2 [NCIS] | 1240m² | 2027-03-16 | 2027-04-26 | 41 | NotStart
L5 | 1.2 | SLB | P1_CN_20130 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [2315 m²] at L3 Zone P-1.2 [NCIS] | 2315m² | 2027-04-05 | 2027-04-22 | 17 | NotStart
L5 | 1.2-T | SLB | P1_CN_20110 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [1075 m²] at L5 Zone P-1.2 [NCIS] | 1075m² | 2027-03-09 | 2027-05-17 | 69 | NotStart
L5 | 3.1-T | SLB | P1_CN_20190 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1096 m²] at L2 Zone P-3.1 [NCIS] | 1096m² | 2027-04-01 | 2027-04-20 | 19 | NotStart
L5 | 3.1-T | SLB | P1_CN_20210 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1096 m²] at L5 Zone P-3.1 [NCIS] | 1096m² | 2027-04-01 | 2027-05-12 | 41 | NotStart
L5 | 3.1-T | SLB | P1_CN_20200 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1096 m²] at L3 Zone P-3.1 [NCIS] | 1096m² | 2027-04-21 | 2027-05-10 | 19 | NotStart
L5 | 3.1CIS-T | SLB | P1_CN_20220 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [883 m²] at L5 Zone P-3.1 [CIS] | 883m² | 2027-03-22 | 2027-05-28 | 67 | NotStart
L5 | 3.2 | SLB | P1_CN_20160 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1088 m²] at L2 Zone P-3.2 [NCIS] | 1088m² | 2027-04-10 | 2027-04-23 | 13 | NotStart
L5 | 3.2 | SLB | P1_CN_20180 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [953 m²] at L5 Zone P-3.2 [NCIS] | 953m² | 2027-04-12 | 2027-05-21 | 39 | NotStart
L5 | 3.2 | SLB | P1_CN_20170 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [1088 m²] at L3 Zone P-3.2 [NCIS] | 1088m² | 2027-04-24 | 2027-05-07 | 13 | NotStart
L5 | 3.2-T | SLB | P1_CN_20150 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [135 m²] at L5 Zone P-3.2 [NCIS] | 135m² | 2027-03-15 | 2027-04-23 | 39 | NotStart
L5 | 3.3-T | SLB | P1_CN_20270 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [415 m²] at L2 Zone P-3.3 [NCIS] | 415m² | 2027-02-23 | 2027-03-12 | 17 | NotStart
L5 | 3.3-T | SLB | P1_CN_20280 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [415 m²] at L3 Zone P-3.3 [NCIS] | 415m² | 2027-03-15 | 2027-04-01 | 17 | NotStart
L5 | 3.3CIS-T | SLB | P1_CN_20290 | CON¦MR¦SLB¦T¦ Slab [ Scaffold + Rebar + Casting] [730 m²] at L5 Zone P-3.3 [CIS] | 730m² | 2027-04-10 | 2027-05-29 | 49 | NotStart
L5 | 3.4 | SLB | P1_CN_20240 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [933 m²] at L2 Zone P-3.4 [NCIS] | 933m² | 2027-04-01 | 2027-04-20 | 19 | NotStart
L5 | 3.4 | SLB | P1_CN_20260 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [659 m²] at L5 Zone P-3.4 [NCIS] | 659m² | 2027-04-01 | 2027-05-12 | 41 | NotStart
L5 | 3.4 | SLB | P1_CN_20250 | CON¦MR¦SLB¦NT¦ Slab [Scaffold + Rebar + Casting] [933 m²] at L3 Zone P-3.4 [NCIS] | 933m² | 2027-04-21 | 2027-05-10 | 19 | NotStart
L5 | 3.4-T | SLB | P1_CN_20230 | CON¦MR¦SLB¦T¦ Slab [Scaffold + Rebar + Casting] [274 m²] at L5 Zone P-3.4 [NCIS] | 274m² | 2027-03-12 | 2027-05-20 | 69 | NotStart

## 6_区域工作量汇总
各区域工作量汇总（按专业拆分）
工程量来源=活动名内标注(m²面积/m³方量/nos数量)。含L5 Transfer归还楼板。COL柱·MBR/STB梁·SLB板·EXC挖土·WAL/CRW墙筒·DEM拆除·EAR土方·PIL桩·RCW/RCWDT海工。
区域(建筑/楼层/小区) | EXC | EAR | DEM | PIL | COL | MBR | STB | SLB | WAL | CRW | RCW | RCWDT | 合计
EB / B2 / 3.3 | — | — | — | — | 7 | — | — | — | — | — | — | — | 7nos
EB / B2 / EB2-2.1 | — | — | — | 9 | 5 | — | — | — | — | 2 | — | — | 16nos
EB / B2 / EB2-2.2 | — | — | — | 4 | 4 | — | — | — | — | — | — | — | 8nos
EB / B2 / EB2-2.3 | — | — | — | 6 | 6 | — | — | — | — | — | — | — | 12nos
EB / B2 / EB2-2.4 | — | — | — | 4 | 3 | — | — | — | — | — | — | — | 7nos
EB / B2 / EB2-3.1A-1 | — | — | — | 4 | 4 | — | — | — | — | — | — | — | 8nos
EB / B2 / EB2-3.1A-2+3.2-2 | — | — | — | 2 | 8 | — | — | — | — | — | — | — | 10nos
EB / B2 / EB2-3.2-1 | — | — | — | — | 3 | — | — | — | — | — | — | — | 3nos
EB / B2 / EB2-3.4+3.5 | — | — | — | — | 1 | — | — | — | — | 1 | — | — | 2nos
EB / B1 / S2.1 | — | — | 1755㎡ | — | 2 | — | — | 1061㎡ 12 | — | 2 | — | — | 2816m²+16nos
EB / B1 / S2.2 | — | — | 630㎡ | — | 4 | — | — | 614㎡ | — | — | — | — | 1244m²+4nos
EB / B1 / S2.3 | — | — | 789㎡ | — | 4 | — | — | 780㎡ | — | — | — | — | 1569m²+4nos
EB / B1 / S2.4 | — | — | 510㎡ | — | 5 | — | — | 599㎡ 4 | — | — | — | — | 1108m²+9nos
EB / B1 / S5 | — | — | 757㎡ | — | 2 | — | — | 380㎡ | — | — | — | — | 1137m²+2nos
EB / B1 / S6 | — | — | 1038㎡ | — | 7 | — | — | 1051㎡ 3 | — | — | — | — | 2089m²+10nos
EB / B1 / S7 | — | — | 604㎡ | — | 5 | — | — | 763㎡ 13 | — | — | — | — | 1367m²+18nos
EB / B1 / S8 | — | — | 1028㎡ | — | 9 | — | — | 1181㎡ 10 | — | 2 | — | — | 2209m²+21nos
EB / L1 / 4.1 | — | — | — | — | 8 | 2 | 9 | 770㎡ 8 | — | — | — | — | 770m²+27nos
EB / L1 / 4.1CIS-T | — | — | — | — | 10 | 24 | 44 | 1277㎡ 42 | 5 | 2 | — | — | 1277m²+127nos
EB / L1 / 4.2 | — | — | — | — | 10 | 5 | 22 | 718㎡ 17 | — | — | — | — | 718m²+54nos
EB / L1 / 4.2-T | — | — | — | — | 8 | 3 | 21 | 737㎡ 1 | — | — | — | — | 737m²+33nos
EB / L1 / 4.3-T | — | — | — | — | 12 | 3 | 23 | 741㎡ 13 | — | — | — | — | 741m²+51nos
EB / L1 / 4.3CIS-T | — | — | — | — | 2 | 8 | 17 | 493㎡ 17 | 2 | — | — | — | 493m²+46nos
EB / L1 / 4.4 | — | — | — | — | 16 | 8 | — | 1209㎡ 39 | — | 1 | — | — | 1209m²+64nos
EB / L1 / 4.4-OT | — | — | — | — | 20 | 8 | 40 | 1328㎡ 62 | — | — | — | — | 1328m²+130nos
EB / L1 / B2.1 | — | — | 1148㎡ | — | — | — | — | — | — | — | — | — | 1148m²
EB / L1 / B2.2 | — | — | 645㎡ | — | — | — | — | — | — | — | — | — | 645m²
EB / L1 / B2.3 | — | — | 911㎡ | — | — | — | — | — | — | — | — | — | 911m²
EB / L1 / B2.4 | — | — | 491㎡ | — | — | — | — | — | — | — | — | — | 491m²
EB / L1 / B3.1 | — | — | 1875㎡ | — | — | — | — | — | — | — | — | — | 1875m²
EB / L1 / B3.2 | — | — | 730㎡ | — | — | — | — | — | — | — | — | — | 730m²
EB / L1 / B3.3+3.5 | — | — | 2529㎡ | — | — | — | — | — | — | — | — | — | 2529m²
EB / L1 / B3.4 | — | — | 311㎡ | — | — | — | — | — | — | — | — | — | 311m²
EB / L2 / 4.1 | — | — | — | — | 6 | 2 | 9 | 589㎡ | — | — | — | — | 589m²+17nos
EB / L2 / 4.1CIS-T | — | — | — | — | 14 | 24 | 44 | 1272㎡ | 5 | 1 | — | — | 1272m²+88nos
EB / L2 / 4.2 | — | — | — | — | 6 | 5 | 22 | — | — | — | — | — | 33nos
EB / L2 / 4.2-T | — | — | — | — | 6 | 3 | 21 | 882㎡ | — | — | — | — | 882m²+30nos
EB / L2 / 4.3-T | — | — | — | — | 14 | 3 | 23 | 943㎡ | — | — | — | — | 943m²+40nos
EB / L2 / 4.3CIS-T | — | — | — | — | 6 | 8 | 17 | 374㎡ | 3 | — | — | — | 374m²+34nos
EB / L2 / 4.4 | — | — | — | — | 10 | 8 | 40 | 750㎡ | — | — | — | — | 750m²+58nos
EB / L3 / 4.1 | — | — | — | — | 6 | 2 | 9 | 589㎡ | — | — | — | — | 589m²+17nos
EB / L3 / 4.1CIS-T | — | — | — | — | 14 | 24 | 44 | 1272㎡ | 5 | 1 | — | — | 1272m²+88nos
EB / L3 / 4.2 | — | — | — | — | 6 | 5 | 22 | — | — | — | — | — | 33nos
EB / L3 / 4.2-T | — | — | — | — | 6 | 3 | 21 | 882㎡ | — | — | — | — | 882m²+30nos
EB / L3 / 4.3-T | — | — | — | — | 14 | 3 | 23 | 943㎡ | — | — | — | — | 943m²+40nos
EB / L3 / 4.3CIS-T | — | — | — | — | 6 | 8 | 17 | 374㎡ | 3 | — | — | — | 374m²+34nos
EB / L3 / 4.4 | — | — | — | — | 10 | 8 | 40 | 750㎡ | — | — | — | — | 750m²+58nos
EB / L4 / 4.1 | — | — | — | — | 6 | 2 | 9 | 589㎡ | — | — | — | — | 589m²+17nos
EB / L4 / 4.1CIS-T | — | — | — | — | 14 | 24 | 44 | 1272㎡ | 5 | 1 | — | — | 1272m²+88nos
EB / L4 / 4.2 | — | — | — | — | 6 | 5 | 22 | 887㎡ | — | — | — | — | 887m²+33nos
EB / L4 / 4.2-T | — | — | — | — | 6 | 3 | 21 | — | — | — | — | — | 30nos
EB / L4 / 4.3-T | — | — | — | — | 14 | 3 | 23 | 943㎡ | — | — | — | — | 943m²+40nos
EB / L4 / 4.3CIS-T | — | — | — | — | 6 | 8 | 17 | 374㎡ | 3 | — | — | — | 374m²+34nos
EB / L4 / 4.4 | — | — | — | — | 10 | 8 | 40 | 750㎡ | — | — | — | — | 750m²+58nos
EB / L5 / 1 | — | — | — | — | — | — | — | 323㎡ | — | — | — | — | 323m²
EB / L5 / 2 | — | — | — | — | — | — | — | 2616㎡ | — | — | — | — | 2616m²
EB / L5 / 4.1 | — | — | — | — | — | — | — | — | — | 1 | — | — | 1nos
EB / L5 / 4.1CIS | — | — | — | — | — | — | — | 589㎡ | — | — | — | — | 589m²
EB / L5 / 4.1CIST | — | — | — | — | — | — | — | 1272㎡ | — | — | — | — | 1272m²
EB / L5 / 4.3 | bar: EXC to 合计
NB / B2 / B2-S1+1a | 8200㎥ | — | — | — | 12 | — | — | 1635㎡ 13 | — | 1 | — | — | 1635m²+8200m³+26nos
NB / B2 / B2-S10 | 4900㎥ | — | — | — | 11 | — | — | 955㎡ 11 | — | — | — | — | 955m²+4900m³+22nos
NB / B2 / B2-S11 | 3100㎥ | — | — | — | 8 | — | — | 610㎡ | 1 | — | — | — | 610m²+3100m³+9nos
NB / B2 / B2-S12 | 6600㎥ | — | — | — | 14 | — | — | 1291㎡ 14 | 1 | 1 | — | — | 1291m²+6600m³+30nos
NB / B2 / B2-S13 | 3400㎥ | — | — | — | 9 | — | — | 695㎡ 9 | — | — | — | — | 695m²+3400m³+18nos
NB / B2 / B2-S14 | 3200㎥ | — | — | — | 9 | — | — | 622㎡ 9 | — | — | — | — | 622m²+3200m³+18nos
NB / B2 / B2-S2+S2a | 8700㎥ | — | — | — | 11 | — | — | 1711㎡ 14 | 1 | — | — | — | 1711m²+8700m³+26nos
NB / B2 / B2-S3 | 6800㎥ | — | — | — | 9 | — | — | 1354㎡ 10 | — | 1 | — | — | 1354m²+6800m³+20nos
NB / B2 / B2-S4 | 6600㎥ | — | — | — | 9 | — | — | 1308㎡ 10 | — | 1 | — | — | 1308m²+6600m³+20nos
NB / B2 / B2-S5 | 7500㎥ | — | — | — | 11 | — | — | 1496㎡ 15 | — | 2 | — | — | 1496m²+7500m³+28nos
NB / B2 / B2-S6+6a | 7100㎥ | — | — | — | 11 | — | — | 1465㎡ 11 | 1 | — | — | — | 1465m²+7100m³+23nos
NB / B2 / B2-S7 | 5100㎥ | — | — | — | 6 | — | — | 1030㎡ 6 | — | 1 | — | — | 1030m²+5100m³+13nos
NB / B2 / B2-S8 | 4900㎥ | — | — | — | 12 | — | — | 989㎡ 12 | — | — | — | — | 989m²+4900m³+24nos
NB / B2 / B2-S8a+14a+13a | 7200㎥ | — | — | — | 20 | — | — | 1401㎡ 21 | — | — | — | — | 1401m²+7200m³+41nos
NB / B2 / B2-S9 | 4300㎥ | — | — | — | 12 | — | — | 871㎡ 12 | — | — | — | — | 871m²+4300m³+24nos
NB / B1 / A-01+03 | — | — | — | — | 10 | — | — | 971㎡ 6 | — | — | — | — | 971m²+16nos
NB / B1 / A-02+B-01 | — | — | — | — | 15 | — | — | 1180㎡ 5 | — | — | — | — | 1180m²+20nos
NB / B1 / A-04 | — | — | — | — | 7 | — | — | 563㎡ | — | — | — | — | 563m²+7nos
NB / B1 / A-05+06 | — | — | — | — | 16 | — | — | 999㎡ 7 | — | — | — | — | 999m²+23nos
NB / B1 / A-07 | — | — | — | — | 8 | — | — | 571㎡ 4 | — | — | — | — | 571m²+12nos
NB / B1 / B-02 | — | — | — | — | 9 | — | — | 720㎡ | — | — | — | — | 720m²+9nos
NB / B1 / B-03 | — | — | — | — | 15 | — | — | 1201㎡ 24 | 1 | 1 | — | — | 1201m²+41nos
NB / B1 / B-04+04A | — | — | — | — | 14 | — | — | 1121㎡ 37 | — | — | — | — | 1121m²+51nos
NB / B1 / C-01a+b | 13000㎥ | — | — | — | 12 | — | — | 1343㎡ 10 | 1 | — | — | — | 1343m²+13000m³+23nos
NB / B1 / C-02 | 21000㎥ | — | — | — | 5 | — | — | 1457㎡ 29 | 1 | — | — | — | 1457m²+21000m³+35nos
NB / B1 / D-01 | 11000㎥ | — | — | — | 13 | — | — | 1349㎡ 22 | — | — | — | — | 1349m²+11000m³+35nos
NB / B1 / D-02 | 13200㎥ | — | — | — | 14 | — | — | 1611㎡ 15 | — | — | — | — | 1611m²+13200m³+29nos
NB / B1 / E-01 | 13800㎥ 3 | — | — | — | 9 | — | — | 1415㎡ | — | 1 | — | — | 1415m²+13800m³+13nos
NB / B1 / F-01 | 19000㎥ | — | — | — | 14 | — | — | 1941㎡ 8 | — | 1 | — | — | 1941m²+19000m³+23nos
NB / B1 / F-02 | 9000㎥ | — | — | — | 6 | — | — | 1001㎡ 32 | — | 2 | — | — | 1001m²+9000m³+40nos
NB / B1 / S-1 | — | — | — | — | 14 | — | — | 976㎡ 8 | — | — | — | — | 976m²+22nos
NB / B1 / S-2 | — | — | — | — | 12 | — | — | 28 | — | — | — | — | 40nos
NB / B1 / S-3 | — | — | — | — | 25 | — | — | 1915㎡ 45 | — | — | — | — | 1915m²+70nos
NB / B1 / S-4 | — | — | — | — | 19 | — | — | 1514㎡ 5 | — | — | — | — | 1514m²+24nos
NB / B1 / S-5 | — | — | — | — | 11 | — | — | 1510㎡ 30 | — | — | — | — | 1510m²+41nos
NB / B1 / S-6 | — | — | — | — | 8 | — | — | 1364㎡ 22 | — | — | — | — | 1364m²+30nos
NB / B1 / S-7 | — | — | — | — | 14 | — | — | 1539㎡ 33 | — | — | — | — | 1539m²+47nos
NB / B1 / S-8 | — | — | — | — | 9 | — | — | 836㎡ | — | — | — | — | 836m²+9nos
NB / L1 / 2.1 | — | — | — | — | 4 | 3 | — | 373㎡ 25 | — | 1 | — | — | 373m²+33nos
NB / L1 / 2.1-T | — | — | — | — | 6 | 7 | — | 524㎡ 1 | — | 1 | — | — | 524m²+15nos
NB / L1 / 2.1CIS | — | — | — | — | 10 | 15 | 38 | 518㎡ 21 | 2 | — | — | — | 518m²+86nos
NB / L1 / 2.1CIS-T | — | — | — | — | 4 | 4 | — | 153㎡ 3 | — | — | — | — | 153m²+11nos
NB / L1 / 2.2 | — | — | — | — | 2 | 12 | 26 | 218㎡ | — | — | — | — | 218m²+40nos
NB / L1 / 2.2-T | — | — | — | — | 10 | 10 | 66 | 634㎡ 1 | 1 | — | — | — | 634m²+88nos
NB / L1 / 2.3-T | — | — | — | — | 10 | 7 | 51 | 1174㎡ 8 | — | — | — | — | 1174m²+76nos
NB / L1 / 2.3CIS-T | — | — | — | — | 2 | 12 | 26 | 501㎡ 5 | — | 1 | — | — | 501m²+46nos
NB / L1 / 2.4 | — | — | — | — | — | 6 | — | — | — | — | — | — | 6nos
NB / L1 / 2.4-T | — | — | — | — | 12 | 6 | 35 | 1347㎡ 5 | — | 1 | — | — | 1347m²+59nos
NB / L1 / 2.6CIS | — | — | — | — | 8 | 5 | 7 | 956㎡ 4 | 2 | — | — | — | 956m²+26nos
NB / L1 / 2.6CIS-T | — | — | — | — | 8 | 13 | 16 | 850㎡ 9 | 1 | 1 | — | — | 850m²+48nos
NB / L2 / 2.1 | — | — | — | — | 2 | 3 | — | — | — | — | — | — | 5nos
NB / L2 / 2.1-T | — | — | — | — | 6 | 7 | — | 854㎡ | — | 1 | — | — | 854m²+14nos
NB / L2 / 2.1CIS | — | — | — | — | 12 | 15 | 38 | 559㎡ | 2 | — | — | — | 559m²+67nos
NB / L2 / 2.1CIS-T | — | — | — | — | 4 | 4 | — | 159㎡ | — | — | — | — | 159m²+8nos
NB / L2 / 2.2 | — | — | — | — | 8 | 12 | 26 | — | — | — | — | — | 46nos
NB / L2 / 2.2-T | — | — | — | — | 18 | 10 | 66 | 1413㎡ | — | 1 | — | — | 1413m²+95nos
NB / L2 / 2.3-T | — | — | — | — | 10 | 7 | 51 | 1173㎡ | — | — | — | — | 1173m²+68nos
NB / L2 / 2.3CIS-T | — | — | — | — | 6 | 12 | 26 | 501㎡ | — | 1 | — | — | 501m²+45nos
NB / L2 / 2.4 | — | — | — | — | — | 6 | — | 521㎡ | — | — | — | — | 521m²+6nos
NB / L2 / 2.4-T | — | — | — | — | 12 | 6 | 35 | 700㎡ | — | 1 | — | — | 700m²+54nos
NB / L2 / 2.6CIS | — | — | — | — | 4 | 5 | 7 | 476㎡ | 2 | — | — | — | 476m²+18nos
NB / L2 / 2.6CIS-T | — | — | — | — | 4 | 13 | 16 | 794㎡ | 1 | 1 | — | — | 794m²+35nos
NB / L3 / 2.1 | — | — | — | — | 2 | 3 | — | — | — | — | — | — | 5nos
NB / L3 / 2.1-T | — | — | — | — | 6 | 7 | — | 854㎡ | — | 1 | — | — | 854m²+14nos
NB / L3 / 2.1CIS | — | — | — | — | 12 | 15 | 38 | 560㎡ | 2 | — | — | — | 560m²+67nos
NB / L3 / 2.1CIS-T | — | — | — | — | 4 | 4 | — | 159㎡ | — | — | — | — | 159m²+8nos
NB / L3 / 2.2 | — | — | — | — | 8 | 12 | 26 | — | — | — | — | — | 46nos
NB / L3 / 2.2-T | — | — | — | — | 18 | 10 | 66 | 1413㎡ | — | 1 | — | — | 1413m²+95nos
NB / L3 / 2.3-T | — | — | — | — | 10 | 7 | 51 | 1173㎡ | — | — | — | — | 1173m²+68nos
NB / L3 / 2.3CIS-T | — | — | — | — | 6 | 12 | 26 | 501㎡ | — | 1 | — | — | 501m²+45nos
NB / L3 / 2.4 | — | — | — | — | — | 6 | — | 521㎡ | — | — | — | — | 521m²+6nos
NB / L3 / 2.4-T | — | — | — | — | 12 | 6 | 35 | 700㎡ | — | 1 | — | — | 700m²+54nos
NB / L3 / 2.6CIS | — | — | — | — | 4 | 5 | 7 | 476㎡ | 2 | — | — | — | 476m²+18nos
NB / L3 / 2.6CIS-T | — | — | — | — | 4 | 13 | 16 | 794㎡ | 1 | 1 | — | — | 794m²+35nos
NB / L4 / 2.1 | — | — | — | — | 2 | 3 | — | 666㎡ | — | — | — | — | 666m²+5nos
NB / L4 / 2.1-T | — | — | — | — | 6 | 7 | — | 503㎡ | — | 1 | — | — | 503m²+14nos
NB / L4 / 2.1CIS | — | — | — | — | 12 | 15 | 38 | 560㎡ | 2 | — | — | — | 560m²+67nos
NB / L4 / 2.1CIS-T | — | — | — | — | 4 | 4 | — | 159㎡ | — | — | — | — | 159m²+8nos
NB / L4 / 2.2 | — | — | — | — | 8 | 12 | 26 | — | — | — | — | — | 46nos
NB / L4 / 2.2-T | — | — | — | — | 18 | 10 | 66 | 1412㎡ | 1 | — | — | — | 1412m²+95nos
NB / L4 / 2.3-T | — | — | — | — | 10 | 7 | 51 | 1173㎡ | — | — | — | — | 1173m²+68nos
NB / L4 / 2.3CIS-T | — | — | — | — | 6 | 12 | 26 | 501㎡ | — | 1 | — | — | 501m²+45nos
NB / L4 / 2.4-T | — | — | — | — | 12 | 6 | 35 | 1221㎡ | — | 1 | — | — | 1221m²+54nos
NB / L4 / 2.6CIS | — | — | — | — | 4 | 5 | 7 | 476㎡ | 2 | — | — | — | 476m²+18nos
NB / L4 / 2.6CIS-T | — | — | — | — | 4 | 13 | 16 | 794㎡ | 1 | 1 | — | — | 794m²+35nos
NB / L5 / 2.1 | — | — | — | — | — | — | — | 910㎡ | — | — | — | — | 910m²
NB / L5 / 2.1-T | — | — | — | — | — | — | — | 662㎡ | — | — | — | — | 662m²
NB / L5 / 2.2 | — | — | — | — | — | — | — | 587㎡ | — | — | — | — | 587m²
NB / L5 / 2.2-T | — | — | — | — | — | — | — | 826㎡ | — | — | — | — | 826m²
NB / L5 / 2.3-T | — | — | — | — | — | — | — | 1671㎡ | — | — | — | — | 1671m²
NB / L5 / 2.4-T | — | — | — | — | — | — | — | 1221㎡ | — | — | — | — | 1221m²
NB / L5 / 2.6CIS | — | — | — | — | — | — | — | 476㎡ | — | — | — | — | 476m²
NB / L5 / 2.6CIS-T | — | — | — | — | — | — | — | 794㎡ | — | — | — | — | 794m²
MA / Deck / Deck | — | — | — | — | — | — | — | — | — | — | — | — | 132nos
MA / Deck / ZC1 | — | — | — | — | — | — | — | — | — | — | 5183㎡ 20 | 5183㎡ | 10366m²+20nos
MA / Deck / ZC2.1+2.2 | — | — | — | — | — | — | — | — | — | — | 4683㎡ | 4683㎡ | 9366m²
MA / Deck / ZC3.1a+3.2 | — | — | — | — | — | — | — | — | — | — | 2731㎡ | 2731㎡ | 5462m²
MA / Deck / ZC3.1b | — | — | — | — | — | — | — | — | — | — | 4748㎡ | 4748㎡ | 9496m²
MA / L1 / 1.1 | — | — | — | — | 10 | 8 | 32 | — | — | — | — | — | 50nos
MA / L1 / 1.2 | — | — | — | — | 20 | 11 | 38 | — | 1 | — | — | — | 70nos
MA / L1 / 1.2-T | — | — | — | — | 18 | 9 | 72 | — | — | — | — | — | 99nos
MA / L1 / 3.1-T | — | — | — | — | 12 | 13 | 29 | — | — | — | — | — | 54nos
MA / L1 / 3.1CIS-T | — | — | — | — | 14 | 6 | 21 | — | 4 | 1 | — | — | 46nos
MA / L1 / 3.2 | — | — | — | — | 10 | 11 | 40 | — | 1 | — | — | — | 62nos
MA / L1 / 3.2-T | — | — | — | — | 2 | 1 | 8 | — | — | — | — | — | 11nos
MA / L1 / 3.3-T | — | — | — | — | 2 | 2 | 16 | — | — | — | — | — | 20nos
MA / L1 / 3.3CIS-T | — | — | — | — | 12 | 9 | 24 | — | 4 | — | — | — | 49nos
MA / L1 / 3.4 | — | — | — | — | 10 | 5 | 11 | — | — | — | — | — | 26nos
MA / L1 / 3.4-T | — | — | — | — | 4 | 4 | 32 | — | — | — | — | — | 40nos
MA / L1 / TOP SLAB | — | — | — | — | — | — | — | 15867㎡ | — | — | — | — | 15867m²
MA / L2 / 1.1 | — | — | — | — | 10 | 8 | 32 | 540㎡ | — | — | — | — | 540m²+50nos
MA / L2 / 1.2 | — | — | — | — | 12 | 11 | 38 | — | 1 | — | — | — | 62nos
MA / L2 / 1.2-T | — | — | — | — | 30 | 9 | 72 | 2315㎡ | — | — | — | — | 2315m²+111nos
MA / L2 / 3.1-T | — | — | — | — | 12 | 13 | 29 | 1096㎡ | — | — | — | — | 1096m²+54nos
MA / L2 / 3.1CIS-T | — | — | — | — | 14 | 6 | 21 | 883㎡ | 4 | 1 | — | — | 883m²+46nos
MA / L2 / 3.2 | — | — | — | — | 16 | 11 | 40 | — | 1 | — | — | — | 68nos
MA / L2 / 3.2-T | — | — | — | — | 2 | 1 | 8 | 1088㎡ | — | — | — | — | 1088m²+11nos
MA / L2 / 3.3-T | — | — | — | — | 4 | 2 | 16 | 415㎡ | — | — | — | — | 415m²+22nos
MA / L2 / 3.3CIS-T | — | — | — | — | 12 | 9 | 24 | 730㎡ | 4 | — | — | — | 730m²+49nos
MA / L2 / 3.4 | — | — | — | — | 4 | 5 | 11 | — | — | — | — | — | 20nos
MA / L2 / 3.4-T | — | — | — | — | 6 | 4 | 32 | 933㎡ | — | — | — | — | 933m²+42nos
MA / L3 / 1.1 | — | — | — | — | 10 | 8 | 32 | 540㎡ | — | — | — | — | 540m²+50nos
MA / L3 / 1.2 | — | — | — | — | 12 | 1 | 38 | — | 1 | — | — | — | 52nos
MA / L3 / 1.2-T | — | — | — | — | 28 | 9 | 72 | 2315㎡ | — | — | — | — | 2315m²+109nos
MA / L3 / 3.1-T | — | — | — | — | 12 | 13 | 29 | 1096㎡ | — | — | — | — | 1096m²+54nos
MA / L3 / 3.1CIS-T | — | — | — | — | 14 | 6 | 21 | 883㎡ | 4 | 1 | — | — | 883m²+46nos
MA / L3 / 3.2 | — | — | — | — | 16 | 11 | 40 | — | 1 | — | — | — | 68nos
MA / L3 / 3.2-T | — | — | — | — | 2 | 1 | 8 | 1088㎡ | — | — | — | — | 1088m²+11nos
MA / L3 / 3.3-T | — | — | — | — | 4 | 2 | 16 | 415㎡ | — | — | — | — | 415m²+22nos
MA / L3 / 3.3CIS-T | — | — | — | — | 12 | 9 | 24 | 730㎡ | 4 | — | — | — | 730m²+49nos
MA / L3 / 3.4 | — | — | — | — | 4 | 5 | 11 | — | — | — | — | — | 20nos
MA / L3 / 3.4-T | — | — | — | — | 8 | 4 | 32 | 933㎡ | — | — | — | — | 933m²+44nos
MA / L4 / 1.1 | — | — | — | — | — | — | — | 540㎡ | — | — | — | — | 540m²
MA / L4 / 1.2 | — | — | — | — | 12 | 11 | 38 | 2315㎡ | 1 | — | — | — | 2315m²+62nos
MA / L4 / 1.2-T | — | — | — | — | 28 | 9 | 72 | — | — | — | — | — | 109nos
MA / L4 / 3.1-T | — | — | — | — | 12 | 13 | 29 | 1096㎡ | — | — | — | — | 1096m²+54nos
MA / L4 / 3.1CIS-T | — | — | — | — | 14 | 6 | 21 | 883㎡ | 4 | 1 | — | — | 883m²+46nos
MA / L4 / 3.2 | — | — | — | — | 16 | 11 | 40 | 1088㎡ | 1 | — | — | — | 1088m²+68nos
MA / L4 / 3.2-T | — | — | — | — | 2 | 1 | 8 | — | — | — | — | — | 11nos
MA / L4 / 3.3-T | — | — | — | — | 4 | 2 | 16 | 415㎡ | — | — | — | — | 415m²+22nos
MA / L4 / 3.3CIS-T | — | — | — | — | 12 | 9 | 24 | 730㎡ | 4 | — | — | — | 730m²+49nos
MA / L4 / 3.4 | — | — | — | — | 4 | 5 | 11 | 933㎡ | — | — | — | — | 933m²+20nos
MA / L4 / 3.4-T | — | — | — | — | 8 | 4 | 32 | — | — | — | — | — | 44nos
MA / L5 / 1.2 | — | — | — | — | — | — | — | 1240㎡ | — | — | — | — | 1240m²
MA / L5 / 1.2-T | — | — | — | — | — | — | — | 1075㎡ | — | — | — | — | 1075m²
MA / L5 / 3.1-T | — | — | — | — | — | — | — | 1096㎡ | — | — | — | — | 1096m²
MA / L5 / 3.1CIS-T | — | — | — | — | — | — | — | 883㎡ | — | — | — | — | 883m²
MA / L5 / 3.2 | — | — | — | — | — | — | — | 953㎡ | — | — | — | — | 953m²
MA / L5 / 3.2-T | — | — | — | — | — | — | — | 135㎡ | — | — | — | — | 135m²
MA / L5 / 3.3CIS-T | — | — | — | — | — | — | — | 730㎡ | — | — | — | — | 730m²
MA / L5 / 3.4 | — | — | — | — | — | — | — | 659㎡ | — | — | — | — | 659m²
MA / L5 / 3.4-T | — | — | — | — | — | — | — | 274㎡ | — | — | — | — | 274m²